## PBW_SUMMARY
UNIVERSITIES of WISCONSIN | [6 empty] | PROJECT BUDGET WORKSHEET SUMMARY Rev. 2025-05BR | CONSTRUCTION COST ANALYSIS: CONSTRUCTION COST ESCALATION VALUE CALCULATION
[8 empty] | 0 |  | NEW CONSTRUCTION & REMODELING COST SUBTOTAL
PROJECT TITLE: | X |  |  |  | Date Prepared: |  | 2025-04-30 | 0 |  | DEMOLITION SUBTOTAL
LOCATION: | X |  |  |  | Prepared By: |  | XXX | 0 |  | ADDITIONAL CONSTRUCTION & REMODELING COST SUBTOTAL
PROJECT TYPE ID: | X |  |  |  | Revised By: |  | XXX | 0 |  | FF&E: CONTRACTOR FURNISHED, CONTRACTOR INSTALLED (CFCI) SUBTOTAL
OPTION TITLE: | X |  |  |  | TOTAL PROJECT ESTIMATE: |  | 0 | 0 |  | CONSTRUCTION & REMODELING COST SUBTOTAL
[8 empty] | 0 | 0% | DESIGN CONTINGENCY
NEW BUILDING AREA | [7 empty] | 0 | 0% | OVERHEAD & PROFIT (OH&P)
ASF New Const | 0 |  |  |  | Base Date: |  | 2025-05-01 | 0 |  | HAZARDOUS MATERIALS ABATEMENT
GSF New Const | 0 | 0% | Efficiency |  | Base Date Index: |  | 8520.44 | 0 |  | UNESCALATED CONSTRUCTION COST SUBTOTAL
[5 empty] | Inflation Date: |  | 2029-07-01 | 0 | 1.2832 | ESCALATED CONSTRUCTION COST SUBTOTAL
[5 empty] | Inflation Date Index: |  | 10933.6486 | 0 |  | ESCALATION INCLUDED IN CONSTRUCTION COST SUBTOTAL
REMODELING AREA |  |  |  | NORMAL | Inflation Factor: |  | 1.2832
GSF Remodeling | 0 | [6 empty] | FURNISHINGS, FIXTURES, & EQUIPMENT COST ANALYSIS
GSF Total Bldg | 0 | 0% | Remodeling |  | Occupancy Date: |  |  | 0 |  | FF&E: CONTRACTOR FURNISHED, CONTRACTOR INSTALLED (CFCI)
[8 empty] | 0 | 0% | FF&E: OWNER FURNISHED, CONTRACTOR INSTALLED (OFCI) | 0 | FF&E:OFCI DESIGN FEE
|  | 0 | /ASF: Construction Cost (building & site) |  |  |  |  | 0 | 0% | FF&E: OWNER FURNISHED, OWNER INSTALLED (OFOI) | 0 | FF&E:OFOI ALLOWANCE
|  | 0 | /GSF: Construction Cost (building & site) |  |  |  |  | 0 |  | FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E) SUBTOTAL
|  | 0 | /ASF: Total Project Cost |  |  |  |  | ARCHITECT/ENGINEER DESIGN SERVICES COST ANALYSIS
|  | 0 | /GSF: Total Project Cost |  |  |  |  | 0 | 0% | BASIC SERVICES
[8 empty] | 0 | 0% | REIMBURSIBLE COSTS
[8 empty] | 0 |  | ARCHITECT/ENGINEER BASIC SERVICES SUBTOTAL
TOTAL CONSTRUCTION | [6 empty] | 0
CONSTRUCTION | [6 empty] | 0 | 0 | 0% | PRE-DESIGN
HAZARDOUS MATERIALS ABATEMENT | [6 empty] | 0 | 0 |  | LEED CERTIFICATION
[8 empty] | 0 | 0% | COMMISSIONING
TOTAL DESIGN FEES | [6 empty] | 0 | 0 |  | EIS/EIA CONSULTANT
DESIGN FEES (BASIC) | [6 empty] | 0 | 0 |  | CONSTRUCTION TESTING
DESIGN FEES (OTHER) | [6 empty] | 0 | 0 |  | TESTING & BALANCING
[8 empty] | 0 |  | CUSTOM LINE ITEMS SUBTOTAL
CONTINGENCY | [6 empty] | 0 | 0 |  | ADDITIONAL DESIGN SERVICES SUBTOTAL
MANAGEMENT FEES | [6 empty] | 0
FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E) | [6 empty] | 0
OWNER FURNISHED, CONTRACTOR INSTALLED (OFCI) | [6 empty] | 0
OWNER FURNISHED, OWNER INSTALLED (OFOI) | [6 empty] | 0
TOTAL BUDGET ESTIMATE | [6 empty] | 0
CAPITAL PROJECT REQUEST "Project Budget" Table |  |  |  |  | SBC "CAPITAL BUDGET REQUEST" Table |  |  | PBW_ALTERNATE_SUMMARY
[7 empty] | NORMAL | NO INFLATION
Construction: |  | $ | 0 | LINE 3A | Construction: | $ | 0 | 0
Hazardous Materials: |  | $ | 0 | LINE 1 | Design: | $ | 0 | 0
Total Construction: |  | $ | 0 | LINE 0 | DFD Fee: | $ | 0 | 0
Design Fees (Basic): |  | $ | 0 | LINE 3B | Contingency: | $ | 0 | 0
Design Fees (Other): |  | $ | 0 | LINE 4 | Equipment: | $ | 0 | 0
Total Design Fees: |  | $ | 0 |  | Inflation: | $ | 0 | 0
Contingency: |  | $ | 0 |  | TOTAL: | $ | 0 | 0
Management Fees: |  | $ | 0
Furnishings/Fixtures/Eqpt: |  | $ | 0
Total Budget Estimate: |  | $ | 0
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This worksheet will auto-complete based on Project Budget Worksheet (PBW).

## PBW
UNIVERSITIES of WISCONSIN | [6 empty] | PROJECT BUDGET WORKSHEET Rev. 2025-05BR
PROJECT TITLE: | X |  |  |  | Date Prepared: |  | 2025-04-30
LOCATION: | X |  |  |  | Prepared By: |  | XXX
PROJECT TYPE ID: | X |  |  |  | Revised By: |  | XXX
OPTION TITLE: | X |  |  |  | TOTAL PROJECT ESTIMATE: |  | 0
NEW BUILDING AREA | [5 empty] | ENR Index | Month/Year
ASF New Const | 0 |  |  |  | Base Date: | 8520.44 | 2025-05-01
GSF New Const | 0 | 0% | Efficiency |  | Inflation Date: | 10933.6486 | 2029-07-01
|  |  |  | NORMAL | Inflation Factor C (Calculated): |  | 1.2832
REMODELING AREA |  |  |  |  | Inflation Factor O (Override): |  | 1.2832
GSF Remodeling | 0 |  |  |  | Inflation Delta (O-C): |  | 0
GSF Total Bldg | 0 | 0% | Remodeling |  | Occupancy:
NEW CONSTRUCTION BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
Function A | 0 | 0 | 0 | 0 |  | 0
Function B | 0 | 0 | 0 | 0 |  | 0
Function C | 0 | 0 | 0 | 0 |  | 0
Function D | 0 | 0 | 0 | 0 |  | 0
Function E | 0 | 0 | 0 | 0 |  | 0
Function F | 0 | 0 | 0 | 0 |  | 0
Function G | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 |  | Subtotal: $ | 0
NEW CONSTRUCTION COST SUBTOTAL | [6 empty] | 0
REMODELING BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
Function H | 0 | 0 | 0 | 0 |  | 0
Function I | 0 | 0 | 0 | 0 |  | 0
Function J | 0 | 0 | 0 | 0 |  | 0
Function K | 0 | 0 | 0 | 0 |  | 0
Function L | 0 | 0 | 0 | 0 |  | 0
Function M | 0 | 0 | 0 | 0 |  | 0
Function N | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 |  | Subtotal: $ | 0 | 0
REMODELING BY TRADE
Trade Category |  |  | GSF | $/GSF | DFD $/GSF | Trade Cost
General | Notes
Surface Treatment | X |  | 0 | 17 | 17 | 0
Minor | X |  | 0 | 59 | 59 | 0
Partial | X |  | 0 | 99 | 99 | 0
Complete | X |  | 0 | 118 | 118 | 0
Plumbing
Minor | X |  | 0 | 19 | 19 | 0
Partial | X |  | 0 | 33 | 33 | 0
Complete | X |  | 0 | 37 | 37 | 0
Special Laboratory Needs | X |  | 0 | 70 | 70 | 0
Heating, Ventilating, & Air Conditioning
Minor | X |  | 0 | 26 | 26 | 0
Partial | X |  | 0 | 54 | 54 | 0
Complete | X |  | 0 | 81 | 81 | 0
Electrical
Minor | X |  | 0 | 21 | 21 | 0
Partial | X |  | 0 | 36 | 36 | 0
Complete | X |  | 0 | 46 | 46 | 0
[5 empty] | Subtotal: $ | 0
REMODELING COST SUBTOTAL (cell will highlight red if Remodeling by Space Type and Remodeling by Trade sections are both used) | [6 empty] | 0
NEW CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
PROJECT TITLE: | X
NEW CONSTRUCTION & REMODELING COST SUBTOTAL (from page 1) | [6 empty] | 0
ADDITIONAL CONSTRUCTION & REMODELING COSTS:
HEADING NAME OR ITEM CODE | ITEM DESCRIPTION |  |  | QUANTITY | UNIT | UNIT COST | SUBTOTAL
DEMO | DEMOLITION (RAZING GROSS SQUARE FOOTAGE) |  |  | 0 | GSF | 21.1498 | 0
ADDITIONAL CONSTRUCTION & REMODELING COSTS
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
ADDITIONAL CONSTRUCTION & REMODELING COSTS: | [6 empty] | 0
FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E): CONTRACTOR FURNISHED, CONTRACTOR INSTALLED (CFCI)
0
0
0
0
0
0
FF&E: CFCI | [6 empty] | 0
ADDITIONAL CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
HAZ MATS | HAZARDOUS MATERIALS ABATEMENT |  |  | 0 | SF | 0 | 0
PROJECT TITLE: | X
CONSTRUCTION & REMODELING COST SUBTOTAL (from page 2) | [6 empty] | 0
1. Total Construction Cost | [6 empty] | 0
NEW CONSTRUCTION & REMODELING COST (from Page 1) |  |  |  | 0
DEMOLITION (from Page 2) |  |  |  | 0
ADDITIONAL CONSTRUCTION & REMODELING COST (from Page 2) |  |  |  | 0
FF&E: CFCI (from Page 2) |  |  |  | 0
CONSTRUCTION & REMODELING COST SUBTOTAL (from Page 2) |  |  |  | 0
Design Contingency |  | 0% | 0 | 0
General Conditions |  | 0% | 0 | 0
Overhead & Profit (OH&P) |  | 0% | 0 | 0
HAZARDOUS MATERIALS ABATEMENT (from Page 2) |  |  |  | 0
Unescalated Construction Cost Subtotal |  | Escalation Factor |  | 0 |  | Inflation Option
Escalated Construction Cost Subtotal |  | 1.2832 | 0 | 0 |  | NORMAL
Construction Cost Threshold
Builder's Risk Insurance Policy |  | 1% | 0 | 0 |  | 21250000
2. Architect/Engineer Basic Services | [6 empty] | 0
Primary Scope of Work Designation: |  |  | 0%
Project Complexity Designation:
Basic Services (Calculated % of Construction $) |  | 0% | 0 | 0
Basic Services (Enter Direct $ for Basic A/E Fees) |  |  |  | 0
Reimbursible costs |  | 0% | 0 | 0
3. Additional Design Services | [6 empty] | 0
Pre-design |  | 0% | 0 | 0
Sustainable/Resilient Design |  |  |  | 0
Commissioning (Level 1 or 2) |  | 0% | 0 | 0
EIS/EIA consultant |  |  |  | 0
Construction Testing |  |  |  | 0
Testing & Balancing |  |  |  | 0
Specify Additional Design Service A |  |  |  | 0
Specify Additional Design Service B |  |  |  | 0
Specify Additional Design Service C |  |  |  | 0
Specify Additional Design Service D |  |  |  | 0
Furnishings, Fixtures, & Equipment (FF&E) Design Fee |  | 0% | 0 | 0
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Contractor Installed (OFCI) |  |  |  |  | FF&E: OFCI | 0
Audio-Visual and Computer Equipment |  |  |  | 0
Systems Furniture |  |  |  | 0
Specify FF&E (OFCI) Title(s), Type(s), and Budget Estimate Lump Sum A |  |  |  | 0
Specify FF&E (OFCI) Title(s), Type(s), and Budget Estimate Lump Sum B |  |  |  | 0
Specify FF&E (OFCI) Title(s), Type(s), and Budget Estimate Lump Sum C |  |  |  | 0
Specify FF&E (OFCI) Title(s), Type(s), and Budget Estimate Lump Sum D |  |  |  | 0
4. Project Contingency |  | 0% | 0 | 0 |  |  | 0
5. Project Management |  | 0% | 0 | 0 |  |  | 0
6. Furnishings, Fixtures, & Equipment (FF&E) | [6 empty] | 0
FF&E: OFCI (from #3 above) |  |  |  | 0
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Owner Installed (OFOI) |  |  |  |  | FF&E: OFOI | 0
Movable & Special Equipment (% of Construction $) |  | 0% | 0 | 0
Audio-Visual and Computer Equipment |  |  |  | 0
Systems Furniture |  |  |  | 0
Specify FF&E (OFOI) Title(s), Type(s), and Budget Estimate Lump Sum A |  |  |  | 0
Specify FF&E (OFOI) Title(s), Type(s), and Budget Estimate Lump Sum B |  |  |  | 0
Specify FF&E (OFOI) Title(s), Type(s), and Budget Estimate Lump Sum C |  |  |  | 0
TOTAL PROJECT BUDGET ESTIMATE | [6 empty] | 0
|  | 0 | /ASF: Construction Cost (building & site)
|  | 0 | /GSF: Construction Cost (building & site)
|  | 0 | /ASF: Total Project Cost
|  | 0 | /GSF: Total Project Cost
NOTES:
X
X
X
X
X
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The contents in this cell should be hard coded to the date the PBW is finalized. Simply overwrite the formula with the actual date entry (i.e. 04/01/2022).
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Intended to contain the UW Institution Name (i.e. UW-INSTITUTION NAME). This field has a drop down pick list to choose from for standardized institution names.
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AA = All Agency IS = Instructional Space MFR = Minor Facilities Renewal MP = Major Project P&D = Planning & Design SP = Small Project X = Unspecified
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Intended to contain the Project Name, Project No., Alternate or Option No., and date reference of publication.
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Base Date should be on or prior to revision date of Project Budget Worksheet template to maximize the actual inflation included in the budget estimate vs. estimated inflation. Cell has conditional formatting to highlight RED if Base Date > PBW Revision Date or if Base Date is more than 4 years old, highlight YELLOW if the Base Date is between 2-4 years old.
Note on F10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Traditionally prescribed as the Bid Date…but can be defined as the Start of Construction, Mid-Point of Construction, etc. for certain applications if required.
Note on G12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will default to the Escalation (Calculated) value above based on the Base Date and Bid Date values embedded in the ENR Index worksheet included in this workbook template. This value can be manually overwritten using the ENR Index values from a future Project Budget Worksheet edition to correct inflation value calculations and estimates after the initial Project Budget Worksheet creation and submittal.
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Occupancy Date will autocalculate based on project size and DFD guidance on project duration based on project size.
Note on F39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DFD Standard Trade Unit Costs: Automatically updated based on July 2011 ENR Value and the PBW Base Index Value defined above.
Note on G67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DFD Standard Demolition Cost: Automatically updated based on July 2018 ENR Value and the PBW Base Index Value defined above.
Note on B130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Default to 10%, but may range above or below that value dependent on size, complexity, and development status of project. Use Designer's value from feasibility study when possible. Value should be 0% if Design Report is complete.
Note on B131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indirect project costs, project specific costs that do not result in an asset. Use Desiger's value from Pre-Design Report when necessary (i.e. when pre-design values that are used in PBW do not already include General conditions factors).
Note on B132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indirect non-project costs. Typically ranges from 5% to 15%. Use Desiger's value from Pre-Design Report when necessary (i.e. when pre-design values that are used in PBW do not already include OH&P factors).
Note on B140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Must be paired with the “Project Complexity Designation” to auto populate the Basic Services percentage based on the “Unescalated Construction Cost Subtotal” value.
Note on B141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Must be paired with the “Primary Scope of Work Designation” to auto populate the Basic Services percentage based on the “Unescalated Construction Cost Subtotal” value.
Note on B142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on three factors and values: “Primary Scope of Work Designation”, “Project Complexity Designation”, and “Unescalated Construction Cost Subtotal”…all of which are located on this page.
Note on D143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data Entry in this cell will override the calculated Fee in the Row above based on the % of Construction Cost. This cell can be used for Fees only type projects (i.e. Feasibility Studies, Master Plans, etc.) or when the user needs to match a specific $ amount that is easier to enter than to calculate.
Note on B144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Normally 4% of A/E fee for Major Projects. Includes survey, geotechnical, and plan review.
Note on B147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ranges from 1/2% to 1-1/4% for Major Projects.
Note on B149: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Level 1 = 0.00% - 0.25% Level 2 = 0.15% - 1.00%
Note on D150: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Type I: $50,000 - $100,000 Type II: $30,000 - $50,000
Note on B157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This Design Fee is a percent of the OFCI Furnishings, Fixtures, & Equipment Cost Estimate. Percentages will vary based on complexity of project, FF&E items, and services desired. ≤4% of FF&E Budget: Selection and specification only. ≤10% of FF&E Budget: Selection, specification, layout/design, and procurement assistance. REQUIRES DATA ENTRY IN ONE OR MORE OF THE FIVE ROWS IMMEDIATELY BELOW THIS ROW.
Note on B166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Percent of Total Construction Cost. 15% default for all projects.
Note on D168: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4% of (Total Construction Cost + Project Contingency).
Note on B173: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lump sum percentage of construction value + the itemized costs in the five rows below this row. Percentages will vary based on project type, how much existing FF&E will be salvaged, etc. - Typical project 5-10% - Laboratory buildings 10-15%

## PBW_ALTERNATE_SUMMARY
UNIVERSITIES of WISCONSIN | [6 empty] | PROJECT BUDGET WORKSHEET SUMMARY (NO INFLATION) Rev. 2025-05BR
PROJECT TITLE: | X |  |  |  | Date Prepared: |  | 2025-04-30
LOCATION: | X |  |  |  | Prepared By: |  | XXX
PROJECT TYPE ID: | X |  |  |  | Revised By: |  | XXX
OPTION TITLE: | X |  |  |  | TOTAL PROJECT ESTIMATE: |  | 0
NEW BUILDING AREA
ASF New Const | 0 |  |  |  | Base Date: |  | 2025-05-01
GSF New Const | 0 | 0% | Efficiency |  | Base Date Index: |  | 8520.44
[5 empty] | Inflation Date: |  | 2029-07-01
[5 empty] | Inflation Date Index: |  | 10933.6486
REMODELING AREA |  |  |  | NO INFLATION | Inflation Factor: |  | 1
GSF Remodeling | 0
GSF Total Bldg | 0 | 0% | Remodeling |  | Occupancy Date:
|  | 0 | /ASF: Construction Cost (building & site)
|  | 0 | /GSF: Construction Cost (building & site)
|  | 0 | /ASF: Total Project Cost
|  | 0 | /GSF: Total Project Cost
TOTAL CONSTRUCTION | [6 empty] | 0
CONSTRUCTION | [6 empty] | 0
HAZARDOUS MATERIALS ABATEMENT | [6 empty] | 0
TOTAL DESIGN FEES | [6 empty] | 0
DESIGN FEES (BASIC) | [6 empty] | 0
DESIGN FEES (OTHER) | [6 empty] | 0
CONTINGENCY | [6 empty] | 0
MANAGEMENT FEES | [6 empty] | 0
FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E) | [6 empty] | 0
OWNER FURNISHED, CONTRACTOR INSTALLED (OFCI) | [6 empty] | 0
OWNER FURNISHED, OWNER INSTALLED (OFOI) | [6 empty] | 0
TOTAL BUDGET ESTIMATE | [6 empty] | 0
CAPITAL PROJECT REQUEST "Project Budget" Table (NO INFLATION) |  |  |  |  | SBC "CAPITAL BUDGET REQUEST" Table
NO INFLATION
Construction: |  | $ | 0 | LINE 3A | Construction: | $ | 0
Hazardous Materials: |  | $ | 0 | LINE 1 | Design: | $ | 0
Total Construction: |  | $ | 0 | LINE 0 | DFD Fee: | $ | 0
Design Fees (Basic): |  | $ | 0 | LINE 3B | Contingency: | $ | 0
Design Fees (Other): |  | $ | 0 | LINE 4 | Equipment: | $ | 0
Total Design Fees: |  | $ | 0 |  | Inflation | $ | 0
Contingency: |  | $ | 0 |  | TOTAL: | $ | 0
Management Fees: |  | $ | 0
Furnishings/Fixtures/Eqpt: |  | $ | 0
Total Budget Estimate: |  | $ | 0
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This worksheet will auto-complete based on Project Budget Worksheet (PBW).

## PBW_ALTERNATE
UNIVERSITIES of WISCONSIN | [6 empty] | PROJECT BUDGET WORKSHEET (NO INFLATION) Rev. 2025-05BR
PROJECT TITLE: | X |  |  |  | Date Prepared: |  | 2025-04-30
LOCATION: | X |  |  |  | Prepared By: |  | XXX
PROJECT TYPE ID: | X |  |  |  | Revised By: |  | XXX
OPTION TITLE: | X |  |  |  | TOTAL PROJECT ESTIMATE: |  | 0
NEW BUILDING AREA | [5 empty] | ENR Index | Month/Year
ASF New Const | 0 |  |  |  | Base Date: | 8520.44 | 2025-05-01
GSF New Const | 0 | 0% | Efficiency |  | Inflation Date: | 10933.6486 | 2029-07-01
|  |  |  | NO INFLATION | Inflation Factor C (Calculated): |  | 1
REMODELING AREA |  |  |  |  | Inflation Factor O (Override): |  | 1
GSF Remodeling | 0 |  |  |  | Inflation Delta (O-C): |  | 0
GSF Total Bldg | 0 | 0% | Remodeling |  | Occupancy:
NEW CONSTRUCTION BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
Function A | 0 | 0 | 0 | 0 |  | 0
Function B | 0 | 0 | 0 | 0 |  | 0
Function C | 0 | 0 | 0 | 0 |  | 0
Function D | 0 | 0 | 0 | 0 |  | 0
Function E | 0 | 0 | 0 | 0 |  | 0
Function F | 0 | 0 | 0 | 0 |  | 0
Function G | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 |  | Subtotal: $ | 0
NEW CONSTRUCTION COST SUBTOTAL | [6 empty] | 0
REMODELING BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
Function H | 0 | 0 | 0 | 0 |  | 0
Function I | 0 | 0 | 0 | 0 |  | 0
Function J | 0 | 0 | 0 | 0 |  | 0
Function K | 0 | 0 | 0 | 0 |  | 0
Function L | 0 | 0 | 0 | 0 |  | 0
Function M | 0 | 0 | 0 | 0 |  | 0
Function N | 0 | 0 | 0 | 0 |  | 0
| 0 |  | 0 |  | Subtotal: $ | 0 | 0
REMODELING BY TRADE
Trade Category |  |  | GSF | $/GSF | DFD $/GSF | Trade Cost
General | Notes
Surface Treatment | X | 0 | 0 | 17 | 17 | 0
Minor | X | 0 | 0 | 59 | 59 | 0
Partial | X | 0 | 0 | 99 | 99 | 0
Complete | X | 0 | 0 | 118 | 118 | 0
Plumbing
Minor | X | 0 | 0 | 19 | 19 | 0
Partial | X | 0 | 0 | 33 | 33 | 0
Complete | X | 0 | 0 | 37 | 37 | 0
Special Laboratory Needs | X | 0 | 0 | 70 | 70 | 0
Heating, Ventilating, & Air Conditioning
Minor | X | 0 | 0 | 26 | 26 | 0
Partial | X | 0 | 0 | 54 | 54 | 0
Complete | X | 0 | 0 | 81 | 81 | 0
Electrical
Minor | X | 0 | 0 | 21 | 21 | 0
Partial | X | 0 | 0 | 36 | 36 | 0
Complete | X | 0 | 0 | 46 | 46 | 0
[5 empty] | Subtotal: $ | 0
REMODELING COST SUBTOTAL (cell H63 will highlight red if Remodeling by Space Type and Remodeling by Trade sections are both used) | [6 empty] | 0
NEW CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
PROJECT TITLE: | X
NEW CONSTRUCTION & REMODELING COST SUBTOTAL (from page 1) | [6 empty] | 0
ADDITIONAL CONSTRUCTION & REMODELING COSTS:
HEADING NAME OR ITEM CODE | ITEM DESCRIPTION |  |  | QUANTITY | UNIT | UNIT COST | SUBTOTAL
DEMO | DEMOLITION (RAZING GROSS SQUARE FOOTAGE) |  |  | 0 | GSF | 21.1498 | 0
ADDITIONAL CONSTRUCTION & REMODELING COSTS
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
ADDITIONAL CONSTRUCTION & REMODELING COSTS: | [6 empty] | 0
FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E): CONTRACTOR FURNISHED, CONTRACTOR INSTALLED (CFCI)
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
|  |  |  | 0 |  | 0 | 0
FF&E: CFCI | [6 empty] | 0
ADDITIONAL CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 0
HAZ MATS | HAZARDOUS MATERIALS ABATEMENT |  |  | 0 | SF | 0 | 0
PROJECT TITLE: | X
CONSTRUCTION & REMODELING COST SUBTOTAL (from page 2) | [6 empty] | 0
1. Total Construction Cost | [6 empty] | 0
NEW CONSTRUCTION & REMODELING COST (from Page 1) |  |  |  | 0
DEMOLITION (from Page 2) |  |  |  | 0
ADDITIONAL CONSTRUCTION & REMODELING COST (from Page 2) |  |  |  | 0
FF&E: CFCI (from Page 2) |  |  |  | 0
CONSTRUCTION & REMODELING COST SUBTOTAL (from Page 2) |  |  |  | 0
Design Contingency |  | 0% | 0 | 0
General Conditions |  | 0% | 0 | 0
Overhead & Profit (OH&P) |  | 0% | 0 | 0
HAZARDOUS MATERIALS ABATEMENT (from Page 2) |  |  |  | 0
Unescalated Construction Cost Subtotal |  |  |  | 0 |  | Inflation Option
Escalation Factor (NO INFLATION OPTION) |  | 1 | 0 | 0 |  | NO INFLATION
|  | Escalation Factor |  |  |  | Construction Cost Threshold
Builder's Risk Insurance Policy |  | 1% | 0 | 0 |  | 21250000
2. Architect/Engineer Basic Services | [6 empty] | 0
Primary Scope of Work Designation: |  | 0
Project Complexity Designation: |  | 0
Basic Services (Calculated % of Construction $) |  | 0% | 0 | 0
Basic Services (Enter Direct $ for Basic A/E Fees) |  |  |  | 0
Reimbursible costs |  | 0% | 0 | 0
3. Additional Design Services | [6 empty] | 0
Pre-design |  | 0% | 0 | 0
Sustainable/Resilient Design |  |  |  | 0
Commissioning (Level 1 or 2) |  | 0% | 0 | 0
EIS/EIA consultant |  |  |  | 0
Construction Testing |  |  |  | 0
Testing & Balancing |  |  |  | 0
Specify Additional Design Service A | 0 | 0 |  | 0
Specify Additional Design Service B | 0 | 0 |  | 0
Specify Additional Design Service C | 0 | 0 |  | 0
Specify Additional Design Service D | 0 | 0 |  | 0
Furnishings, Fixtures, & Equipment (FF&E) Design Fee |  | 0% | 0 | 0
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Contractor Installed (OFCI) |  |  |  |  | FF&E: OFCI | 0
Audio-Visual and Computer Equipment |  |  |  | 0
Systems Furniture |  |  |  | 0
Specify FF&E (OFCI) Title(s), Type(s), and Budget Estimate Lump Sum A | 0 | 0 |  | 0
Specify FF&E (OFCI) Title(s), Type(s), and Budget Estimate Lump Sum B | 0 | 0 |  | 0
Specify FF&E (OFCI) Title(s), Type(s), and Budget Estimate Lump Sum C | 0 | 0 |  | 0
Specify FF&E (OFCI) Title(s), Type(s), and Budget Estimate Lump Sum D | 0 | 0 |  | 0
4. Project Contingency |  | 0% | 0 | 0 |  |  | 0
5. Project Management |  | 0% | 0 | 0 |  |  | 0
6. Furnishings, Fixtures, & Equipment (FF&E) | [6 empty] | 0
FF&E: OFCI (from #3 above) |  |  |  | 0
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Owner Installed (OFOI) |  |  |  |  | FF&E: OFOI | 0
Movable/Special Equipment (% of Construction $) |  | 0% | 0 | 0
Audio-Visual and Computer Equipment |  |  |  | 0
Systems Furniture |  |  |  | 0
Specify FF&E (OFOI) Title(s), Type(s), and Budget Estimate Lump Sum A | 0 | 0 |  | 0
Specify FF&E (OFOI) Title(s), Type(s), and Budget Estimate Lump Sum B | 0 | 0 |  | 0
Specify FF&E (OFOI) Title(s), Type(s), and Budget Estimate Lump Sum C | 0 | 0 |  | 0
TOTAL PROJECT BUDGET ESTIMATE | [6 empty] | 0
|  | 0 | /ASF: Construction Cost (building & site)
|  | 0 | /GSF: Construction Cost (building & site)
|  | 0 | /ASF: Total Project Cost
|  | 0 | /GSF: Total Project Cost
NOTES:
X
X
X
X
X
Note on H1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This worksheet will auto-complete based on Project Budget Worksheet (PBW).

## ENR
| START A | END A |  | START B | END B |  | DOA CAPITAL BUDGET REQUEST APPLICATION INFLATION (2025-27)
YEAR | 2022 | 2023 |  | 2024 | 2070 |  |  | BASE | BID | INFLATION | FACTOR
MONTH | 7 | 12 |  | 1 | 12 |  | YEAR | 2025 | 2024
COMBO | 202207 | 202312 |  | 202401 | 207012 |  | MONTH | 5 | 10
DATE | 2022-07-01 | 2023-12-01 |  | 2024-01-01 | 2070-12-01 |  | COMBO | 202505 | 202410
| ANNUAL A | MONTHLY A |  | ANNUAL B | MONTHLY B |  | DATE | 2025-05-01 | 2024-10-01
RATE | 16% | 1.333% |  | 6% | 0.5% |  | INDEX | 8520.44 | 8404.93 | -1.356% | 0.98644
| PROJECT REQUEST INFORMATION [PBW WORKSHEET] | [5 empty] | INDEPENDENT INFLATION FACTOR SCENARIO BUILDER INFORMATION | [5 empty] | REMODELING BY TRADE INFORMATION [PBW WORKSHEET] | [5 empty] | DEMOLITION (RAZING GROSS SQUARE FOOTAGE) INFORMATION [PBW WORKSHEET] | [5 empty] | UNIT COST ESTIMATE INFORMATION [COST GUIDELINES WORKSHEET]
|  | PBW BASE | PBW BID | INFLATION | FACTOR |  |  | BASE | BID | INFLATION | FACTOR |  |  | TRADE BASE | NEW BASE | INFLATION | FACTOR |  |  | DEMO BASE | NEW BASE | INFLATION | FACTOR |  |  | COST BASE | NEW BASE | INFLATION | FACTOR
| YEAR | 2025 | 2029 |  |  |  | YEAR | 2025 | 2029 |  |  |  | YEAR | 2011 | 2025 |  |  |  | YEAR | 2018 | 2025 |  |  |  | YEAR | 2022 | 2025
| MONTH | 5 | 7 |  |  |  | MONTH | 3 | 7 |  |  |  | MONTH | 7 | 5 |  |  |  | MONTH | 7 | 5 |  |  |  | MONTH | 12 | 5
| COMBO | 202505 | 202907 |  |  |  | COMBO | 202503 | 202907 |  |  |  | COMBO | 201107 | 202505 |  |  |  | COMBO | 201807 | 202505 |  |  |  | COMBO | 202212 | 202505
| DATE | 2025-05-01 | 2029-07-01 |  |  |  | DATE | 2025-03-01 | 2029-07-01 |  | 1.2959 |  | DATE | 2011-07-01 | 2025-05-01 |  |  |  | DATE | 2018-07-01 | 2025-05-01 |  |  |  | DATE | 2022-12-01 | 2025-05-01
| INDEX | 8520.44 | 10933.6486 | 28.32% | 1.2832 |  | INDEX | 8437.01 | 10933.6486 | 29.59% | 1.2959 |  | INDEX | 5074 | 8520.44 | 67.92% | 1.6792 |  | INDEX | 6042.91 | 8520.44 | 41% | 1.41 |  | INDEX | 7971.96 | 8520.44 | 6.88% | 1.0688
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1990 | 2664 | 2668 | 2673 | 2676 | 2691 | 2715 | 2716 | 2716 | 2730 | 2728 | 2730 | 2720 | 199001 | 199002 | 199003 | 199004 | 199005 | 199006 | 199007 | 199008 | 199009 | 199010 | 199011 | 199012
1991 | 2720 | 2716 | 2715 | 2709 | 2723 | 2733 | 2757 | 2792 | 2785 | 2786 | 2791 | 2784 | 199101 | 199102 | 199103 | 199104 | 199105 | 199106 | 199107 | 199108 | 199109 | 199110 | 199111 | 199112
1992 | 2784 | 2775 | 2799 | 2809 | 2828 | 2838 | 2845 | 2854 | 2857 | 2867 | 2873 | 2875 | 199201 | 199202 | 199203 | 199204 | 199205 | 199206 | 199207 | 199208 | 199209 | 199210 | 199211 | 199212
1993 | 2886 | 2886 | 2915 | 2976 | 3071 | 3066 | 3038 | 3014 | 3009 | 3016 | 3029 | 3046 | 199301 | 199302 | 199303 | 199304 | 199305 | 199306 | 199307 | 199308 | 199309 | 199310 | 199311 | 199312
1994 | 3071 | 3106 | 3116 | 3127 | 3125 | 3115 | 3107 | 3109 | 3116 | 3116 | 3109 | 3110 | 199401 | 199402 | 199403 | 199404 | 199405 | 199406 | 199407 | 199408 | 199409 | 199410 | 199411 | 199412
1995 | 3112 | 3111 | 3103 | 3100 | 3096 | 3095 | 3114 | 3121 | 3109 | 3117 | 3131 | 3128 | 199501 | 199502 | 199503 | 199504 | 199505 | 199506 | 199507 | 199508 | 199509 | 199510 | 199511 | 199512
1996 | 3127 | 3131 | 3135 | 3148 | 3161 | 3178 | 3190 | 3223 | 3246 | 3284 | 3304 | 3311 | 199601 | 199602 | 199603 | 199604 | 199605 | 199606 | 199607 | 199608 | 199609 | 199610 | 199611 | 199612
1997 | 3332 | 3333 | 3323 | 3364 | 3377 | 3396 | 3392 | 3385 | 3378 | 3372 | 3350 | 3370 | 199701 | 199702 | 199703 | 199704 | 199705 | 199706 | 199707 | 199708 | 199709 | 199710 | 199711 | 199712
1998 | 3363 | 3372 | 3368 | 3375 | 3374 | 3379 | 3382 | 3391 | 3414 | 3423 | 3424 | 3419 | 199801 | 199802 | 199803 | 199804 | 199805 | 199806 | 199807 | 199808 | 199809 | 199810 | 199811 | 199812
1999 | 3425 | 3417 | 3411 | 3421 | 3422 | 3433 | 3460 | 3474 | 3504 | 3505 | 3498 | 3497 | 199901 | 199902 | 199903 | 199904 | 199905 | 199906 | 199907 | 199908 | 199909 | 199910 | 199911 | 199912
2000 | 3503 | 3523 | 3536 | 3534 | 3558 | 3553 | 3545 | 3546 | 3539 | 3547 | 3541 | 3548 | 200001 | 200002 | 200003 | 200004 | 200005 | 200006 | 200007 | 200008 | 200009 | 200010 | 200011 | 200012
2001 | 3545 | 3536 | 3541 | 3541 | 3547 | 3572 | 3625 | 3605 | 3597 | 3602 | 3596 | 3577 | 200101 | 200102 | 200103 | 200104 | 200105 | 200106 | 200107 | 200108 | 200109 | 200110 | 200111 | 200112
2002 | 3581 | 3581 | 3597 | 3583 | 3612 | 3624 | 3652 | 3648 | 3655 | 3651 | 3654 | 3640 | 200201 | 200202 | 200203 | 200204 | 200205 | 200206 | 200207 | 200208 | 200209 | 200210 | 200211 | 200212
2003 | 3648 | 3655 | 3649 | 3652 | 3660 | 3677 | 3683 | 3712 | 3717 | 3745 | 3765 | 3757 | 200301 | 200302 | 200303 | 200304 | 200305 | 200306 | 200307 | 200308 | 200309 | 200310 | 200311 | 200312
2004 | 3767 | 3802 | 3859 | 3908 | 3956 | 3996 | 4013 | 4027 | 4102 | 4129 | 4128 | 4123 | 200401 | 200402 | 200403 | 200404 | 200405 | 200406 | 200407 | 200408 | 200409 | 200410 | 200411 | 200412
2005 | 4112 | 4116 | 4127 | 4168 | 4189 | 4195 | 4197 | 4210 | 4242 | 4265 | 4312 | 4329 | 200501 | 200502 | 200503 | 200504 | 200505 | 200506 | 200507 | 200508 | 200509 | 200510 | 200511 | 200512
2006 | 4335 | 4337 | 4330 | 4335 | 4331 | 4340 | 4356 | 4359 | 4375 | 4431 | 4462 | 4441 | 200601 | 200602 | 200603 | 200604 | 200605 | 200606 | 200607 | 200608 | 200609 | 200610 | 200611 | 200612
2007 | 4432 | 4432 | 4411 | 4416 | 4475 | 4471 | 4493 | 4512 | 4533 | 4535 | 4558 | 4556 | 200701 | 200702 | 200703 | 200704 | 200705 | 200706 | 200707 | 200708 | 200709 | 200710 | 200711 | 200712
2008 | 4557 | 4556 | 4571 | 4574 | 4599 | 4640 | 4723 | 4733 | 4827 | 4867 | 4847 | 4797 | 200801 | 200802 | 200803 | 200804 | 200805 | 200806 | 200807 | 200808 | 200809 | 200810 | 200811 | 200812
2009 | 4782 | 4765 | 4767 | 4761 | 4773 | 4771 | 4762 | 4768 | 4764 | 4762 | 4757 | 4795 | 200901 | 200902 | 200903 | 200904 | 200905 | 200906 | 200907 | 200908 | 200909 | 200910 | 200911 | 200912
2010 | 4800 | 4812 | 4811 | 4817 | 4858 | 4888 | 4910 | 4905 | 4910 | 4947 | 4968 | 4970 | 201001 | 201002 | 201003 | 201004 | 201005 | 201006 | 201007 | 201008 | 201009 | 201010 | 201011 | 201012
2011 | 4969 | 5007 | 5010 | 5028 | 5035 | 5059 | 5074 | 5091 | 5098 | 5104 | 5113 | 5115 | 201101 | 201102 | 201103 | 201104 | 201105 | 201106 | 201107 | 201108 | 201109 | 201110 | 201111 | 201112
2012 | 5120 | 5122 | 5144 | 5150 | 5167 | 5170 | 5184 | 5204 | 5195 | 5204 | 5213 | 5210 | 201201 | 201202 | 201203 | 201204 | 201205 | 201206 | 201207 | 201208 | 201209 | 201210 | 201211 | 201212
2013 | 5226 | 5246 | 5249 | 5257 | 5272 | 5286 | 5281 | 5277 | 5285 | 5308 | 5317 | 5326 | 201301 | 201302 | 201303 | 201304 | 201305 | 201306 | 201307 | 201308 | 201309 | 201310 | 201311 | 201312
2014 | 5324 | 5321 | 5336 | 5357 | 5370 | 5375 | 5383 | 5390 | 5409 | 5442 | 5468 | 5480 | 201401 | 201402 | 201403 | 201404 | 201405 | 201406 | 201407 | 201408 | 201409 | 201410 | 201411 | 201412
2015 | 5497 | 5488.1 | 5487.34 | 5500.82 | 5490.44 | 5507.38 | 5510.47 | 5514.7 | 5541.1 | 5543.93 | 5563.51 | 5560.64 | 201501 | 201502 | 201503 | 201504 | 201505 | 201506 | 201507 | 201508 | 201509 | 201510 | 201511 | 201512
2016 | 5561.76 | 5588.02 | 5605.55 | 5632.95 | 5637.09 | 5636.49 | 5659.51 | 5669.5 | 5657.28 | 5681.63 | 5690.35 | 5722.81 | 201601 | 201602 | 201603 | 201604 | 201605 | 201606 | 201607 | 201608 | 201609 | 201610 | 201611 | 201612
2017 | 5733.88 | 5742.06 | 5789.41 | 5801.76 | 5815.76 | 5826.4 | 5844.3 | 5862.24 | 5872.8 | 5866.92 | 5901.86 | 5913.81 | 201701 | 201702 | 201703 | 201704 | 201705 | 201706 | 201707 | 201708 | 201709 | 201710 | 201711 | 201712
2018 | 5921.32 | 5932.09 | 5942.13 | 5954.16 | 5995.06 | 6004.8 | 6042.91 | 6060.07 | 6081.34 | 6092.62 | 6093.13 | 6105.29 | 201801 | 201802 | 201803 | 201804 | 201805 | 201806 | 201807 | 201808 | 201809 | 201810 | 201811 | 201812
2019 | 6107.7 | 6108.09 | 6109.67 | 6109.83 | 6111.77 | 6118.34 | 6131.42 | 6146.81 | 6146.98 | 6168.75 | 6179.22 | 6199.11 | 201901 | 201902 | 201903 | 201904 | 201905 | 201906 | 201907 | 201908 | 201909 | 201910 | 201911 | 201912
2020 | 6213.68 | 6217.29 | 6218.26 | 6233.93 | 6239.42 | 6246.69 | 6258.19 | 6267.65 | 6300.3 | 6343.55 | 6391.74 | 6445.14 | 202001 | 202002 | 202003 | 202004 | 202005 | 202006 | 202007 | 202008 | 202009 | 202010 | 202011 | 202012
2021 | 6459.83 | 6493.19 | 6545.22 | 6612.5 | 6754.51 | 6876.96 | 7006.95 | 7201.88 | 7214.29 | 7244.9 | 7255.67 | 7289.5 | 202101 | 202102 | 202103 | 202104 | 202105 | 202106 | 202107 | 202108 | 202109 | 202110 | 202111 | 202112
2022 | 7359.09 | 7457.68 | 7565.14 | 7677.45 | 7785.64 | 7889.98 | 7950.39 | 7952.5 | 7958.27 | 7965.04 | 7966.9 | 7971.96 | 202201 | 202202 | 202203 | 202204 | 202205 | 202206 | 202207 | 202208 | 202209 | 202210 | 202211 | 202212
2023 | 7976.68 | 7989.84 | 8000.61 | 8000.86 | 8054.43 | 8095.33 | 8179.87 | 8227.44 | 8240.55 | 8255.58 | 8268.19 | 8272.36 | 202301 | 202302 | 202303 | 202304 | 202305 | 202306 | 202307 | 202308 | 202309 | 202310 | 202311 | 202312
2024 | 8277.69 | 8288.93 | 8302.79 | 8305.54 | 8307.78 | 8322.09 | 8331.36 | 8378.62 | 8404.89 | 8404.93 | 8405.03 | 8407.35 | 202401 | 202402 | 202403 | 202404 | 202405 | 202406 | 202407 | 202408 | 202409 | 202410 | 202411 | 202412
2025 | 8407.47 | 8436.93 | 8437.01 | 8463.02 | 8520.44 | 8563.0422 | 8605.8574 | 8648.8867 | 8692.1311 | 8735.5918 | 8779.2697 | 8823.1661 | 202501 | 202502 | 202503 | 202504 | 202505 | 202506 | 202507 | 202508 | 202509 | 202510 | 202511 | 202512
2026 | 8867.2819 | 8911.6183 | 8956.1764 | 9000.9573 | 9045.9621 | 9091.1919 | 9136.6479 | 9182.3311 | 9228.2428 | 9274.384 | 9320.7559 | 9367.3597 | 202601 | 202602 | 202603 | 202604 | 202605 | 202606 | 202607 | 202608 | 202609 | 202610 | 202611 | 202612
2027 | 9414.1965 | 9461.2675 | 9508.5738 | 9556.1167 | 9603.8972 | 9651.9167 | 9700.1763 | 9748.6772 | 9797.4206 | 9846.4077 | 9895.6397 | 9945.1179 | 202701 | 202702 | 202703 | 202704 | 202705 | 202706 | 202707 | 202708 | 202709 | 202710 | 202711 | 202712
2028 | 9994.8435 | 10044.8177 | 10095.0418 | 10145.517 | 10196.2446 | 10247.2258 | 10298.462 | 10349.9543 | 10401.704 | 10453.7126 | 10505.9811 | 10558.511 | 202801 | 202802 | 202803 | 202804 | 202805 | 202806 | 202807 | 202808 | 202809 | 202810 | 202811 | 202812
2029 | 10611.3036 | 10664.3601 | 10717.6819 | 10771.2703 | 10825.1267 | 10879.2523 | 10933.6486 | 10988.3168 | 11043.2584 | 11098.4747 | 11153.9671 | 11209.7369 | 202901 | 202902 | 202903 | 202904 | 202905 | 202906 | 202907 | 202908 | 202909 | 202910 | 202911 | 202912
2030 | 11265.7856 | 11322.1145 | 11378.7251 | 11435.6187 | 11492.7968 | 11550.2608 | 11608.0121 | 11666.0521 | 11724.3824 | 11783.0043 | 11841.9193 | 11901.1289 | 203001 | 203002 | 203003 | 203004 | 203005 | 203006 | 203007 | 203008 | 203009 | 203010 | 203011 | 203012
2031 | 11960.6346 | 12020.4378 | 12080.5399 | 12140.9426 | 12201.6474 | 12262.6556 | 12323.9689 | 12385.5887 | 12447.5167 | 12509.7542 | 12572.303 | 12635.1645 | 203101 | 203102 | 203103 | 203104 | 203105 | 203106 | 203107 | 203108 | 203109 | 203110 | 203111 | 203112
2032 | 12698.3403 | 12761.832 | 12825.6412 | 12889.7694 | 12954.2183 | 13018.9894 | 13084.0843 | 13149.5047 | 13215.2522 | 13281.3285 | 13347.7351 | 13414.4738 | 203201 | 203202 | 203203 | 203204 | 203205 | 203206 | 203207 | 203208 | 203209 | 203210 | 203211 | 203212
2033 | 13481.5462 | 13548.9539 | 13616.6987 | 13684.7822 | 13753.2061 | 13821.9721 | 13891.082 | 13960.5374 | 14030.3401 | 14100.4918 | 14170.9942 | 14241.8492 | 203301 | 203302 | 203303 | 203304 | 203305 | 203306 | 203307 | 203308 | 203309 | 203310 | 203311 | 203312
2034 | 14313.0585 | 14384.6238 | 14456.5469 | 14528.8296 | 14601.4738 | 14674.4811 | 14747.8535 | 14821.5928 | 14895.7008 | 14970.1793 | 15045.0302 | 15120.2553 | 203401 | 203402 | 203403 | 203404 | 203405 | 203406 | 203407 | 203408 | 203409 | 203410 | 203411 | 203412
2035 | 15195.8566 | 15271.8359 | 15348.1951 | 15424.936 | 15502.0607 | 15579.571 | 15657.4689 | 15735.7562 | 15814.435 | 15893.5072 | 15972.9747 | 16052.8396 | 203501 | 203502 | 203503 | 203504 | 203505 | 203506 | 203507 | 203508 | 203509 | 203510 | 203511 | 203512
2036 | 16133.1038 | 16213.7693 | 16294.8381 | 16376.3123 | 16458.1939 | 16540.4849 | 16623.1873 | 16706.3032 | 16789.8347 | 16873.7839 | 16958.1528 | 17042.9436 | 203601 | 203602 | 203603 | 203604 | 203605 | 203606 | 203607 | 203608 | 203609 | 203610 | 203611 | 203612
2037 | 17128.1583 | 17213.7991 | 17299.8681 | 17386.3674 | 17473.2993 | 17560.6658 | 17648.4691 | 17736.7114 | 17825.395 | 17914.522 | 18004.0946 | 18094.1151 | 203701 | 203702 | 203703 | 203704 | 203705 | 203706 | 203707 | 203708 | 203709 | 203710 | 203711 | 203712
2038 | 18184.5856 | 18275.5086 | 18366.8861 | 18458.7205 | 18551.0141 | 18643.7692 | 18736.9881 | 18830.673 | 18924.8264 | 19019.4505 | 19114.5478 | 19210.1205 | 203801 | 203802 | 203803 | 203804 | 203805 | 203806 | 203807 | 203808 | 203809 | 203810 | 203811 | 203812
2039 | 19306.1711 | 19402.7019 | 19499.7155 | 19597.214 | 19695.2001 | 19793.6761 | 19892.6445 | 19992.1077 | 20092.0682 | 20192.5286 | 20293.4912 | 20394.9587 | 203901 | 203902 | 203903 | 203904 | 203905 | 203906 | 203907 | 203908 | 203909 | 203910 | 203911 | 203912
2040 | 20496.9335 | 20599.4181 | 20702.4152 | 20805.9273 | 20909.957 | 21014.5067 | 21119.5793 | 21225.1772 | 21331.3031 | 21437.9596 | 21545.1494 | 21652.8751 | 204001 | 204002 | 204003 | 204004 | 204005 | 204006 | 204007 | 204008 | 204009 | 204010 | 204011 | 204012
2041 | 21761.1395 | 21869.9452 | 21979.2949 | 22089.1914 | 22199.6373 | 22310.6355 | 22422.1887 | 22534.2997 | 22646.9711 | 22760.206 | 22874.007 | 22988.3771 | 204101 | 204102 | 204103 | 204104 | 204105 | 204106 | 204107 | 204108 | 204109 | 204110 | 204111 | 204112
2042 | 23103.319 | 23218.8355 | 23334.9297 | 23451.6044 | 23568.8624 | 23686.7067 | 23805.1402 | 23924.1659 | 24043.7868 | 24164.0057 | 24284.8257 | 24406.2499 | 204201 | 204202 | 204203 | 204204 | 204205 | 204206 | 204207 | 204208 | 204209 | 204210 | 204211 | 204212
2043 | 24528.2811 | 24650.9225 | 24774.1771 | 24898.048 | 25022.5383 | 25147.651 | 25273.3892 | 25399.7562 | 25526.7549 | 25654.3887 | 25782.6606 | 25911.574 | 204301 | 204302 | 204303 | 204304 | 204305 | 204306 | 204307 | 204308 | 204309 | 204310 | 204311 | 204312
2044 | 26041.1318 | 26171.3375 | 26302.1942 | 26433.7051 | 26565.8737 | 26698.703 | 26832.1965 | 26966.3575 | 27101.1893 | 27236.6953 | 27372.8787 | 27509.7431 | 204401 | 204402 | 204403 | 204404 | 204405 | 204406 | 204407 | 204408 | 204409 | 204410 | 204411 | 204412
2045 | 27647.2919 | 27785.5283 | 27924.456 | 28064.0782 | 28204.3986 | 28345.4206 | 28487.1477 | 28629.5835 | 28772.7314 | 28916.595 | 29061.178 | 29206.4839 | 204501 | 204502 | 204503 | 204504 | 204505 | 204506 | 204507 | 204508 | 204509 | 204510 | 204511 | 204512
2046 | 29352.5163 | 29499.2789 | 29646.7753 | 29795.0092 | 29943.9842 | 30093.7041 | 30244.1727 | 30395.3935 | 30547.3705 | 30700.1073 | 30853.6079 | 31007.8759 | 204601 | 204602 | 204603 | 204604 | 204605 | 204606 | 204607 | 204608 | 204609 | 204610 | 204611 | 204612
2047 | 31162.9153 | 31318.7299 | 31475.3235 | 31632.7001 | 31790.8636 | 31949.818 | 32109.567 | 32270.1149 | 32431.4655 | 32593.6228 | 32756.5909 | 32920.3739 | 204701 | 204702 | 204703 | 204704 | 204705 | 204706 | 204707 | 204708 | 204709 | 204710 | 204711 | 204712
2040 | 33084.9757 | 33250.4006 | 33416.6526 | 33583.7359 | 33751.6545 | 33920.4128 | 34090.0149 | 34260.465 | 34431.7673 | 34603.9261 | 34776.9458 | 34950.8305 | 204001 | 204002 | 204003 | 204004 | 204005 | 204006 | 204007 | 204008 | 204009 | 204010 | 204011 | 204012
2049 | 35125.5846 | 35301.2126 | 35477.7186 | 35655.1072 | 35833.3827 | 36012.5497 | 36192.6124 | 36373.5755 | 36555.4433 | 36738.2206 | 36921.9117 | 37106.5212 | 204901 | 204902 | 204903 | 204904 | 204905 | 204906 | 204907 | 204908 | 204909 | 204910 | 204911 | 204912
2050 | 37292.0538 | 37478.5141 | 37665.9067 | 37854.2362 | 38043.5074 | 38233.7249 | 38424.8935 | 38617.018 | 38810.1031 | 39004.1536 | 39199.1744 | 39395.1703 | 205001 | 205002 | 205003 | 205004 | 205005 | 205006 | 205007 | 205008 | 205009 | 205010 | 205011 | 205012
2051 | 39592.1461 | 39790.1068 | 39989.0574 | 40189.0027 | 40389.9477 | 40591.8974 | 40794.8569 | 40998.8312 | 41203.8253 | 41409.8445 | 41616.8937 | 41824.9782 | 205101 | 205102 | 205103 | 205104 | 205105 | 205106 | 205107 | 205108 | 205109 | 205110 | 205111 | 205112
2052 | 42034.1031 | 42244.2736 | 42455.4949 | 42667.7724 | 42881.1113 | 43095.5168 | 43310.9944 | 43527.5494 | 43745.1871 | 43963.9131 | 44183.7326 | 44404.6513 | 205201 | 205202 | 205203 | 205204 | 205205 | 205206 | 205207 | 205208 | 205209 | 205210 | 205211 | 205212
2053 | 44626.6746 | 44849.8079 | 45074.057 | 45299.4272 | 45525.9244 | 45753.554 | 45982.3218 | 46212.2334 | 46443.2946 | 46675.511 | 46908.8886 | 47143.433 | 205301 | 205302 | 205303 | 205304 | 205305 | 205306 | 205307 | 205308 | 205309 | 205310 | 205311 | 205312
2054 | 47379.1502 | 47616.0459 | 47854.1262 | 48093.3968 | 48333.8638 | 48575.5331 | 48818.4108 | 49062.5028 | 49307.8153 | 49554.3544 | 49802.1262 | 50051.1368 | 205401 | 205402 | 205403 | 205404 | 205405 | 205406 | 205407 | 205408 | 205409 | 205410 | 205411 | 205412
2055 | 50301.3925 | 50552.8995 | 50805.664 | 51059.6923 | 51314.9907 | 51571.5657 | 51829.4235 | 52088.5706 | 52349.0135 | 52610.7586 | 52873.8124 | 53138.1814 | 205501 | 205502 | 205503 | 205504 | 205505 | 205506 | 205507 | 205508 | 205509 | 205510 | 205511 | 205512
2056 | 53403.8723 | 53670.8917 | 53939.2461 | 54208.9424 | 54479.9871 | 54752.387 | 55026.149 | 55301.2797 | 55577.7861 | 55855.675 | 56134.9534 | 56415.6282 | 205601 | 205602 | 205603 | 205604 | 205605 | 205606 | 205607 | 205608 | 205609 | 205610 | 205611 | 205612
2057 | 56697.7063 | 56981.1948 | 57266.1008 | 57552.4313 | 57840.1935 | 58129.3944 | 58420.0414 | 58712.1416 | 59005.7023 | 59300.7308 | 59597.2345 | 59895.2207 | 205701 | 205702 | 205703 | 205704 | 205705 | 205706 | 205707 | 205708 | 205709 | 205710 | 205711 | 205712
2058 | 60194.6968 | 60495.6703 | 60798.1486 | 61102.1394 | 61407.6501 | 61714.6883 | 62023.2617 | 62333.3781 | 62645.0449 | 62958.2702 | 63273.0615 | 63589.4268 | 205801 | 205802 | 205803 | 205804 | 205805 | 205806 | 205807 | 205808 | 205809 | 205810 | 205811 | 205812
2059 | 63907.374 | 64226.9108 | 64548.0454 | 64870.7856 | 65195.1395 | 65521.1152 | 65848.7208 | 66177.9644 | 66508.8542 | 66841.3985 | 67175.6055 | 67511.4835 | 205901 | 205902 | 205903 | 205904 | 205905 | 205906 | 205907 | 205908 | 205909 | 205910 | 205911 | 205912
2060 | 67849.0409 | 68188.2862 | 68529.2276 | 68871.8737 | 69216.2331 | 69562.3143 | 69910.1258 | 70259.6765 | 70610.9748 | 70964.0297 | 71318.8499 | 71675.4441 | 206001 | 206002 | 206003 | 206004 | 206005 | 206006 | 206007 | 206008 | 206009 | 206010 | 206011 | 206012
2061 | 72033.8213 | 72393.9904 | 72755.9604 | 73119.7402 | 73485.3389 | 73852.7656 | 74222.0294 | 74593.1396 | 74966.1053 | 75340.9358 | 75717.6405 | 76096.2287 | 206101 | 206102 | 206103 | 206104 | 206105 | 206106 | 206107 | 206108 | 206109 | 206110 | 206111 | 206112
2062 | 76476.7098 | 76859.0934 | 77243.3888 | 77629.6058 | 78017.7538 | 78407.8426 | 78799.8818 | 79193.8812 | 79589.8506 | 79987.7998 | 80387.7388 | 80789.6775 | 206201 | 206202 | 206203 | 206204 | 206205 | 206206 | 206207 | 206208 | 206209 | 206210 | 206211 | 206212
2063 | 81193.6259 | 81599.5941 | 82007.592 | 82417.63 | 82829.7181 | 83243.8667 | 83660.0861 | 84078.3865 | 84498.7784 | 84921.2723 | 85345.8787 | 85772.6081 | 206301 | 206302 | 206303 | 206304 | 206305 | 206306 | 206307 | 206308 | 206309 | 206310 | 206311 | 206312
2064 | 86201.4711 | 86632.4785 | 87065.6409 | 87500.9691 | 87938.4739 | 88378.1663 | 88820.0571 | 89264.1574 | 89710.4782 | 90159.0306 | 90609.8257 | 91062.8749 | 206401 | 206402 | 206403 | 206404 | 206405 | 206406 | 206407 | 206408 | 206409 | 206410 | 206411 | 206412
2065 | 91518.1892 | 91975.7802 | 92435.6591 | 92897.8374 | 93362.3266 | 93829.1382 | 94298.2839 | 94769.7753 | 95243.6242 | 95719.8423 | 96198.4415 | 96679.4337 | 206501 | 206502 | 206503 | 206504 | 206505 | 206506 | 206507 | 206508 | 206509 | 206510 | 206511 | 206512
2066 | 97162.8309 | 97648.645 | 98136.8883 | 98627.5727 | 99120.7106 | 99616.3141 | 100114.3957 | 100614.9677 | 101118.0425 | 101623.6327 | 102131.7509 | 102642.4096 | 206601 | 206602 | 206603 | 206604 | 206605 | 206606 | 206607 | 206608 | 206609 | 206610 | 206611 | 206612
2067 | 103155.6217 | 103671.3998 | 104189.7568 | 104710.7056 | 105234.2591 | 105760.4304 | 106289.2326 | 106820.6787 | 107354.7821 | 107891.556 | 108431.0138 | 108973.1689 | 206701 | 206702 | 206703 | 206704 | 206705 | 206706 | 206707 | 206708 | 206709 | 206710 | 206711 | 206712
2068 | 109518.0347 | 110065.6249 | 110615.953 | 111169.0328 | 111724.8779 | 112283.5023 | 112844.9199 | 113409.1444 | 113976.1902 | 114546.0711 | 115118.8015 | 115694.3955 | 206801 | 206802 | 206803 | 206804 | 206805 | 206806 | 206807 | 206808 | 206809 | 206810 | 206811 | 206812
2069 | 116272.8675 | 116854.2318 | 117438.503 | 118025.6955 | 118615.824 | 119208.9031 | 119804.9476 | 120403.9723 | 121005.9922 | 121611.0221 | 122219.0773 | 122830.1726 | 206901 | 206902 | 206903 | 206904 | 206905 | 206906 | 206907 | 206908 | 206909 | 206910 | 206911 | 206912
2070 | 123444.3235 | 124061.5451 | 124681.8529 | 125305.2621 | 125931.7884 | 126561.4474 | 127194.2546 | 127830.2259 | 128469.377 | 129111.7239 | 129757.2825 | 130406.0689 | 207001 | 207002 | 207003 | 207004 | 207005 | 207006 | 207007 | 207008 | 207009 | 207010 | 207011 | 207012
KEY
| TEXT | ACTUAL ENR INDEX VALUE (DATA ENTRY)
| TEXT | ESTIMATED ENR INDEX VALUE (FORMULA)

## READ ME
CAPITAL PROJECT BUDGET WORKSHEETS Rev. 2025-05BR
Tab | WORKSHEET INDEX (left to right worksheets organized top to bottom below)
1 | [PBW_SUMMARY]: Summarizes and maps content from [PBW] worksheet. Provides budget table for copy/paste into CPR.
2 | [PBW]: Project Budget Worksheet template and primary worksheet intended for user entry/modification.
3 | [PBW_ALTERNATE_SUMMARY]: Summarizes and maps content from [PBW_ALTERNATE] worksheet.
4 | [PBW_ALTERNATE]: Maps content from [PBW] worksheet, provides alternate Inflation Factor(s) to modify budget estimate.
5 | [ENR]: Engineering New Record's Building Cost Index History and Forecast based on prescribed inflation rates.
6 | [READ ME]: Provides Worksheet Index and some narrative directions and references to template contents and intents.
7 | [COST GUIDELINES]: Unit construction cost ranges and reference for various building space types. Auto-inflates costs based on ENR.
8 | [SAMPLE]: Guide & Sample of the PBW Worksheet, intended to show completed template and formatting/nomenclature standards.
9 | [LOOKUPS]: Various lookup tables (i.e. version ID, universities list, project types, etc.) for use in PBW workbook template.
1 | This budget worksheet should be flexible enough for all capital project request types: Small Projects, All Agency Projects, Instructional Space Projects, Minor Facilities Renewal Projects, enumerated Major Projects, and UW Managed projects. All dark teal text fields are unlocked and intended for user entry and definition. All other fields are locked and protected from user entry or modification.
2 | The [PBW] worksheet allows renovation costs estimates to be conducted using a "Remodeling by Space Type" and/or "Remodeling by Trade" methodologies. Using both methodologies in a single budget estimate would be unusual and could lead to duplicative cost estimates. Use with caution. The "Remodeling by Trade" line items now include a Notes field for user text entry to clarify, further define, and/or re-define the standard category terms. The Notes field should be used when the standard unit costs are overwritten by the user. Cell H63 will automatically highlight in red if both "Remodeling by Space Type" and "Remodeling by Trade" section are used.
3 | Since capital projects seeking Board of Regents (BOR) and/or State Building Commission (SBC) authority to constuct require feasibility and/or pre-design estimates, the budget worksheet has been designed to offer maximum flexibility in the arrangement and organization of the line items. Page 2 is esentially a blank sheet with a few structured sections to organize specific types of cost estimate items. Smart code identifiers (i.e. MasterFormat or UniFormat) can be entered; quantity/unit of measure/unit costs must be entered to calculate the line item cost; and the user determines the organization headings and can arrange the information to their specification.
NOTE: If a 3rd party detailed budget estimate already exists in some other format, it is recommended those construction costs be entered as a lump sum item and the detailed budget estimate be referenced in the line item description vs. recreating the detail in this budget worksheet. If a 3rd party detailed budget estimate is not taken in whole as the basis for this budget estimate, the pertinent detail should be recreated here and be easily referenced and discoverable in the 3rd party estimate in terms of line item organization and terminology.
4 | The "Base Date" and "Inflation Date" cells allow use of any combination of month and year from January 2011 - December 2050. Consequently, the [ENR] worksheet lookup table has also been expanded to allow lookup of inflation values for any combination of Base Date and Inflation Date. There are three fields for ENR Inflation factors on Page 1. "Inflation Factor C (Calculated)" is a lookup of the inflation factor based on the Base Date and Escalation Date data entry values in this worksheet and the projections contained in the embedded ENR Index worksheet. "Inflation Factor O (Override)" defaults to the "Inflation Factor C (Calculated)" value, but can be manually overwrtten by the user using a future PBW template with updated and corrected [ENR] worksheet values. Manual overrides below the default will highlight in red, above the default will highlight in yellow, and unchanged will highlight in green. "Inflation Delta (O - C)" calculates the difference between the default value embedded in the [ENR] worksheet and the manual override. [ENR] worksheet values in BLACK TEXT are actual values, BLUE TEXT is projected/estimated based on the Annual Inflation Factor Estimate at the top of the worksheet.
5 | Furnishings, Fixtures, and Equipment (FF&E): There are three distinct sections of the [PBW] worksheet design to handle FF&E cost estimate items. Contractor Furnished, Contractor Installed (CFCI) items should be entered at the bottom of Page 2, and these items are then integrated into the Construction Cost line. Owner Furnished, Contractor Installed (OFCI) items should be entered at the bottom of Section 3 "Additional Design Services" on Page 3 along with the associated FF&E Design Fee. Owner Furnished. The Owner Installed (OFOI) items should be entered in Section 6 on Page 3. These OFOI cost items can include specific line items and/or a percent of Construction Cost calculation.
6 | At the bottom of the [PBW_SUMMARY] worksheet is a table which can be selected, copied, and pasted directly into the Capital Project Request's (CPR) Project Budget section. The table formatting is identical in cell and font size, style, and color.
7 | Architectural/Engineering Basic Design Fees Guidance: Current as per DFD's biennial capital budget instructions (2025-27). Outlined below for ease of reading since new Excel in-cell Comments do not allow formatted text.
New Construction Design Fee Guidance Project Complexity Construction Cost HIGH ¦ AVG ¦ LOW ≦ $100K: (14.2% ¦ 13.6% ¦ 12.8%) $100K - $500K: (14.1% ¦ 13.3% ¦ 12.3%) $500K - $1M: (11.6% ¦ 10.9% ¦ 9.9%) $1M - $2.5M: (10.6% ¦ 9.8% ¦ 8.8%) $2.5M - $5M: ( 9.2% ¦ 8.3% ¦ 7.3%) $5M - $30M: ( 8.3% ¦ 7.4% ¦ 6.3%) $30M - $50M: ( 7.0% ¦ 6.2% ¦ 5.3%) $50M+: ( 6.1% ¦ 5.5% ¦ 4.7%)
Renovation & Remodeling Design Fee Guidance Project Complexity Construction Cost HIGH ¦ AVG ¦ LOW ≦ $100K: (16.0% ¦ 14.0% ¦ 13.0%) $100K - $500K: (14.3% ¦ 13.5% ¦ 12.5%) $500K - $1M: (12.0% ¦ 11.1% ¦ 10.1%) $1M - $2.5M: (10.9% ¦ 9.9% ¦ 8.9%) $2.5M - $5M: ( 9.4% ¦ 8.5% ¦ 7.4%) $5M - $30M: ( 8.4% ¦ 7.5% ¦ 6.4%) $30M - $50M: ( 7.1% ¦ 6.3% ¦ 5.4%) $50M+: ( 6.2% ¦ 5.6% ¦ 4.8%)
If programming is not done by the agency, or if extensive program verification is required, an additional 0.1% to 1.5% should be added to the fee guidance shown above.
High Complexity: Most complex projects both in design and detail include buildings of specialized architectural character, memorial, historic or monumental nature requiring special study or analysis and/or involve complex programs, mechanical systems, code requirements, etc. Project types include auditorium/theaters, communication buildings, extended care facilities, complex engineering projects, laboratories, historical restoration, and museums.
Average Complexity: Project types include readiness centers, building systems, maintenance shops, firing ranges, recreational facilities, teaching laboratories, medical offices & clinics, laundry facilities, office buildings, site utilities, university centers, residence halls, and child day care facilities.
Low Complexity: Projects are simple or repetitive construction without any great degree of special finish or design effort. May include projects where equipment purchase comprises a large portion of the construction budget. Project types include asbestos removal, building envelope repairs, roofing, life safety compliance, demolition, minimum security correctional centers, park shelters, warehouse, radio/television towers, service garage, and site work.
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Although it is possible to make duplicates of the PBW worksheet in the same file to explore alternatives and options, the PBW_Summary worksheet will only map to the original PBW worksheet content.
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data source found at <https://www.enr.com/economics/historical_indices/building_cost_index_history>, but requires user account to access data content.
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: PBW Revision Date and associated fields primarily created and generated to facilitate easy template updates without having to manually edit each worksheet in the template for a revision date.

## COST GUIDELINES
NEW CONSTRUCTION COST GUIDELINES Rev. 2025-05BR
SPACE CATEGORY | GSF | EFFICIENCY | $/GSF RANGE |  | COMMENTS and NOTES
|  |  | LOW END | HIGH END
Classrooms | 140000 | 65 | 268 | 353
Academic – Multi Use | 140000 | 65 | 268 | 294
Fine Arts Auditorium | 10000 | 65 | 530 | 823
Food Service | 30000 | 65 | 310 | 417 | Movable furnishings, kitchen appliances and fixtures, and specialty items (i.e. coolers or freezers sized for more than day use, blast freezers, large exhaust ventilation hoods) are not included in these $/GSF figures.
Laboratory Space
● Fine Arts Instructional Laboratory | 100000 | 62 | 353 | 412
● Instructional Dry Laboratory | 25000 | 60 | 385 | 417
● Instructional Wet Laboratory | 25000 | 58 | 524 | 759
● Research Laboratory | 100000 | 55 | 508 | 759
● Animal Space | 15000 | 55 | 674 | 738
● Computer Laboratory | 25000 | 65 | 316 | 417
● Instructional Greenhouse | 10000 | 80 | 316 | 353
● Research Greenhouse | 25000 | 80 | 353 | 407
Library | 80000 | 65 | 236 | 337
Offices
● 1 story | 10000 | 65 | 225 | 284 | For offices as part of other buildings with higher costs/ GSF use average of office cost and the other space type cost
● 2-4 stories | 40000 | 65 | 214 | 284
Physical Education | 120000 | 70 | 246 | 284
● Arena | 80000 | 78 | 246 | 294
● Field House | 45000 | 75 | 236 | 268
● Gymnasium/Track | 115000 | 74 | 177 | 209
● Pool | 10000 | 78 | 353 | 412
Residence Hall
● Semi-Suite Doubles (Type 2) | 160000 | 80 | 278 | 375
● Suite Style (Type 3) | 110000 | 80 | 278 | 375 | $63,000 - $75,000/ bed
Student Union | 100000 |  | 353 | 396
Agricultural
● Animal Housing | 35000 | 85 | 150 | 177 | Pole Barn, includes fixed equipment
● Hay Storage | 15000 | 90 | 118 | 150 | Pole Barn, unheated
Service and Maintenance | 25000 | 85 | 177 | 209
Storage (Prefabricated Metal)
● Unheated | 4000 | 95 | 91 | 123
● Heated | 4000 | 95 | 118 | 161
Parking | CAPACITY |  | $/STALL RANGE
● Freestanding ramp | 500 stalls | 55 | 18800 | 24200
● Ramp beneath building | 100 stalls | 52 | 34300 | 53000
● Surface Lot | 200 stalls |  | 4600 | 7400

## SAMPLE
UNIVERSITIES of WISCONSIN | [6 empty] | PROJECT BUDGET WORKSHEET GUIDE & SAMPLE Rev. 2025-05BR
PROJECT TITLE: | OLD MAIN MEMORIAL HALL ADDITION & RENOVATION - PHASE VIII + ALTERNATE X |  |  |  | Date Prepared: |  | 2024-06-06
LOCATION: | UW SYSTEM |  |  |  | Prepared By: |  | UWSA
PROJECT TYPE ID: | X |  |  |  | Revised By: |  | XXX
OPTION TITLE: | PRE-DESIGN (APRIL 2024) |  |  |  | TOTAL PROJECT ESTIMATE: |  | 193518000
NEW BUILDING AREA | [5 empty] | ENR Index | Month/Year
ASF New Const | 16665 |  |  |  | Base Date: | 8305.54 | 2024-04-01
GSF New Const | 25100 | 66.39% | Efficiency |  | Inflation Date: | 10558.511 | 2028-12-01
|  |  |  | NORMAL | Inflation Factor C (Calculated): |  | 1.2713
REMODELING AREA |  |  |  |  | Inflation Factor O (Override): |  | 1.2713
GSF Remodeling | 50800 |  |  |  | Inflation Delta (O-C): |  | 0
GSF Total Bldg | 222222 | 22.86% | Remodeling |  | Occupancy: | 42 months | 2032-05-31 12:00
NEW CONSTRUCTION BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
ENTRANCE/LOBBY | 1111 | 0.75 | 1500 | 111.11 |  | 166700
CLASSROOMS | 2222 | 0.6 | 3700 | 222.22 |  | 822200
LABORATORIES | 3333 | 0.52 | 6400 | 333.33 |  | 2133300
OFFICES | 4444 | 0.67 | 6600 | 444.44 |  | 2933300
STORAGE | 5555 | 0.8 | 6900 | 555.55 |  | 3833300
Function F | 0 | 0 | 0 | 0 |  | 0
Function G | 0 | 0 | 0 | 0 |  | 0
| 16665 |  | 25100 |  | Subtotal: $ | 9889000
NEW CONSTRUCTION COST SUBTOTAL | [6 empty] | 9889000
REMODELING BY SPACE TYPE
Space Category | ASF | Eff | GSF | $/GSF |  | Category Cost
CLASSROOMS | 6666 | 0.6 | 11100 | 666.66 |  | 7399900
LABORATORIES | 7777 | 0.52 | 15000 | 777.77 |  | 11666600
OFFICES | 8888 | 0.67 | 13300 | 888.88 |  | 11822100
MULTI-PURPOSE | 9999 | 0.88 | 11400 | 999.99 |  | 11399900
Function L | 0 | 0 | 0 | 0 |  | 0
Function M | 0 | 0 | 0 | 0 |  | 0
Function N | 0 | 0 | 0 | 0 |  | 0
| 33330 |  | 50800 |  | Subtotal: $ | 42289000 | 42289000
REMODELING BY TRADE
Trade Category |  |  | GSF | $/GSF | DFD $/GSF | Trade Cost
General | Notes
Surface Treatment | SUSPENDED ACOUSTICAL CEILING PANELS |  | 8888 | 8.18 | 17 | 72700
Minor | X |  | 0 | 59 | 59 | 0
Partial | X |  | 8888 | 99 | 99 | 879900
Complete | X |  | 0 | 118 | 118 | 0
Plumbing
Minor | X |  | 0 | 19 | 19 | 0
Partial | UPDATED UNIT COST FROM CONTRACTOR |  | 8888 | 33.33 | 33 | 296200
Complete | X |  | 0 | 37 | 37 | 0
Special Laboratory Needs | X |  | 0 | 70 | 70 | 0
Heating, Ventilating, & Air Conditioning
Minor | X |  | 0 | 26 | 26 | 0
Partial | X |  | 0 | 54 | 54 | 0
Complete | BASED ON PROJECT NO. 88X8X |  | 88888 | 81 | 81 | 7199900
Electrical
Minor | X |  | 0 | 21 | 21 | 0
Partial | X |  | 0 | 36 | 36 | 0
Complete | X |  | 88888 | 46 | 46 | 4088800
[5 empty] | Subtotal: $ | 12538000
REMODELING COST SUBTOTAL (cell will highlight red if Remodeling by Space Type and Remodeling by Trade sections are both used) | [5 empty] | ERROR? | 12538000
NEW CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 64716000
PROJECT TITLE: | OLD MAIN MEMORIAL HALL ADDITION & RENOVATION - PHASE VIII + ALTERNATE X
NEW CONSTRUCTION & REMODELING COST SUBTOTAL (from page 1) | [6 empty] | 64716000
ADDITIONAL CONSTRUCTION & REMODELING COSTS:
HEADING NAME OR ITEM CODE | ITEM DESCRIPTION |  |  | QUANTITY | UNIT | UNIT COST | SUBTOTAL
DEMO | DEMOLITION (RAZING GROSS SQUARE FOOTAGE) |  |  | 88888 | GSF | 21.1498 | 1880000
ADDITIONAL CONSTRUCTION & REMODELING COSTS
1. HEADING #1 | [6 empty] | 0
| HEADING #1, COST ITEM A |  |  | 1.11 | ACRES | 111.11 | 100
| HEADING #1, COST ITEM B |  |  | 22.22 | SF | 222.22 | 4900
| HEADING #1, COST ITEM C |  |  | 33.33 | GSF | 33.33 | 1100
2. HEADING #2 | [6 empty] | 0
| HEADING #2, COST ITEM D |  |  | 4444.44 | EACH | 444.44 | 1975300
| HEADING #2, COST ITEM E |  |  | 55555.55 | LUMP SUM | 55.55 | 3086100
| HEADING #2, COST ITEM F |  |  | 666666.66 | ALLOWANCE | 6.66 | 4440000
| HEADING #2, COST ITEM G |  |  | 7777777.77 | LEGOS | 0.07 | 544400
3. HEADING #3 | [6 empty] | 0
| HEADING #3, COST ITEM H |  |  | 8.88 | EACH | 8888.88 | 78900
| HEADING #3, COST ITEM I |  |  | 999.99 | ASF | 333.33 | 333300
| HEADING #3, COST ITEM J |  |  | 1111.11 | VF | 111.11 | 123500
| HEADING #3, COST ITEM K |  |  | 22222.22 | LF | 22.22 | 493800
0
0
|  | … OR … |  |  |  |  | 0
0
0
PROJECT NO. 88X8X | PRE-DESIGN BUDGET ESTIMATE (APRIL 1, 2024 pp. 88 - 99) |  |  | 1 | LUMP SUM | 8888888.88 | 8888900
0
0
0
0
0
0
0
0
0
0
0
0
0
0
ADDITIONAL CONSTRUCTION & REMODELING COSTS: | [6 empty] | 19970000
FURNISHINGS, FIXTURES, & EQUIPMENT (FF&E): CONTRACTOR FURNISHED, CONTRACTOR INSTALLED (CFCI)
FURNSHINGS | TELESCOPING BLEACHERS, CONTROLS, & COVERS |  |  | 1 | EACH | 77777.77 | 77800
EQUIPMENT | AUTOCLAVE |  |  | 1 | EACH | 66666.66 | 66700
ATHLETICS/RECREATION | CLIMBING WALL & ROPES COURSE |  |  | 1 | ALLOWANCE | 55555.55 | 55600
0
0
0
FF&E: CFCI | [6 empty] | 200000
ADDITIONAL CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 22050000
CONSTRUCTION & REMODELING COST SUBTOTAL | [6 empty] | 86766000
HAZ MATS | HAZARDOUS MATERIALS ABATEMENT |  |  | 44444 | SF | 4.44 | 197000
PROJECT TITLE: | OLD MAIN MEMORIAL HALL ADDITION & RENOVATION - PHASE VIII + ALTERNATE X
CONSTRUCTION & REMODELING COST SUBTOTAL (from page 2) | [6 empty] | 86766000
1. Total Construction Cost | [6 empty] | 141366000
NEW CONSTRUCTION & REMODELING COST (from Page 1) |  |  |  | 64716000
DEMOLITION (from Page 2) |  |  |  | 1880000
ADDITIONAL CONSTRUCTION & REMODELING COST (from Page 2) |  |  |  | 19970000
FF&E: CFCI (from Page 2) |  |  |  | 200000
CONSTRUCTION & REMODELING COST SUBTOTAL (from Page 2) |  |  |  | 86766000
Design Contingency |  | 8.889% | 86766000 | 7712500
General Conditions |  | 8.889% | 86766000 | 7712500
Overhead & Profit (OH&P) |  | 8.889% | 86766000 | 7712500
HAZARDOUS MATERIALS ABATEMENT (from Page 2) |  |  |  | 197000
Unescalated Construction Cost Subtotal |  | Escalation Factor |  | 110100500 |  | Inflation Option
Escalated Construction Cost Subtotal |  | 1.2713 | 110100500 | 139966500 |  | NORMAL
Construction Cost Threshold
Builder's Risk Insurance Policy |  | 1% | 139966500 | 1399700 |  | 21250000
2. Architect/Engineer Basic Services | [5 empty] | 5.722% | 8089000
Primary Scope of Work Designation: |  | CONSTRUCTION | 5.5%
Project Complexity Designation: |  | AVERAGE
Basic Services (Calculated % of Construction $) |  | 5.5% | 141366000 | 7775100
Basic Services (Enter Direct $ for Basic A/E Fees) |  |  |  | 0
Reimbursible costs |  | 4.04% | 7775100 | 314100
3. Additional Design Services | [5 empty] | 2.013% | 2845000
Pre-design |  | 1.25% | 141366000 | 1767100
Sustainable/Resilient Design |  |  |  | 0
Commissioning (Level 1 or 2) |  | 0.75% | 141366000 | 1060200
EIS/EIA consultant |  |  |  | 0
Construction Testing |  |  |  | 0
Testing & Balancing |  |  |  | 0
HAZARDOUS MATERIALS DESIGN |  |  |  | 8888
GEOTCHNICAL SURVEY |  |  |  | 8888
Specify Additional Design Service C |  |  |  | 0
Specify Additional Design Service D |  |  |  | 0
Furnishings, Fixtures, & Equipment (FF&E) Design Fee |  | 0% | 944400 | 0
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Contractor Installed (OFCI) |  |  |  |  | FF&E: OFCI | 944400
Audio-Visual and Computer Equipment |  |  |  | 777777
Systems Furniture |  |  |  | 66666
LABORATORY CASEWORK, MOBILE WORKSTATIONS |  |  |  | 55555
MOBILE INFORMATION & LIBRARY KIOSKS |  |  |  | 44444
Specify FF&E (OFCI) Title(s), Type(s), and Budget Estimate Lump Sum C |  |  |  | 0
Specify FF&E (OFCI) Title(s), Type(s), and Budget Estimate Lump Sum D |  |  |  | 0
4. Project Contingency |  | 15% | 141366000 | 21204900 |  | 15% | 21205000
5. Project Management |  | 4% | 162571000 | 6502800 |  | 4.6% | 6503000
6. Furnishings, Fixtures, & Equipment (FF&E) | [5 empty] | 9.557% | 13510000
FF&E: OFCI (from #3 above) |  |  |  | 944400
Furnishings, Fixtures, & Equipment (FF&E): Owner Furnished, Owner Installed (OFOI) |  |  |  |  | FF&E: OFOI | 12565700
Movable & Special Equipment (% of Construction $) |  | 8.889% | 141366000 | 12565700
Audio-Visual and Computer Equipment |  |  |  | 0
Systems Furniture |  |  |  | 0
Specify FF&E (OFOI) Title(s), Type(s), and Budget Estimate Lump Sum A |  |  |  | 0
Specify FF&E (OFOI) Title(s), Type(s), and Budget Estimate Lump Sum B |  |  |  | 0
Specify FF&E (OFOI) Title(s), Type(s), and Budget Estimate Lump Sum C |  |  |  | 0
TOTAL PROJECT BUDGET ESTIMATE | [6 empty] | 193518000
|  | 1286 | /ASF: Construction Cost (building & site)
|  | 1143 | /GSF: Construction Cost (building & site)
|  | 2868 | /ASF: Total Project Cost
|  | 2550 | /GSF: Total Project Cost
NOTES:
X
X
X
X
X
Note on G3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The contents in this cell should be hard coded to the date the PBW is finalized. Simply overwrite the formula with the actual date entry (i.e. 04/01/2022).
Note on A4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Intended to contain the UW Institution Name (i.e. UW-INSTITUTION NAME). This field has a drop down pick list to choose from for standardized institution names.
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: AA = All Agency IS = Instructional Space MFR = Minor Facilities Renewal MP = Major Project P&D = Planning & Design SP = Small Project X = Unspecified
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Intended to contain the Project Name, Project No., Alternate or Option No., and date reference of publication.
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Base Date should be on or prior to revision date of Project Budget Worksheet template to maximize the actual inflation included in the budget estimate vs. estimated inflation. Cell has conditional formatting to highlight RED if Base Date > PBW Revision Date or if Base Date is more than 4 years old, highlight YELLOW if the Base Date is between 2-4 years old.
Note on F10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Traditionally prescribed as the Bid Date…but can be defined as the Start of Construction, Mid-Point of Construction, etc. for certain applications if required.
Note on G12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This value will default to the Escalation (Calculated) value above based on the Base Date and Bid Date values embedded in the ENR Index worksheet included in this workbook template. This value can be manually overwritten using the ENR Index values from a future Project Budget Worksheet edition to correct inflation value calculations and estimates after the initial Project Budget Worksheet creation and submittal.
Note on G14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Occupancy Date will autocalculate based on project size and DFD guidance on project duration based on project size.
Note on F39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DFD Standard Trade Unit Costs: Automatically updated based on July 2011 ENR Value and the PBW Base Index Value defined above.
Note on G67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: DFD Standard Demolition Cost: Automatically updated based on July 2018 ENR Value and the PBW Base Index Value defined above.
Note on B130: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Default to 10%, but may range above or below that value dependent on size, complexity, and development status of project. Use Designer's value from feasibility study when possible. Value should be 0% if Design Report is complete.
Note on B131: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indirect project costs, project specific costs that do not result in an asset. Use Desiger's value from Pre-Design Report when necessary (i.e. when pre-design values that are used in PBW do not already include General conditions factors).
Note on B132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Indirect non-project costs. Typically ranges from 5% to 15%. Use Desiger's value from Pre-Design Report when necessary (i.e. when pre-design values that are used in PBW do not already include OH&P factors).
Note on B140: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Must be paired with the “Project Complexity Designation” to auto populate the Basic Services percentage based on the “Unescalated Construction Cost Subtotal” value.
Note on B141: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Must be paired with the “Primary Scope of Work Designation” to auto populate the Basic Services percentage based on the “Unescalated Construction Cost Subtotal” value.
Note on B142: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on three factors and values: “Primary Scope of Work Designation”, “Project Complexity Designation”, and “Unescalated Construction Cost Subtotal”…all of which are located on this page.
Note on D143: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data Entry in this cell will override the calculated Fee in the Row above based on the % of Construction Cost. This cell can be used for Fees only type projects (i.e. Feasibility Studies, Master Plans, etc.) or when the user needs to match a specific $ amount that is easier to enter than to calculate.
Note on B144: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Normally 4% of A/E fee for Major Projects. Includes survey, geotechnical, and plan review.
Note on B147: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ranges from 1/2% to 1-1/4% for Major Projects.
Note on B149: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Level 1 = 0.00% - 0.25% Level 2 = 0.15% - 1.00%
Note on D150: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Type I: $50,000 - $100,000 Type II: $30,000 - $50,000
Note on B157: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This Design Fee is a percent of the OFCI Furnishings, Fixtures, & Equipment Cost Estimate. Percentages will vary based on complexity of project, FF&E items, and services desired. ≤4% of FF&E Budget: Selection and specification only. ≤10% of FF&E Budget: Selection, specification, layout/design, and procurement assistance. REQUIRES DATA ENTRY IN ONE OR MORE OF THE FIVE ROWS IMMEDIATELY BELOW THIS ROW.
Note on B166: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Percent of Total Construction Cost. 15% default for all projects.
Note on D168: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 4% of (Total Construction Cost + Project Contingency).
Note on B173: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lump sum percentage of construction value + the itemized costs in the five rows below this row. Percentages will vary based on project type, how much existing FF&E will be salvaged, etc. - Typical project 5-10% - Laboratory buildings 10-15%

## LOOKUPS
Rev. 2025-05BR |  | PROJECT TYPE |  | DURATION |  |  | LOCATION | BUILDER'S INSURANCE POLICY THRESHOLDS |  | INFLATION OPTIONS | DESIGN FEE TYPE | COMPLEXITY FACTOR | DESIGN FEES
2025-05-01 |  | AA | ALL AGENCY | 5000 | 600000 | 182.5 | UW-EAU CLAIRE | PERCENTAGE | 1% | NORMAL | CONSTRUCTION | LOW | BUDGET RANGE |  | CONSTRUCTION COMPLEXITY |  |  | BLANK | RENOVATION COMPLEXITY
2025-04-30 | TODAY | IS | INSTRUCTIONAL SPACE | 600000 | 3000000 | 365 | UW-GREEN BAY | CONSTRUCTION COST | 21250000 | NO INFLATION | RENOVATION | AVERAGE | BUDGET_START | BUDGET_END | LOW_CNST | AVERAGE_CNST | HIGH_CNST | NULL | LOW_RENV | AVERAGE_RENV | HIGH_RENV
2023-05-01 | TODAY-730 | MFR | MINOR FACILITIES RENEWAL | 3000000 | 7400000 | 547.5 | UW-LA CROSSE |  |  | 2025-27 CBR |  | HIGH | 5000 | 100000 | 12.8% | 13.6% | 14.2% | 0% | 13% | 14% | 16%
2021-05-01 | TODAY-1460 | MP | MAJOR PROJECT | 7400000 | 15000000 | 912.5 | UW-MADISON | [5 empty] | 100001 | 500000 | 12.3% | 13.3% | 14.1% | 0% | 12.5% | 13.5% | 14.3%
|  | P&D | PLANNING & DESIGN | 15000000 | 30000000 | 1095 | UW-MILWAUKEE | [5 empty] | 500001 | 1000000 | 9.9% | 10.9% | 11.6% | 0% | 10.1% | 11.1% | 12%
|  | SP | SMALL PROJECT | 30000000 | 1000000000 | 1277.5 | UW-OSHKOSH | [5 empty] | 1000001 | 2500000 | 8.8% | 9.8% | 10.6% | 0% | 8.9% | 9.9% | 10.9%
|  | X | UNSPECIFIED |  |  |  | UW-PARKSIDE | [5 empty] | 2500001 | 5000000 | 7.3% | 8.3% | 9.2% | 0% | 7.4% | 8.5% | 9.4%
[7 empty] | UW-PLATTEVILLE | [5 empty] | 5000001 | 30000000 | 6.3% | 7.4% | 8.3% | 0% | 6.4% | 7.5% | 8.4%
[7 empty] | UW-RIVER FALLS | [5 empty] | 30000001 | 50000000 | 5.3% | 6.2% | 7% | 0% | 5.4% | 6.3% | 7.1%
[7 empty] | UW-STEVENS POINT | [5 empty] | 50000001 | 999999999 | 4.7% | 5.5% | 6.1% | 0% | 4.8% | 5.6% | 6.2%
UW-STOUT
UW-SUPERIOR
UW-WHITEWATER
UW SYSTEM
SYSTEMWIDE
MULTI-INSTITUTION
X