## UAT-ADM CAT Test Scripts
Test Script Type: | UAT-ADM | Tested By:
User Type: | CAT Admin | Tested Date:
Test Script Objective Number | Test Script Objective | Key User | UAT Participants Execute? | Pass/Fail | Notes
1 | Perform Annual Set Up of CAT | Universal User | N
2 | Unlock All CAT Users | Universal User | N
UAT-ADM-03 | Run Initialization Report | Admin | Y
UAT-ADM-04 | IR to IPS Transfer | Admin | Y
UAT-ADM-05 | Institutional Planning Spreadsheet (Add a rate increase, edit a funding split) | Admin/Update | Y
UAT-ADM-06 | IPS - AAP Tab (Add multiple Vacants & Bud Adj.) | Admin/Update | Y
UAT-ADM-07 | IPS Load to CAT | Admin/Update | Y
UAT-ADM-08 | IPS Load to AAP | Admin/Update | Y
UAT-ADM-09 | CAT Page | Admin/Update/Read | Y
UAT-ADM-10 | Additional Adjustments Page | Admin/Update/Read | Y
UAT-ADM-11 | HRS Compare Report | Admin/Update/Read | Y
UAT-ADM-12 | Missing From CAT Report | Admin/Update/Read | Y
UAT-ADM-13 | HRS Change Report | Admin/Update/Read | Y
UAT-ADM-14 | Record Errors Report | Admin/Update/Read | Y
UAT-ADM-15 | Position Report | Admin/Update/Read | Y
UAT-ADM-16 | CAT Summary Reporting Page | Admin/Update/Read | Y
UAT-ADM-17 | BSUM | Admin/Update | Y
UAT-ADM-18 | Query a CAT EPM View | Admin/Update/Read | Y
UAT-ADM-19 | IPS Load Edit/Overwrite | Admin | Y
UAT-ADM-20 | Turn off Job Data Feed | Admin | Y
UAT-ADM-21 | Lock out Users in a Unit | Admin | Y

## UAT-ADM-03
Test Script ID: | UAT-ADM-03 |  | Overall Pass/Fail:
Test Script Description: | Run an Initialization Report |  | KB#: | 55327
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External Systems > Compensation Administration Tool > CAT Processes > Initialization Report Process
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Run the Initialization Report | 1 | Navigate to Main Menu > Workforce Administration > UW External Systems > Compensation Administration Tool > CAT Processes > Initialization Report Process.
Run the Initialization Report | 2 | Click the Add a New Value tab.
Run the Initialization Report | 3 | Enter a Run Control ID. | Any unique identifier (ex. your initials and the date) - NOT the example Note: cannot include spaces
Run the Initialization Report | 4 | Click the Add button. |  | Taken to the Initialization Report run control page.
Run the Initialization Report | 5 | Select the desired information for the Fiscal Year field. | 2017
Run the Initialization Report | 6 | Select the desired information for the Effective Date field. | Start of Fiscal Year for University Staff employees (7/01/2016)
Run the Initialization Report | 7 | Select the desired information for the Business Unit field. | Tester's Business Unit
Run the Initialization Report | 8 | Select the desired information for the Division field. | Tester's Division (if desired or applicable)
Run the Initialization Report | 9 | Click the Select Values button |  | Taken to the Employee Class selection page.
Run the Initialization Report | 10 | Click the Clear button.
Run the Initialization Report | 11 | Select the desired information for the Empl Class checkboxes. | University Staff employee values (CJ and CP) and FA/LI/AS employee values (FA, LI, and AS)
Run the Initialization Report | 12 | Click the OK button. |  | Taken to the Initialization Report run control page.
Run the Initialization Report | 13 | Click the Run button. |  | Taken to the Process Scheduler Request page.
Run the Initialization Report | 14 | Click the OK button. |  | Taken to the Initialization Report run control page.
Run the Initialization Report | 15 | Note the process instance number under the Process Monitor link.
Run the Initialization Report | 16 | Click the Process Monitor link. |  | Taken to the Process Monitor page. Note: To view previous files on the Process Monitor page at any time, navigate to Main Menu > People Tools > Process Scheduler > Process Monitor.
Run the Initialization Report | 17 | Click the Refresh button intermittently until the Run Status is Success, and the Distribution Status is Posted.
Run the Initialization Report | 18 | Click the Details link next to the UW_CAT_IR process just run. |  | Taken to the Process Detail page.
Run the Initialization Report | 19 | Click the View Log/Trace. |  | Taken to the View Log/Trace page.
Run the Initialization Report | 20 | Click the file named “init_report_ProcessMonitor#.xls”. The “ProcessMonitor#” will be the seven digit code associated with the Initaitlization Report process just processed.
Run the Initialization Report | 21 | Click Open to open the .xls file. If the file does not automatically open, you may need to bring up Excel and select Yes in the pop-up window. Note: Different browsers may have different opening processes. Ensure po- ups are allowed. |  | This file contains all employees, in the selected business unit and employee classes with less than 5 funding splits.
Run the Initialization Report | 22 | Save the Initialization Report as a (.xls) file.
Run the Initialization Report | 23 | Return to the View Log/Trace page if employees with more than five funding splits exist within the Tester's Business Unit.
Run the Initialization Report | 24 | Click the file named “init_report_addtlsplits_ProcessMonitor#.xls” if it exists and is listed following the previous file. Please note that the file will not exist if employees with more than five funding splits do not exist within the Tester's Business Unit. |  | This will only generate for employees with greater than 5 funding splits.
Run the Initialization Report | 25 | Click Open to open the .xls file. If the file does not automatically open, you may need to bring up Excel and select Yes in the pop-up window. |  | This file contains all employees with greater than 5 funding splits, should employees such as this exist given the run control criteria.
Run the Initialization Report | 26 | Save the Initialization Report.
Run the Initialization Report | 27 | Verify the header information matches what was entered on the run control.
Run the Initialization Report | 28 | Verify compensation information is correct based on HRS Job Data for five employees - including verification that only CJ, CL, CP Employee Classes appear on output. (Main Menu > Workforce Administration > Job Information > Job Data, Compensation Tab) | Record validated Employee IDs here: 1) 2) 3) 4) 5) | Column values should match Job Data: - Column 1 (Business Unit) - Column 2 (Job Data Dept UDDS) - Column 7 (Employee Class) - Column 8 (Position Number) - Column 9 (Job Code) - Column 20 (Annualized Base Salary) *Note: Calculated hourly salary based on 2080 in CAT and 2088 in PeopleSoft.

## UAT-ADM-04
Test Script ID: | UAT-ADM-04 |  | Overall Pass/Fail:
Test Script Description: | IR to IPS Transfer and Institutional Planning Spreadsheet |  | KB#: | XXXXX
Tested By: |  |  | Tested Date:
Environment Link: | N/A
Page Navigation: | N/A
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Transfer Employee Data to IPS (Columns 1-33) | 1 | Open the off-base or cumulative IPS file from the CAT Project website. | https://www.wisconsin.edu/cat-project/user-acceptance-testing/
Transfer Employee Data to IPS (Columns 1-33) | 2 | Click Enable Content when Excel opens.
Transfer Employee Data to IPS (Columns 1-33) | 3 | Open the Initialization Report (IR) excel file saved in UAT-ADM-03.
Transfer Employee Data to IPS (Columns 1-33) | 4 | Select and copy columns 1-33 in the IR, starting with the first employee (cell A13) and dragging down (or pressing Ctrl+Shift+Down Arrow as a shortcut) to the last Note: do not copy column headers - just data
Transfer Employee Data to IPS (Columns 1-33) | 5 | Navigate back to the IPS.
Transfer Employee Data to IPS (Columns 1-33) | 6 | Right click cell C16 in IPS on the Comp Admin Planning Tool Tab. Under 'Paste Options' click paste.
Transfer Funding Data to IPS (Columns 77-116) | 7 | Navigate back to the IR.
Transfer Funding Data to IPS (Columns 77-116) | 8 | Select and copy columns 77-116 in the IR, starting with the first employee (cell AH13) and dragging down (or pressing Ctrl+Shift+Down Arrow as a shortcut) to the last
Transfer Funding Data to IPS (Columns 77-116) | 9 | Navigate back to the IPS.
Transfer Funding Data to IPS (Columns 77-116) | 10 | Right click cell CA16 in the IPS on the Comp Admin Tool Tab. Under 'Paste Options' click paste.
Transfer Funding Data to IPS (Columns 77-116) | 11 | Repeat steps 4-10 for any additional IRs created.
Change Column 20 from text to number to ensure all IPS features function correctly. | 12 | In the IPS: 1. Select Cell V16 (Annualized Base Salary Adjusted for FTE) 2. Highlight every row in that column by dragging down (or pressing Ctrl+Shift+Down Arrow as a shortcut) 3.Scroll back to cell V16 (your selection should still be highlighted) 4. Press the caution box adjacent to cell V16 (exclamation point to upper left of highlighted cells) and chose 'convert to number' 5. Wait for the column to convert (this may take a minute)
Lock cells that should not be edited in the IPS | 13 | In the Review tab press Protect Sheet -Do not require a password to unprotect the sheet. -Check the following boxes under “Allow all users of this worksheet to:” 1. Select locked cells 2. Select unlocked cells 3. Sort 4. Use AutoFilter
Save the IPS File | 14 | Save the IPS file in (.xlsm) format. Note: For Excel 2013 users, this is the Excel Macro-Enabled Workbook type.

## UAT-ADM-05
Test Script ID: | UAT-ADM-05 |  | Overall Pass/Fail:
Test Script Description: | Institutional Planning Spreadsheet (Add a rate increase, edit a funding source) |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | N/A
Page Navigation: | N/A
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Open IPS File | 1 | Open the saved IPS file generated in UAT-ADM-04.
Answer Question 1 column for each employee | 2 | Answer the Question 1 column in the IPS. Should the employee be included in the IPS Upload to CAT? | Value will default Yes, indicating the employee will load to the CAT. Type No to indicate the employee should not load to the CAT. | If employee will not load to CAT during the IPS--> CAT load proccess, the cell will turn blue. Question 2 cell for the employee will turn red (an employee who is not being budgeted for in the next FY cannot be part of the CSB).
Answer Question 2 column for each employee | 3 | Answer the Question 2 column in the IPS. Should the employee be included as part of the Continuing Staff Base (CSB)? | Value will default to Yes, to include the employee in the continuing staff base. Type No for an employee who should not be part of the Continuing Staff Base. | The cell will turn yellow if the employee will not be inlcuded in the CSB summary table at the top of the sheet.
Assign a mass merit increase on the IPS | 4 | Navigate to the 'Merit Increase Amount %' Column 64 for Cumulative, 36 for Off-Base.
Assign a mass merit increase on the IPS | 5 | Assign a 1% increase to the first employee in IPS.
Assign a mass merit increase on the IPS | 6 | Left Double-Click the bottom, right corner of the cell. Note: If applicable, unprotect the sheet to conduct this action. |  | The 1% increase will auto-fill for every employee in the institution.
Assign a non-merit increase to 10 employees | 7 | Navigate to the 'Other Pay Rate Adjustment #1 Action Reason' (Column 34).
Assign a non-merit increase to 10 employees | 8 | Select an Action Reason from the drop-down list for the first employee in IPS.
Assign a non-merit increase to 10 employees | 9 | Copy and paste the selected Action Reason down 10 rows. |  | The action reason will repeat for the ten employees selected.
Assign a non-merit increase to 10 employees | 10 | Assign a 1% increase for the first employee in the 'Other Increase Amount (%)' (Column 36).
Assign a non-merit increase to 10 employees | 11 | Drag the 1% increase down ten rows. |  | The change amount will repeat for the ten employees selected.
Assign a non-merit increase to all hourly employees. | 12 | Filter Pay-Basis (Column 17) to be H to return all hourly employees.
Assign a non-merit increase to all hourly employees. | 13 | Navigate to the 'Other Pay Rate Adjustment #1 Action Reason' - (Column 34 Cumulative, Column 41 Off-Base).
Assign a non-merit increase to all hourly employees. | 14 | Select an Action Reason from the drop-down list for one employee.
Assign a non-merit increase to all hourly employees. | 15 | Copy and paste the selected Action Reason down to the last hourly employee.
Assign a non-merit increase to all hourly employees. | 16 | Assign the first employee an 'Increase Amount ($)' of $1.00
Assign a non-merit increase to all hourly employees. | 17 | Drag the $1.00 increase amount down to the last Hourly employee
Assign a non-merit increase to all hourly employees. | 18 | Remove Pay-Basis filter on Column 17. |  | All Hourly employees will have a comprate increase of $1.00
Add a funding source for an employee | 19 | Navigate to the funding section of the IPS, starting in Column 77.
Add a funding source for an employee | 20 | Select an employee with only one funding source.
Add a funding source for an employee | 21 | Add a second funding source, starting in column 83 by entering in the following information: 1) Business Unit GL (required) 2) Fund Code (required) 3) Department (required) 4) Program (required) 5) Project ID (not required) | 1) Business Unit GL = Tester's BU GL 2) Fund Code 3) Department 4) Program 5) Project ID (if desired)
Add a funding source for an employee | 22 | Enter a value in 'Distribution Percentage from 2' (Column 88) | 100 | Column 118, Total Distribution will read 200% and have a red fill.
Add a funding source for an employee | 23 | Change 'Distribution Percentage from 1' (Column 82) and Distribution Percentage from 2' (Column 88) to add a funding source equal to 100%. | 50 for 'Distribution Percentage from 1' 50 for 'Distribution Percentage from 2' | Column 118, Total Distribution will read 100% and have a green fill.
Remove a funding source for an employee | 24 | Select an employee from Column 83 with two funding sources.
Remove a funding source for an employee | 25 | Remove the second funding source, starting in column 83 by deleting the following information: 1) Business Unit GL 2) Fund Code 3) Department 4) Program 5) Project ID 6) Distribution Percentage from 2 | Blank values for the five columns | Column 118, Total Distribution will equal the value in Distribution Percentage from 1 value
Remove a funding source for an employee | 26 | Change 'Distribution Percentage from 1' (Column 82) to equal to 100%. | 100 | Column 118, Total Distribution will read 100% and have a green fill.
Remove employees from IPS for manual addition | 27 | Delete five employees from the IPS upload by selecting "No" in Column 1. Note: these will be used for manually adding employees to the CAT in Script UAT-ADM-09B. | Record deleted Employee IDs here: 1) 2) 3) 4) 5)
Save the IPS File | 28 | Save the IPS file.

## UAT-ADM-06
Test Script ID: | UAT-ADM-06 |  | Overall Pass/Fail:
Test Script Description: | IPS - AAP Tab (Add multiple Vacants & Bud. Adj.) |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | N/A
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Add Multiple Vacant Positions and Budget Adjusments in AAP | 1 | Click the Additional Adjustments tab in the IPS file updated in UAT-ADM-05.
Add Multiple Vacant Positions and Budget Adjusments in AAP | 2 | Identify an adjustment to include in the IPS Upload to AAP.
Add Multiple Vacant Positions and Budget Adjusments in AAP | 3 | Enter the Business Unit for the identified adjustment as you would like it to appear in the Additional Adjustments Page, including UW. | Tester's Business Unit (Ex. UWEAU, UWOSH, etc.)
Add Multiple Vacant Positions and Budget Adjusments in AAP | 4 | Enter the Funding Department (Deptid) for the identified adjustment corresponding to the Funding Department within the funding string for the adjustment. | (Ex. C021200) Note: The Business Unit and the DeptID fields should be the same as the GL Business Unit and Department fields in the funding string. Note: the first Dept field - Funding Department (DeptID) - should not have the letter included.
Add Multiple Vacant Positions and Budget Adjusments in AAP | 5 | Enter the Fiscal Year in which this Additional Adjustment will take place. | 2017
Add a Vacant Position in AAP | 6 | For all vacancies, enter Position Type: ‘Vacant’. |  | Note: the Jobcode field becomes red as it is required for a Vacant entry. The Pay Basis and Position Number fields are not required.
Add a Vacant Position in AAP | 7 | Enter the Adjustment Type from the drop down list
Add a Vacant Position in AAP | 8 | Enter the Job Code for the vacancy (required).
Add a Vacant Position in AAP | 9 | Enter a Pay Basis from the drop down list (not required).
Add a Vacant Position in AAP | 10 | Enter a HRS Position Number for vacant position types (not required).
Add a Vacant Position in AAP | 11 | Enter FTE as you would like it to appear on the Additional Adjustments Page. FTE should not be entered for adjustment types LTE and Student Help.
Add a Vacant Position in AAP | 12 | Enter the GL Business Unit (Business Unit) from within the funding string of the desired adjustment. Note: This needs to match the Business Unit value in Column 1.
Add a Vacant Position in AAP | 13 | Enter the Fund Code from within the funding string of the desired adjustment.
Add a Vacant Position in AAP | 14 | Enter the Department from within the funding string of the desired adjustment. Note: This needs to match the Department value in Column 2.
Add a Vacant Position in AAP | 15 | Enter the Program from within the funding string of the desired adjustment.
Add a Vacant Position in AAP | 16 | Enter the Project ID from within the funding string of the desired adjustment.
Add a Vacant Position in AAP | 17 | Enter the Description of the desired adjustment.
Add a Vacant Position in AAP | 18 | Enter the Budgeted Amount of the desired adjustment.
Add Other Budget Adjustments in AAP | 19 | For all other budget adjustments (group, lump, and negative), enter Position Type: Bud. Adj. |  | Note: the Jobcode, Pay Basis, and Position Number fields become gray as they are not applicable to a Bud. Adj. entry.
Add Other Budget Adjustments in AAP | 20 | Enter the Adjustment Type from the drop down list |  | Note: the FTE field become gray as it is not applicable to a Bud. Adj. entry.
Add Other Budget Adjustments in AAP | 21 | Leave Job Code blank.
Add Other Budget Adjustments in AAP | 22 | Leave Pay Basis blank.
Add Other Budget Adjustments in AAP | 23 | Leave Position Number blank.
Add Other Budget Adjustments in AAP | 24 | Enter FTE as you would like it to appear on the Additional Adjustments Page. FTE should not be entered for adjustment types LTE and Student Help.
Add Other Budget Adjustments in AAP | 25 | Enter the GL Business Unit (Business Unit) from within the funding string of the desired adjustment. Note: This needs to match the Business Unit value in Column 1.
Add Other Budget Adjustments in AAP | 26 | Enter the Fund Code from within the funding string of the desired adjustment.
Add Other Budget Adjustments in AAP | 27 | Enter the Department from within the funding string of the desired adjustment. Note: This needs to match the Department value in Column 2.
Add Other Budget Adjustments in AAP | 28 | Enter the Program from within the funding string of the desired adjustment.
Add Other Budget Adjustments in AAP | 29 | Enter the Project ID from within the funding string of the desired adjustment.
Add Other Budget Adjustments in AAP | 30 | Enter the Description of the desired adjustment.
Add Other Budget Adjustments in AAP | 31 | Enter the Budgeted Amount of the desired adjustment.
Save the IPS File | 32 | Save the IPS file with the AAP adjustment entries. |  | Completed Vacant and Budget Adjustments for given Funding Department.

## UAT-ADM-07
Test Script ID: | UAT-ADM-07 |  | Overall Pass/Fail:
Test Script Description: | IPS Load to CAT |  | KB#: | 55923
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Processes > IPS Load to CAT/AAP
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Create CSV document to transfer IPS data to CAT | 1 | After making all rate and funding data changes in the IPS, go to the IPS --> CAT tab.
Create CSV document to transfer IPS data to CAT | 2 | Drag the text string formula in column A down until the last corresponding row populated with employees in the Comp Admin Planning Tool tab (e.g. if you have 80 emloyees, you have to copy at least 80 rows). Stop before and make final highlighted row be the row above the first row in this format: IPS;;;;000000;00000000;00;;;;0.000000. Delete all null rows that are in this format.
Create CSV document to transfer IPS data to CAT | 3 | Press the 'Click Here to Export File for CAT Upload' button |  | A 'Save As' box will appear on the screen.
Create CSV document to transfer IPS data to CAT | 4 | Name the document. The default naming format is "IPS-CAT Entry Output FileYYYY-MM-DD.CSV". Save as a .CSV (Comma Separated Value) document. |  | A message box 'Make sure this file looks correct' will appear.
Create CSV document to transfer IPS data to CAT | 5 | Press OK on the window that appears. |  | A Notepad file will appear on the screen. Note that the file name will begin with IPS-CAT.
Create CSV document to transfer IPS data to CAT | 6 | Exit out of the Notepad document that appears on the screen. Do not edit the file.
Navigate to the CAT IPS/AAP Upload Page | 7 | Navigate to the CAT IPS Load to CAT/AAP Page: Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Processes > IPS Load to CAT/AAP
Run the IPS to CAT Load process - Report Only mode. | 8 | Click the Add a New Value tab.
Run the IPS to CAT Load process - Report Only mode. | 9 | Enter a Run Control ID. | Any unique identifier (ex. your initials and the date)
Run the IPS to CAT Load process - Report Only mode. | 10 | Click the Add button. |  | Taken to the IPS Load to CAT/AAP page.
Run the IPS to CAT Load process - Report Only mode. | 11 | Select Report Only mode. (This processes data without committing data to the CAT. It generates an output .xls file that allows the data and any possible errors to be reviewed.) |  | Note: Report only mode will not load values to CAT or AAP.
Run the IPS to CAT Load process - Report Only mode. | 12 | Enter Fiscal Year.
Run the IPS to CAT Load process - Report Only mode. | 13 | Select 'Compensation Adjustment' as the File Type.
Run the IPS to CAT Load process - Report Only mode. | 14 | Enter or click the magnifying glass to select Business Unit.
Run the IPS to CAT Load process - Report Only mode. | 15 | Enter the File Description, which will be used to name the output file after the process runs. | Any identifier for the output report (ex.CAT Upload_YY_MM_DD)
Run the IPS to CAT Load process - Report Only mode. | 16 | Click the 'Upload File' link. |  | The 'File Attachment' Window appears.
Run the IPS to CAT Load process - Report Only mode. | 17 | Click 'Browse' on the 'File Attachment' window. |  | A 'choose file to upload' screen appears.
Run the IPS to CAT Load process - Report Only mode. | 18 | Navigate to the .CSV file created in steps 1-6 on the 'Choose File to Upload' screen. This file will begin with "IPS-CAT".
Run the IPS to CAT Load process - Report Only mode. | 19 | Click Open. |  | Return to the 'File Attachment' window.
Run the IPS to CAT Load process - Report Only mode. | 20 | Click Upload on the File Attachment window.
Run the IPS to CAT Load process - Report Only mode. | 21 | Wait while the file attaches.
Run the IPS to CAT Load process - Report Only mode. | 22 | Click Save.
Run the IPS to CAT Load process - Report Only mode. | 23 | Click Run. |  | Process Scheduler Request screen appears.
Run the IPS to CAT Load process - Report Only mode. | 24 | Click OK on the Process Scheduler Request screen. |  | IPS Load to CAT/AAP screen reappears.
Run the IPS to CAT Load process - Report Only mode. | 25 | Click the Process Monitor link. |  | The Process Monitor screen appears.
Run the IPS to CAT Load process - Report Only mode. | 26 | Click the Refresh button intermittently until the Run Status is Success, and the Distribution Status is Posted.
Run the IPS to CAT Load process - Report Only mode. | 27 | Click the Details link next to the UW_CAT_LOAD process just run. |  | The Process Detail page appears.
Run the IPS to CAT Load process - Report Only mode. | 28 | Click the View Log/Trace. |  | The View Log/Trace page appears.
Run the IPS to CAT Load process - Report Only mode. | 29 | Click the UW_IPS_Upload_XX.xls link |  | The IPS to CAT Upload Process excel report appears.
Run the IPS to CAT Load process - Report Only mode. | 30 | Review the output report. |  | Review the report to review Error, Warning, and Successful sections.
Run the IPS to CAT Load process - Report Only mode. | 31 | Verify information is correct in the output compared to information previously included in the IPS (see script UAT-ADM-05) | Record validated Employee IDs here: 1) 2) 3) 4) 5)
Run the IPS to CAT Load process - Process and Report mode | 32 | Navigate to the CAT IPS Load to CAT/AAP Page: Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Processes > IPS Load to CAT/AAP
Run the IPS to CAT Load process - Process and Report mode | 33 | Click the Add a New Value tab.
Run the IPS to CAT Load process - Process and Report mode | 34 | Enter a Run Control ID. | Any unique identifier (ex. your initials and the date)
Run the IPS to CAT Load process - Process and Report mode | 35 | Click the Add button. |  | Taken to the IPS Load to CAT/AAP page.
Run the IPS to CAT Load process - Process and Report mode | 36 | Select Process and Report mode. (This commits data to the CAT and generates an output .xls file.) | Report only mode will not load values to CAT or AAP.
Run the IPS to CAT Load process - Process and Report mode | 37 | Enter Fiscal Year.
Run the IPS to CAT Load process - Process and Report mode | 38 | Select 'Compensation Adjustment' as the File Type.
Run the IPS to CAT Load process - Process and Report mode | 39 | Enter or click the magnifying glass to select Business Unit.
Run the IPS to CAT Load process - Process and Report mode | 40 | Enter the File Description, which will be used to name the output file after the process runs. | Any identifier for the output report (ex.CAT Upload_YY_MM_DD)
Run the IPS to CAT Load process - Process and Report mode | 41 | Click the 'Upload File' link. |  | The 'File Attachment' Window appears.
Run the IPS to CAT Load process - Process and Report mode | 42 | Click 'Browse' on the 'File Attachment' window. |  | A 'choose file to upload' screen appears.
Run the IPS to CAT Load process - Process and Report mode | 43 | Navigate to the .CSV file created in steps 1-6 on the 'Choose File to Upload' screen. This file will begin with "IPS-CAT".
Run the IPS to CAT Load process - Process and Report mode | 44 | Click Open. |  | Return to the 'File Attachment' window.
Run the IPS to CAT Load process - Process and Report mode | 45 | Click Upload on the File Attachment window.
Run the IPS to CAT Load process - Process and Report mode | 46 | Wait while the file attaches.
Run the IPS to CAT Load process - Process and Report mode | 47 | Click Save.
Run the IPS to CAT Load process - Process and Report mode | 48 | Click Run. |  | Process Scheduler Request screen appears.
Run the IPS to CAT Load process - Process and Report mode | 49 | Click OK on the Process Scheduler Request screen. |  | IPS Load to CAT/AAP screen reappears.
Run the IPS to CAT Load process - Process and Report mode | 50 | Click the Process Monitor link. |  | The Process Monitor screen appears.
Run the IPS to CAT Load process - Process and Report mode | 51 | Click the Refresh button intermittently until the Run Status is Success, and the Distribution Status is Posted.
Run the IPS to CAT Load process - Process and Report mode | 52 | Click the Details link next to the UW_CAT_LOAD process just run. |  | The Process Detail page appears.
Run the IPS to CAT Load process - Process and Report mode | 53 | Click the View Log/Trace. |  | The View Log/Trace page appears.
Run the IPS to CAT Load process - Process and Report mode | 54 | Click the UW_IPS_Upload_XX.xls link |  | The IPS to CAT Upload Process excel report appears.
Run the IPS to CAT Load process - Process and Report mode | 55 | Review the output report. |  | Review the report to review Error, Warning, and Successful sections.
Run the IPS to CAT Load process - Process and Report mode | 56 | Verify information is correct in the output compared to information previously included in the IPS (see script UAT-ADM-05) | Record validated Employee IDs here: 1) 2) 3) 4) 5)

## UAT-ADM-08
Test Script ID: | UAT-ADM-08 |  | Overall Pass/Fail:
Test Script Description: | IPS Load to AAP |  | KB#: | 55923
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Processes > IPS Load to CAT/AAP
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Create CSV document to transfer IPS data to AAP | 1 | After making all vacant and other budget adjustment changes in the IPS, go to the IPS --> AAP tab.
Create CSV document to transfer IPS data to AAP | 2 | Drag the text string formula in column A down until the last corresponding row populated with employees in the Additional Adjustments Tab. Stop when you see a row like this: ;;;;;;;;;;----;
Create CSV document to transfer IPS data to AAP | 3 | Press the 'Click Here to Export File for AAP Upload' button |  | A 'Save As' box will appear on the screen.
Create CSV document to transfer IPS data to AAP | 4 | Name the document. The default naming format is "IPS-CAT Entry Output FileYYYY-MM-DD.CSV". Save as a .CSV (Comma Separated Value) document. |  | A message box 'Make sure this file looks correct' will appear.
Create CSV document to transfer IPS data to AAP | 5 | Press OK on the window that appears. |  | A Notepad file will appear on the screen. Note that the file name will begin with IPS-AAP.
Create CSV document to transfer IPS data to AAP | 6 | Exit out of the Notepad document that appears on the screen. Do not edit the file.
Run the IPS to AAP Load process - Report Only mode. | 7 | Navigate to the CAT IPS Load to CAT/AAP Page: Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Processes > IPS Load to CAT/AAP
Run the IPS to AAP Load process - Report Only mode. | 8 | Click the Add a New Value tab.
Run the IPS to AAP Load process - Report Only mode. | 9 | Enter a Run Control ID. | Any unique identifier (ex. your initials and the date)
Run the IPS to AAP Load process - Report Only mode. | 10 | Click the Add button. |  | Taken to the IPS Load to CAT/AAP page.
Run the IPS to AAP Load process - Report Only mode. | 11 | Select Report Only mode. (This processes data without committing data to the AAP. It generates an output .xls file that allows the data and any possible errors to be reviewed.) |  | Note: Report only mode will not load values to CAT or AAP.
Run the IPS to AAP Load process - Report Only mode. | 12 | Enter Fiscal Year.
Run the IPS to AAP Load process - Report Only mode. | 13 | Select Additional Adjustments as the File Type.
Run the IPS to AAP Load process - Report Only mode. | 14 | Enter or click the magnifying glass to select Business Unit.
Run the IPS to AAP Load process - Report Only mode. | 15 | Enter the File Description, which will be used to name the output file after the process runs. | Any identifier for the output report (ex.AAP Upload_YY_MM_DD)
Run the IPS to AAP Load process - Report Only mode. | 16 | Click the 'Upload File' link. |  | The 'File Attachment' Window appears.
Run the IPS to AAP Load process - Report Only mode. | 17 | Click 'Browse' on the 'File Attachment' window. |  | A 'choose file to upload' screen appears.
Run the IPS to AAP Load process - Report Only mode. | 18 | Navigate to the .CSV file created in steps 1-6 on the 'Choose File to Upload' screen. This file will begin with "IPS-AAP".
Run the IPS to AAP Load process - Report Only mode. | 19 | Click Open. |  | Return to the 'File Attachment' window.
Run the IPS to AAP Load process - Report Only mode. | 20 | Click Upload on the File Attachment window.
Run the IPS to AAP Load process - Report Only mode. | 21 | Wait while the file attaches.
Run the IPS to AAP Load process - Report Only mode. | 22 | Click Save.
Run the IPS to AAP Load process - Report Only mode. | 23 | Click Run. |  | Process Scheduler Request screen appears.
Run the IPS to AAP Load process - Report Only mode. | 24 | Click OK on the Process Scheduler Request screen. |  | IPS Load to CAT/AAP screen reappears.
Run the IPS to AAP Load process - Report Only mode. | 25 | Click the Process Monitor link. |  | The Process Monitor screen appears.
Run the IPS to AAP Load process - Report Only mode. | 26 | Click the Refresh button intermittently until the Run Status is Success, and the Distribution Status is Posted.
Run the IPS to AAP Load process - Report Only mode. | 27 | Click the Details link next to the UW_CAT_LOAD process just run. |  | The Process Detail page appears.
Run the IPS to AAP Load process - Report Only mode. | 28 | Click the View Log/Trace. |  | The View Log/Trace page appears.
Run the IPS to AAP Load process - Report Only mode. | 29 | Click the UW_IPS_Upload_XX.xls link |  | The IPS to CAT/AAP Upload Process excel report appears.
Run the IPS to AAP Load process - Report Only mode. | 30 | Review the output report. |  | Review the report to review Error, Warning, and Successful sections.
Run the IPS to AAP Load process - Report Only mode. | 31 | Verify information is correct in the output compared to information previously included in the IPS (see script UAT-ADM-06)
Run the IPS to AAP Load process - Process and Report mode. | 32 | Navigate to the CAT IPS Load to CAT/AAP Page: Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Processes > IPS Load to CAT/AAP
Run the IPS to AAP Load process - Process and Report mode. | 33 | Click the Add a New Value tab.
Run the IPS to AAP Load process - Process and Report mode. | 34 | Enter a Run Control ID. | Any unique identifier (ex. your initials and the date)
Run the IPS to AAP Load process - Process and Report mode. | 35 | Click the Add button. |  | Taken to the IPS Load to CAT/AAP page.
Run the IPS to AAP Load process - Process and Report mode. | 36 | Select Process and Report mode. (This commits data to the CAT and generates an output .xls file.) | Process and Report mode will load values to CAT or AAP.
Run the IPS to AAP Load process - Process and Report mode. | 37 | Enter Fiscal Year.
Run the IPS to AAP Load process - Process and Report mode. | 38 | Select Additional Adjustments as the File Type.
Run the IPS to AAP Load process - Process and Report mode. | 39 | Enter or click the magnifying glass to select Business Unit.
Run the IPS to AAP Load process - Process and Report mode. | 40 | Enter the File Description, which will be used to name the output file after the process runs. | Any identifier for the output report (ex.AAP Upload_YY_MM_DD)
Run the IPS to AAP Load process - Process and Report mode. | 41 | Click the 'Upload File' link. |  | The 'File Attachment' Window appears.
Run the IPS to AAP Load process - Process and Report mode. | 42 | Click 'Browse' on the 'File Attachment' window. |  | A 'choose file to upload' screen appears.
Run the IPS to AAP Load process - Process and Report mode. | 43 | Navigate to the .CSV file created in steps 1-6 on the 'Choose File to Upload' screen. This file will begin with "IPS-AAP".
Run the IPS to AAP Load process - Process and Report mode. | 44 | Click Open. |  | Return to the 'File Attachment' window.
Run the IPS to AAP Load process - Process and Report mode. | 45 | Click Upload on the File Attachment window.
Run the IPS to AAP Load process - Process and Report mode. | 46 | Wait while the file attaches.
Run the IPS to AAP Load process - Process and Report mode. | 47 | Click Save.
Run the IPS to AAP Load process - Process and Report mode. | 48 | Click Run. |  | Process Scheduler Request screen appears.
Run the IPS to AAP Load process - Process and Report mode. | 49 | Click OK on the Process Scheduler Request screen. |  | IPS Load to CAT/AAP screen reappears.
Run the IPS to AAP Load process - Process and Report mode. | 50 | Click the Process Monitor link. |  | The Process Monitor screen appears.
Run the IPS to AAP Load process - Process and Report mode. | 51 | Click the Refresh button intermittently until the Run Status is Success, and the Distribution Status is Posted.
Run the IPS to AAP Load process - Process and Report mode. | 52 | Click the Details link next to the UW_CAT_LOAD process just run. |  | The Process Detail page appears.
Run the IPS to AAP Load process - Process and Report mode. | 53 | Click the View Log/Trace. |  | The View Log/Trace page appears.
Run the IPS to AAP Load process - Process and Report mode. | 54 | Click the UW_IPS_Upload_XX.xls link |  | The IPS to CAT/AAP Upload Process excel report appears.
Run the IPS to AAP Load process - Process and Report mode. | 55 | Review the output report. |  | Review the report to review Error, Warning, and Successful sections.
Run the IPS to AAP Load process - Process and Report mode. | 56 | Verify information is correct in the output compared to information previously included in the IPS (see script UAT-ADM-06) | Record validated Employee IDs here: 1) 2) 3) 4) 5)

## UAT-ADM-09A
Test Script ID: | UAT-ADM-09A |  | Overall Pass/Fail:
Test Script Description: | CAT Page - Find an Existing Value |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Page
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Find existing value in the CAT | 1 | Navigate to Workforce Administration>UW External HR Systems> Compensation Admin Tool> CAT Page.
Find existing value in the CAT | 2 | Select the Find an Existing Value tab.
Find existing value in the CAT | 3 | Select the desired information for the Fiscal Year field. | 2017
Find existing value in the CAT | 4 | Enter employee ID in the Empl ID field. | Select employee previously validated in last step of script UAT-ADM-07. 1) 2) 3) 4) 5)
Find existing value in the CAT | 5 | Select Search to return results. |  | Returns search results if criteria identifies multiple employee records. Directs user to the CAT page if the search criteria identifies one employee.
Find existing value in the CAT | 6 | Click the link to the employee's CAT record, if applicable. |  | Directs user to the CAT page if the search criteria identifies one employee.
Review the Employee Attributes section on the Employee Data Page | 7 | Note the basic job related attributes about the selected Employee Record/Job. |  | Employee job attributes include: - Fiscal Year - Business Unit - Empl Class - Name - HRS Home Dept - Pay Basis - Empl ID & Rcd # - Job Code - Expected Job End Dt - Position - Annual Min and Max - Other Active Jobs Indicator
Review the Employee Attributes section on the Employee Data Page | 8 | Note the Useful Links below the job related attributes. |  | Directs user to the following page (for users with appropriate security access); test accounts currently do not have this access - HRS Job Data Page - HRS Workforce Summary - HRS Multiple Summary
Review the Recent and Future HR/Compensation Transactions section | 9 | Note the Job changes reflected in the Recent and Future HR/Compensation Transactions. |  | Displays Hires, Transfers, Terminations, Leave of Absence, Return from Leave and Short Work Break as a single row
Review the Recent and Future HR/Compensation Transactions section | 10 | Select the View All link on the Recent and Future HR/Compensation Transaction section, if applicable. |  | Displays all transactions meeting the criteria for this section within the last 18 months
Review the Compensation and Funding Data section | 11 | Review the Planned FTE. |  | Total Planned FTE cannot be greater than 1.
Review the Compensation and Funding Data section | 12 | Confirm or select input for Planned Title. |  | Planned Title defaults to the employee's title in HRS. Can be edited via the IPS upload or manually on the CAT Page.
Review the Compensation and Funding Data section | 13 | If desired, change Planned Title by using the search tool to search all available HRS titles.
Review the Compensation and Funding Data section | 14 | Check or uncheck the box for Add to Continuing Staff Basis. |  | Includes employee’s salary in the Continuing Staff Base calculation and loads to the CAT Summary Page as part of the CSB. Any employee that is eligible for merit should have this box checked to be included in the CSB.
Review the Compensation Change section | 15 | Determine if all desired compensation changes are included and accurate. |  | Displays three rows by default.
Review the Compensation Change section | 16 | Select the View All link on the Compensation Change section, if applicable. |  | Displays all previously entered increases.
Add Compensation Change | 17 | Click the “+” button on the right side of the table to add another row. |  | Defaults to blank Action Reason, and Change Amount and Change Percent fields Action field populates automatically with Pay Rate Change as the value
Add Compensation Change | 18 | Select the desired value into the Action Reason field.
Add Compensation Change | 19 | Select the desired value into the Change Amount or Change Percent tabs. |  | Changes to Change Amount will calculate Change Percent accordingly, and vice versa
Review the Compensation Change section | 20 | Review the Rate Calculation Type (either "Cumulative" or "Off of Original Base") to verify the rate increases have been applied in the right order. |  | When using the Off of Original Base method, if included, Merit should be applied first. When using Cumulative method, Merit should be applied last.
Review the Compensation Change section | 21 | To reorder entries, use the "-" button to delete misplaced entries and the "+" button to re-add them in the correct order. |  | Automatically calculates the Comprate (Annual Rate for A, C basis and Hourly Rate for H basis) and Annual Rate Adjusted for FTE (Budgeted Amount, or what the employee will actually get paid over the next fiscal year) at the bottom of the Compensation Change section, as well as the budgeted amount in the Funding Change section.
Review the Compensation Change section | 22 | Check Ok to Load to HRS. |  | At the end of the Comp Admin cycle all compensation changes with a checked Ok to Load to HRS box will load into HRS, effective the first of the upcoming fiscal year. An audit stamp will appear underneath the Compensation Change section displaying the Empl ID and name of the last person to apply changes to it as well as the date and time that the changes occurred.
Add Funding Change | 23 | View the Funding Change section. |  | Funding rows can either be populated from the IPS Upload process or entered manually.
Add Funding Change | 24 | Select the "+" button to manually enter a new row. |  | All fields populate as blank when a new row is added in the Funding Change section.
Add Funding Change | 25 | Select the desired GL Business Unit, Fund, Department, Program, Project and Distribution % for the funding row in the Funding Change section. |  | ·
Add Funding Change | 26 | Note that the bottom of the Funding Change section displays Total Distribution %, Total Budgeted Amount and Total Budgeted FTE.
Add Funding Change |  | As necessary, use the "-" button to delete a funding row and the "+" button to add one.
Add Funding Change | 27 | Ensure that Total Distribution % = 100%.
Add Funding Change | 28 | Note that Budgeted FTE = Distribution % on that split * Total Planned FTE.
Add Funding Change | 29 | Note that Budgeted Amount is calculated by Budgeted FTE * Full Time Rate.
Add Funding Change | 30 | Note that Distribution % = Budgeted FTE * Total Planned FTE.
Add Funding Change | 31 | Check Ok to Load to HRS. |  | At the end of the Comp Admin cycle all funding rows for an employee with a checked Ok to Load to HRS box will load into HRS, effective the first of the upcoming fiscal year.
Add Funding Change | 32 | Tab out of Budgeted FTE, Budgeted Amount or Distribution % to populate the other two.
Add Funding Change | 33 | Select the View All tab to display all previously entered funding splits. |  | The Funding Change section defaults to display 3 funding splits.
Add CAT Comments | 36 | Use the Comments box at the bottom of the CAT Page to keep notes about the particular Employee Record. Users should use name, initials, or Empl ID after their comment followed by “///” for separation and organization.
Save CAT Page | 34 | Select Save to apply changes made to CAT Page. |  | An audit stamp will appear underneath the Funding Change section displaying the Empl ID and name of the last person to apply changes to it as well as the date and time that the changes occurred.
Review the CAT Errors | 35 | Take note of CAT Error pop-up message(s).
Review the CAT Errors | 37 | Notice that the Box labeled CAT Errors will be populated if errors are found on the page. |  | Any identified errors will be categorized as CAT Job, CAT Comp, or CAT Funding errors.
Review the Funding Edits section | 38 | Use the Funding Edits Status to determine whether a funding row has passed SFS edits. |  | Funding rows with status of SFS Edits Unverified will be checked nightly against SFS combination edits. Rows with status of SFS Edits Unverified that fail the check against SFS combination edits will be set to Funding Edits Status of SFS Edits Failed. Rows with status of SFS Edits Unverified that pass the test against SFS chartfield and combination edits will be set to Funding Edits Status of SFS Edits Passed.
Review the Funding Edits section | 39 | Note that all funding rows added during the IPS Upload process will be set to status of SFS Edits Unverified. |  | The Funding Edits Status, for all funding rows tested when the page is saved, will be updated to reflect any changes that have occurred.
Review the Funding Edits section | 40 | Select Save to test all newly added funding rows and existing SFS Edits Unverified or SFS Edits Failed rows against SFS combination edits.

## UAT-ADM-09B
Test Script ID: | UAT-ADM-09B |  | Overall Pass/Fail:
Test Script Description: | CAT Page - Enter a New Value |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Workforce Administration>UW External HR Systems> Compensation Admin Tool> CAT Page
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Add a new value in the CAT | 1 | Navigate to Workforce Administration>UW External HR Systems> Compensation Admin Tool> CAT Page.
Add a new value in the CAT | 2 | Refer to the employees recorded in the last step of UAT-ADM-05. | Record added Employee IDs here: 1) 2) 3) 4) 5)
Add a new value in the CAT | 3 | Select the Add a New Value tab.
Add a new value in the CAT | 4 | Click the search tool next to any field to search for possible values. |  | Brings up search window
Add a new value in the CAT | 5 | Enter Fiscal Year, Empl ID, and Empl Rcd Nbr. | 2017; Employee from Script UAT-ADM-05
Add a new value in the CAT | 6 | Select Add to create a new record.
Review the Employee Attributes section on the Employee Data Page | 7 | Note the basic job related attributes about the selected Employee Record/Job. |  | Employee job attributes include: - Fiscal Year - Business Unit - Empl Class - Name - HRS Home Dept - Pay Basis - Empl ID & Rcd # - Job Code - Expected Job End Dt - Position - Annual Min and Max - Other Active Jobs Indicator
Review the Employee Attributes section on the Employee Data Page | 8 | Note the Useful Links below the job related attributes. |  | Directs user to the following page (for users with appropriate security access) - HRS Job Data Page - HRS Workforce Summary - HRS Multiple Summary
Review the Recent and Future HR/Compensation Transactions section | 9 | Note the Job changes reflected in the Recent and Future HR/Compensation Transactions. |  | Displays Hires, Transfers, Terminations, Leave of Absence, Return from Leave and Short Work Break as a single row
Review the Recent and Future HR/Compensation Transactions section | 10 | Select the View All link on the Recent and Future HR/Compensation Transaction section, if applicable. |  | Displays all transactions meeting the criteria for this section within the last 18 months
Review the Compensation and Funding Data section | 11 | Review the Planned FTE. |  | Total Planned FTE cannot be greater than 1.
Review the Compensation and Funding Data section | 12 | Confirm or select input for Planned Title. |  | Planned Title defaults to the employee's title in HRS. Can be edited via the IPS upload or manually on the CAT Page.
Review the Compensation and Funding Data section | 13 | If desired, change Planned Title by using the search tool to search all available HRS titles.
Review the Compensation and Funding Data section | 14 | Check or uncheck the box for Add to Continuing Staff Basis. |  | Includes employee’s salary in the Continuing Staff Base calculation and loads to the CAT Summary Page as part of the CSB. Any employee that is eligible for merit should have this box checked to be included in the CSB.
Review the Compensation Change section | 15 | Determine if all desired compensation changes are included and accurate. |  | Displays three rows by default.
Review the Compensation Change section | 16 | Select the View All link on the Compensation Change section, if applicable. |  | Displays all previously entered increases.
Add Compensation Change | 17 | Click the “+” button on the right side of the table to add another row. |  | Defaults to blank Action Reason, and Change Amount and Change Percent fields Action field populates automatically with Pay Rate Change as the value
Add Compensation Change | 18 | Select the desired value into the Action Reason field.
Add Compensation Change | 19 | Select the desired value into the Change Amount or Change Percent tabs. |  | Changes to Change Amount will calculate Change Percent accordingly, and vice versa
Review the Compensation Change section | 20 | Review the Rate Calculation Type (either "Cumulative" or "Off of Original Base") to verify the rate increases have been applied in the right order. |  | When using the Off of Original Base method, if included, Merit should be applied first. When using Cumulative method, Merit should be applied last.
Review the Compensation Change section | 21 | To reorder entries, use the "-" button to delete misplaced entries and the "+" button to re-add them in the correct order. |  | Automatically calculates the Comprate (Annual Rate for A, C basis and Hourly Rate for H basis) and Annual Rate Adjusted for FTE (Budgeted Amount, or what the employee will actually get paid over the next fiscal year) at the bottom of the Compensation Change section, as well as the budgeted amount in the Funding Change section.
Review the Compensation Change section | 22 | Check Ok to Load to HRS. |  | At the end of the Comp Admin cycle all compensation changes with a checked Ok to Load to HRS box will load into HRS, effective the first of the upcoming fiscal year. An audit stamp will appear underneath the Compensation Change section displaying the Empl ID and name of the last person to apply changes to it as well as the date and time that the changes occurred.
Add Funding Change | 23 | View the Funding Change section. |  | Funding rows can either be populated from the IPS Upload process or entered manually.
Add Funding Change | 24 | Select the "+" button to manually enter a new row. |  | All fields populate as blank when a new row is added in the Funding Change section.
Add Funding Change | 25 | Select the desired GL Business Unit, Fund, Department, Program, Project and Distribution % for the funding row in the Funding Change section. |  | ·
Add Funding Change | 26 | Note that the bottom of the Funding Change section displays Total Distribution %, Total Budgeted Amount and Total Budgeted FTE.
Add Funding Change |  | As necessary, use the "-" button to delete a funding row and the "+" button to add one.
Add Funding Change | 27 | Ensure that Total Distribution % = 100%.
Add Funding Change | 28 | Note that Budgeted FTE = Distribution % on that split * Total Planned FTE.
Add Funding Change | 29 | Note that Budgeted Amount is calculated by Budgeted FTE * Full Time Rate.
Add Funding Change | 30 | Note that Distribution % = Budgeted FTE * Total Planned FTE.
Add Funding Change | 31 | Check Ok to Load to HRS. |  | At the end of the Comp Admin cycle all funding rows for an employee with a checked Ok to Load to HRS box will load into HRS, effective the first of the upcoming fiscal year.
Add Funding Change | 32 | Tab out of Budgeted FTE, Budgeted Amount or Distribution % to populate the other two.
Add Funding Change | 33 | Select the View All tab to display all previously entered funding splits. |  | The Funding Change section defaults to display 3 funding splits.
Add CAT Comments | 36 | Use the Comments box at the bottom of the CAT Page to keep notes about the particular Employee Record. Users should use name, initials, or Empl ID after their comment followed by “///” for separation and organization.
Save CAT Page | 34 | Select Save to apply changes made to CAT Page. |  | An audit stamp will appear underneath the Funding Change section displaying the Empl ID and name of the last person to apply changes to it as well as the date and time that the changes occurred.
Review the CAT Errors | 35 | Take note of CAT Error pop-up message(s).
Review the CAT Errors | 37 | Notice that the Box labeled CAT Errors will be populated if errors are found on the page. |  | Any identified errors will be categorized as CAT Job, CAT Comp, or CAT Funding errors.
Review the Funding Edits section | 38 | Use the Funding Edits Status to determine whether a funding row has passed SFS edits. |  | Funding rows with status of SFS Edits Unverified will be checked nightly against SFS combination edits. Rows with status of SFS Edits Unverified that fail the check against SFS combination edits will be set to Funding Edits Status of SFS Edits Failed. Rows with status of SFS Edits Unverified that pass the test against SFS chartfield and combination edits will be set to Funding Edits Status of SFS Edits Passed.
Review the Funding Edits section | 39 | Note that all funding rows added during the IPS Upload process will be set to status of SFS Edits Unverified. |  | The Funding Edits Status, for all funding rows tested when the page is saved, will be updated to reflect any changes that have occurred.
Review the Funding Edits section | 40 | Select Save to test all newly added funding rows and existing SFS Edits Unverified or SFS Edits Failed rows against SFS combination edits.

## UAT-ADM-10A
Test Script ID: | UAT-ADM-10A |  | Overall Pass/Fail:
Test Script Description: | Aditional Adjustments Page - Find an Existing Value |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > AAP Page
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Look up an existing Funding Department | 1 | Navigate to Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > AAP Page.
Look up an existing Funding Department | 2 | Select the Find an Existing Value tab.
Look up an existing Funding Department | 3 | Enter the desired search criteria.
Look up an existing Funding Department | 4 | Click the search tool next to any field to search for possible values. |  | Prompts search window.
Look up an existing Funding Department | 5 | Click Search to find results.
Add information to the Vacant Positions section | 6 | Click the “+” button on the right side of the Vacant Positions section. |  | Adds a new blank row to the Vacant Position section.
Add information to the Vacant Positions section | 7 | Select desired Adj. Type.
Add information to the Vacant Positions section | 8 | Use the search tool to select Position Number, if desired (field not required).
Add information to the Vacant Positions section | 9 | Use the search tool to select Job Code.
Add information to the Vacant Positions section | 10 | Use the search tool to select Pay Basis if desired (field not required).
Add information to the Vacant Positions section | 11 | Enter desired FTE.
Add information to the Vacant Positions section | 12 | Use the search tool to select Fund.
Add information to the Vacant Positions section | 13 | Use the search tool to select Prog.
Add information to the Vacant Positions section | 14 | Use the search tool to select Project if desired (field not required).
Add information to the Vacant Positions section | 15 | Enter desired Budgeted Amount.
Add information to the Vacant Positions section | 16 | Note that after entering the budgeted amount, the Full-Time Base is automatically calculated based on the entered FTE.
Add information to the Vacant Positions section | 17 | Enter desired Description for the vacant position.
Add information to the Vacant Positions section | 18 | As necessary, use the "-" button to delete a vacant position row and the "+" button to add one.
Add information to the Vacant Positions section | 19 | Click the Save button.
Add information to the Vacant Positions section | 20 | Note that if a vacant position is split funded, it will require one row for each funding string.
Add information to the Other Budget Adjustments section | 21 | Click the “+” button on the right side of the Other Budget Adjustments section. |  | Adds a new blank row to the Other Budget Adjustments section.
Add information to the Other Budget Adjustments section | 22 | Select desired Adj. Type.
Add information to the Other Budget Adjustments section | 23 | Enter desired FTE. Note that a negative value may be entered. The FTE field defaults to zero and is not editable for Adj. Types of Student Help or LTE.
Add information to the Other Budget Adjustments section | 24 | Use the search tool to select Fund.
Add information to the Other Budget Adjustments section | 25 | Use the search tool to select Prog.
Add information to the Other Budget Adjustments section | 26 | Use the search tool to select Project if desired (field not required).
Add information to the Other Budget Adjustments section | 27 | Enter desired Budgeted Amount.
Add information to the Other Budget Adjustments section | 28 | Note that after entering the budgeted amount, the Full-Time Base is automatically calculated based on the entered FTE.
Add information to the Other Budget Adjustments section | 29 | Enter desired Description for the vacant position.
Add information to the Other Budget Adjustments section | 30 | As necessary, use the "-" button to delete an Other Budget Adjustment row and the "+" button to add one.
Add information to the Other Budget Adjustments section | 31 | Click the Save button.
Add information to the Other Budget Adjustments section | 32 | Take note of any SFS Edit Error pop-up message(s), as these records will not be saved until a valid funding string combination is used for the given adjustment row.

## UAT-ADM-10B
Test Script ID: | UAT-ADM-10B |  | Overall Pass/Fail:
Test Script Description: | Aditional Adjustments Page - Enter a New Value |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > AAP Page
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Add a new Funding Department | 1 | Navigate to Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > AAP Page.
Add a new Funding Department | 2 | Select the Add a New Value tab.
Add a new Funding Department | 3 | Enter Fiscal Year, Business Unit, and Funding Department. | 2017; Tester's Business Unit; Tester's Funding Department
Add a new Funding Department | 4 | Click Add to create a new Funding Department.
Add information to the Vacant Positions section | 5 | Click the “+” button on the right side of the Vacant Positions section. |  | Adds a new blank row to the Vacant Position section.
Add information to the Vacant Positions section | 6 | Select desired Adj. Type.
Add information to the Vacant Positions section | 7 | Use the search tool to select Position Number, if desired (field not required).
Add information to the Vacant Positions section | 8 | Use the search tool to select Job Code.
Add information to the Vacant Positions section | 9 | Use the search tool to select Pay Basis.
Add information to the Vacant Positions section | 10 | Enter desired FTE.
Add information to the Vacant Positions section | 11 | Use the search tool to select Fund.
Add information to the Vacant Positions section | 12 | Use the search tool to select Prog.
Add information to the Vacant Positions section | 13 | Use the search tool to select Project if desired (field not required).
Add information to the Vacant Positions section | 14 | Enter desired Budgeted Amount.
Add information to the Vacant Positions section | 15 | Note that after entering the budgeted amount, the Full-Time Base is automatically calculated based on the entered FTE.
Add information to the Vacant Positions section | 16 | Enter desired Description for the vacant position.
Add information to the Vacant Positions section | 17 | As necessary, use the "-" button to delete a vacant position row and the "+" button to add one.
Add information to the Vacant Positions section | 18 | Click the Save button.
Add information to the Vacant Positions section | 19 | Note that if a vacant position is split funded, it will require one row for each funding string.
Add information to the Other Budget Adjustments section | 20 | Click the “+” button on the right side of the Other Budget Adjustments section. |  | Adds a new blank row to the Other Budget Adjustments section.
Add information to the Other Budget Adjustments section | 21 | Select desired Adj. Type.
Add information to the Other Budget Adjustments section | 22 | Enter desired FTE. Note that a negative value may be entered. The FTE field defaults to zero and is not editable for Adj. Types of Student Help or LTE.
Add information to the Other Budget Adjustments section | 23 | Use the search tool to select Fund.
Add information to the Other Budget Adjustments section | 24 | Use the search tool to select Prog.
Add information to the Other Budget Adjustments section | 25 | Use the search tool to select Project if desired (field not required).
Add information to the Other Budget Adjustments section | 26 | Enter desired Budgeted Amount.
Add information to the Other Budget Adjustments section | 27 | Note that after entering the budgeted amount, the Full-Time Base is automatically calculated based on the entered FTE.
Add information to the Other Budget Adjustments section | 28 | Enter desired Description for the vacant position.
Add information to the Other Budget Adjustments section | 29 | As necessary, use the "-" button to delete an Other Budget Adjustment row and the "+" button to add one.
Add information to the Other Budget Adjustments section | 30 | Click the Save button.
Add information to the Other Budget Adjustments section | 31 | Take note of any SFS Edit Error pop-up message(s), as these records will not be saved until a valid funding string combination is used for the given adjustment row.

## UAT-ADM-11
Test Script ID: | UAT-ADM-11 |  | Overall Pass/Fail:
Test Script Description: | HRS Compare Report |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External Systems > Compensation Administration Tool > CAT Reports > HRS Compare Report
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Run the HRS Compare Report | 1 | Navigate to Main Menu > Workforce Administration > UW External Systems > Compensation Administration Tool > CAT Reports > HRS Compare Report.
Run the HRS Compare Report | 2 | Click the Add a New Value tab to create a new Run Control ID.
Run the HRS Compare Report | 3 | Enter a Run Control ID. | Any unique identifier (ex. your initials and the date)
Run the HRS Compare Report | 4 | Click the Add button. |  | Run Control ID is created. Taken to the HRS Compare Report parameters page.
Run the HRS Compare Report | 5 | Enter the Effective Date as the first day of the upcoming fiscal year. | 2016-07-01
Run the HRS Compare Report | 6 | Select the desired information for the Business Unit field. | Tester's Business Unit
Run the HRS Compare Report | 7 | Select the desired information for the Division field. | Tester's Division
Run the HRS Compare Report | 8 | Select the desired information for the Department field (not required). | Tester's Department
Run the HRS Compare Report | 9 | Click the Select Values button employee class box. |  | Taken to the Employee Class selection page.
Run the HRS Compare Report | 10 | Click the Clear button.
Run the HRS Compare Report | 11 | Select the desired information for the Empl Class checkboxes. | University Staff employee values (CJ and CP) and FA/LI/AS employee values (FA, LI, and AS)
Run the HRS Compare Report | 12 | Click the OK button. |  | Return to the HRS Compare Report run control page.
Run the HRS Compare Report | 13 | Click the Run button. |  | Taken to the Process Scheduler Request page.
Run the HRS Compare Report | 14 | Click the OK button. |  | Return to the HRS Compare Report run control page.
Run the HRS Compare Report | 15 | Note the Process Instance number under the Process Instance link.
Run the HRS Compare Report | 16 | Click the Process Monitor link. |  | Taken to the Process Monitor page.
Run the HRS Compare Report | 17 | Click the Refresh button intermittently until the Run Status is Success, and the Distribution Status is Posted.
Run the HRS Compare Report | 18 | Click the Details link next to the UW_CAT_HRCM process just run. |  | Taken to the Process Detail page.
Run the HRS Compare Report | 19 | Click the View Log/Trace. |  | Taken to the View Log/Trace page.
Run the HRS Compare Report | 20 | Click the file named “hrs_compare_report_ProcessMonitor#.xls”. The “Process Monitor#” will be the seven digit code associated with the HRS Compare Report process just processed. |  | Note: there can be two excel outputs if there are employees with more than five funding sources.
Run the HRS Compare Report | 21 | Click Open to open the .xls file. If the file does not automatically open, you may need to bring up Excel and select Yes in the pop-up window. |  | This file contains all employees in the selected business unit, division, and department with a Job Data change submitted during the specified date span.
Run the HRS Compare Report | 22 | Save the HRS Compare Report.
Validate the HRS Compare Report Data | 23 | Review the data in the HRS Compare Report. |  | i. One row per emplid/emplrcd combination is displayed. ii. If the two fields are the same between HRS and the CAT, they will appear blank iii. If a change is due to a termination, only CAT columns will populate iv. If a change is due to a hire, only HRS columns will populate

## UAT-ADM-12
Test Script ID: | UAT-ADM-12 |  | Overall Pass/Fail:
Test Script Description: | Missing from CAT Report |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Reports > Missing from CAT Report
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Run the Missing from CAT Report | 1 | Navigate to Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Reports > Missing from CAT Report.
Run the Missing from CAT Report | 2 | Click the Add a New Value tab to create a new Run Control ID.
Run the Missing from CAT Report | 3 | Enter a Run Control ID. | Any unique identifier (ex. your initials and the date)
Run the Missing from CAT Report | 4 | Click the Add button. |  | Run Control ID is created. Taken to the Missing from CAT Report parameters page.
Run the Missing from CAT Report | 5 | Enter the Fiscal Year. | 2017
Run the Missing from CAT Report | 6 | Select the desired information for the Business Unit field. | Tester's Business Unit
Run the Missing from CAT Report | 7 | Select the desired information for the Division field (optional). | Tester's Division
Run the Missing from CAT Report | 8 | Select the desired information for the Department field (optional). | Tester's Department
Run the Missing from CAT Report | 9 | Click the Select Values button in the employee class box. |  | Taken to the Employee Class selection page.
Run the Missing from CAT Report | 10 | Click the Clear button.
Run the Missing from CAT Report | 11 | Select the desired information for the Empl Class checkboxes. | University Staff employee values (CJ and CP) and FA/LI/AS employee values (FA, LI, and AS)
Run the Missing from CAT Report | 12 | Click the OK button. |  | Return to the Missing from CAT Report run control page.
Run the Missing from CAT Report | 13 | Click Save button.
Run the Missing from CAT Report | 14 | Click the Run button. |  | Taken to the Process Scheduler Request page.
Run the Missing from CAT Report | 15 | Click the OK button. |  | Return to the Missing from CAT Report run control page.
Run the Missing from CAT Report | 16 | Click the Process Monitor link. |  | Taken to the Process Monitor page.
Run the Missing from CAT Report | 17 | Click the Refresh button intermittently until the Run Status is Success.
Run the Missing from CAT Report | 18 | Click the Details link next to the UW_CAT_MSRPT process just run. |  | Taken to the Process Detail page.
Run the Missing from CAT Report | 19 | Click the View Log/Trace. |  | Taken to the View Log/Trace page.
Run the Missing from CAT Report | 20 | Click the file named “cat_miss_rpt_ProcessMonitor#.xls”. The “Process Monitor#” will be the seven digit code associated with the Missing from CAT Report process just processed. |  | Note: there can be two excel outputs if there are employees with more than five funding sources.
Run the Missing from CAT Report | 21 | Click Open to open the .xls file. If the file does not automatically open, you may need to bring up Excel and select Yes in the pop-up window.
Run the Missing from CAT Report | 22 | Save the Missing from CAT Report.
Run the Missing from CAT Report | 23 | Review the data in the Missing from CAT Report. |  | i. Review each record, and determine if that employee is eligible for Merit or should be added to the CAT. ii. If a particular employee record should be added, navigate to WFA> Compensation Administration Tool> CAT Page > Add a Value. iii. Enter the empl id and empl rcd. iv. A blank CAT page will appear for the user to enter rate increases and funding information.

## UAT-ADM-13
Test Script ID: | UAT-ADM-13 |  | Overall Pass/Fail:
Test Script Description: | HRS Change Report |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External Systems > Compensation Administration Tool > CAT Reports > HRS Change Report
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Run the HRS Change Report | 1 | Navigate to Main Menu > Workforce Administration > UW External Systems > Compensation Administration Tool > CAT Reports > HRS Change Report.
Run the HRS Change Report | 2 | Click the Add a New Value tab to create a new Run Control ID.
Run the HRS Change Report | 3 | Enter a Run Control ID. | Any unique identifier (ex. your initials and the date)
Run the HRS Change Report | 4 | Click the Add button. |  | Run Control ID is created. Taken to the HRS Change Report parameters page.
Run the HRS Change Report | 5 | Select the desired information for the Fiscal Year field. | 2017
Run the HRS Change Report | 6 | Enter a From Date, prior to the start of the fiscal year. | 2016-02-01
Run the HRS Change Report | 7 | Enter a To Date, after the start of the fiscal year. | 2016-07-01
Run the HRS Change Report | 8 | Select the desired information for the Business Unit field. | Tester's Business Unit
Run the HRS Change Report | 9 | Select the desired information for the Division field. | Tester's Division
Run the HRS Change Report | 10 | Select the desired information for the Department field. | Tester's Department
Run the HRS Change Report | 11 | Click the Select Values button employee class box. |  | Taken to the Employee Class selection page.
Run the HRS Change Report | 12 | Click the Clear button.
Run the HRS Change Report | 13 | Select the desired information for the Empl Class checkboxes. | University Staff employee values (CJ and CP) and FA/LI/AS employee values (FA, LI, and AS)
Run the HRS Change Report | 14 | Click the OK button. |  | Return to the HRS Change Report run control page.
Run the HRS Change Report | 15 | Click the Run button. |  | Taken to the Process Scheduler Request page.
Run the HRS Change Report | 16 | Click the OK button. |  | Return to the HRS Change Report run control page.
Run the HRS Change Report | 17 | Note the Process Instance number under the Process Instance link.
Run the HRS Change Report | 18 | Click the Process Monitor link. |  | Taken to the Process Monitor page.
Run the HRS Change Report | 19 | Click the Refresh button intermittently until the Run Status is Success, and the Distribution Status is Posted.
Run the HRS Change Report | 20 | Click the Details link next to the UW_CAT_HRCH process just run. |  | Taken to the Process Detail page.
Run the HRS Change Report | 21 | Click the View Log/Trace. |  | Taken to the View Log/Trace page.
Run the HRS Change Report | 22 | Click the file named “hrs_change_report_ProcessMonitor#.xls”. The “Process Monitor#” will be the seven digit code associated with the HRS Change Report process just processed. |  | Note: there can be two excel outputs if there are employees with more than five funding sources.
Run the HRS Change Report | 23 | Click Open to open the .xls file. If the file does not automatically open, you may need to bring up Excel and select Yes in the pop-up window. |  | This file contains all employees in the selected business unit, division, and department with a Job Data change submitted during the specified date span.
Run the HRS Change Report | 24 | Save the HRS Change Report.
Run the HRS Change Report | 25 | Review the data in the HRS Change Report. |  | The report displays one row per emplid/emplrcd combination per row: i. For a new hire – only the updated fields will be populated. ii. For a termination – only the original fields will be populated. iii. For a transfer – both original and updated fields will be populated. iv. For a field that has not undergone change in HRS – both original and updated fields will be blank. v. If more than one ‘action/action reason’ has been entered in HRS in the defined time period, the most recent change to an emplid/emplrcd will appear.

## UAT-ADM-14
Test Script ID: | UAT-ADM-14 |  | Overall Pass/Fail:
Test Script Description: | Record Errors Report |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Reports > Record Errors Report
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Run the Record Errors Report | 1 | Navigate to Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Reports > Record Errors Report.
Run the Record Errors Report | 2 | Click the Add a New Value tab to create a new Run Control ID.
Run the Record Errors Report | 3 | Enter a Run Control ID. | Any unique identifier (ex. your initials and the date)
Run the Record Errors Report | 4 | Click the Add button. |  | Run Control ID is created. Taken to the Record Errors Report parameters page.
Run the Record Errors Report | 5 | Enter the Fiscal Year. | 2017
Run the Record Errors Report | 6 | Select the desired information for the Business Unit field. | Tester's Business Unit
Run the Record Errors Report | 7 | Select the desired information for the Division field (optional). | Tester's Division
Run the Record Errors Report | 8 | Select the desired information for the Department field (optional). | Tester's Department
Run the Record Errors Report | 9 | Click the Select Values button in the employee class box. |  | Taken to the Employee Class selection page.
Run the Record Errors Report | 10 | Click the Clear button.
Run the Record Errors Report | 11 | Select the desired information for the Empl Class checkboxes. | University Staff employee values (CJ and CP) and FA/LI/AS employee values (FA, LI, and AS)
Run the Record Errors Report | 12 | Click the OK button. |  | Return to the Record Errors Report run control page.
Run the Record Errors Report | 13 | Select the types of errors you wish you view in the output by checking the associated boxes.
Run the Record Errors Report | 14 | Press the Effective Dates button if compensation errors are included in the run control. | 2/10/2016 through 7/01/2016
Run the Record Errors Report | 15 | Click Save button.
Run the Record Errors Report | 16 | Click the Run button. |  | Taken to the Process Scheduler Request page.
Run the Record Errors Report | 17 | Click the OK button. |  | Return to the Record Errors Report run control page.
Run the Record Errors Report | 18 | Click the Process Monitor link. |  | Taken to the Process Monitor page.
Run the Record Errors Report | 19 | Click the Refresh button intermittently until the Run Status is Success, and the Distribution Status is Posted.
Run the Record Errors Report | 20 | Click the Details link next to the UW_CAT_RDERR process just run. |  | Taken to the Process Detail page.
Run the Record Errors Report | 21 | Click the View Log/Trace. |  | Taken to the View Log/Trace page.
Run the Record Errors Report | 22 | Click the file named “cat_record_errors_report_ProcessMonitor#.xls”. The “Process Monitor#” will be the seven digit code associated with the Record Errors Report process just processed. |  | Note: there can be two excel outputs if there are employees with more than five funding sources.
Run the Record Errors Report | 23 | Click Open to open the .xls file. If the file does not automatically open, you may need to bring up Excel and select Yes in the pop-up window. |  | This file contains all employees in the selected business unit, division, and department with a Record Error found during the specified date span.
Run the Record Errors Report | 24 | Save the Record Errors Report.
Run the Record Errors Report | 25 | Review the data in the Record Errors Report. |  | i. The report is divided by error type into four sections ii. Emplrcds will likely appear as multiple rows within each section because: a. Emplrcds with more than one error will appear as multiple rows on the report b. Compensation increases and funding splits are added as horizontal rows under each employee iii. Demographic data (columns 1-11) will repeat for every row for each employee record

## UAT-ADM-15
Test Script ID: | UAT-ADM-15 |  | Overall Pass/Fail:
Test Script Description: | CAT Position Report |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Reports > HRS to CAT Position Report
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Run the CAT Position Report | 1 | Navigate to Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Reports > HRS to CAT Position Report.
Run the CAT Position Report | 2 | Click the Add a New Value tab to create a new Run Control ID.
Run the CAT Position Report | 3 | Enter a Run Control ID. | Any unique identifier (ex. your initials and the date)
Run the CAT Position Report | 4 | Click the Add button. |  | Run Control ID is created. Taken to the CAT Position Report parameters page.
Run the CAT Position Report | 5 | Enter the Fiscal Year.
Run the CAT Position Report | 6 | Select the desired information for the Business Unit field. | Tester's Business Unit
Run the CAT Position Report | 7 | Select the desired information for the Division field (optional). | Tester's Division
Run the CAT Position Report | 8 | Enter the Fund Code (optional).
Run the CAT Position Report | 9 | Select the desired information for the Department field (optional). | Tester's Department
Run the CAT Position Report | 10 | Click the Select Values button in the employee class box. |  | Taken to the Employee Class selection page.
Run the CAT Position Report | 11 | Select the desired information for the Empl Class checkboxes. | University Staff employee values (CJ and CP) and FA/LI/AS employee values (FA, LI, and AS)
Run the CAT Position Report | 12 | Click the OK button. |  | Return to the Position Report run control page.
Run the CAT Position Report | 13 | Click Save button.
Run the CAT Position Report | 14 | Click the Run button. |  | Taken to the Process Scheduler Request page.
Run the CAT Position Report | 15 | Click the OK button. |  | Return to the CAT Position Report run control page.
Run the CAT Position Report | 16 | Click the Process Monitor link. |  | Taken to the Process Monitor page.
Run the CAT Position Report | 17 | Click the Refresh button intermittently until the Run Status is Success.
Run the CAT Position Report | 18 | Click the Details link next to the UW_CAT_POS process just run. |  | Taken to the Process Detail page.
Run the CAT Position Report | 19 | Click the View Log/Trace. |  | Taken to the View Log/Trace page.
Run the CAT Position Report | 20 | Click the file named “position_report_ProcessMonitor#.xls”. The “Process Monitor#” will be the seven digit code associated with the CAT Position Report process just processed. |  | Note: there can be two excel outputs if there are employees with more than five funding sources.
Run the CAT Position Report | 21 | Click Open to open the .xls file. If the file does not automatically open, you may need to bring up Excel and select Yes in the pop-up window. |  | This file contains the position of all employees in the selected business unit, division, and department found during the specified date span.
Run the CAT Position Report | 22 | Save the CAT Position Report.
Run the CAT Position Report | 23 | Review the data in the CAT Position Report. |  | i. Funding splits should list as rows beneath each empl record ii. Job and Demographic data will repeat for all funding split rows iii. Jobs from the CAT should be listed first, then vacant positions, then budgeted adjustments.

## UAT-ADM-16
Test Script ID: | UAT-ADM-16 |  | Overall Pass/Fail:
Test Script Description: | CAT Summary Reporting Page |  | KB#: | TBD
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Reports > Summary Reporting Page
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Run a CAT Summary Report | 1 | Navigate to Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Reports > Summary Reporting Page.
Run a CAT Summary Report | 2 | Use the search tool to select the desired information for Fiscal Year.
Run a CAT Summary Report | 3 | Click the Run button. |  | Displays the totals including all parameters "rolled up" in the selected Fiscal Year. Note: if a value was defaulted into the Division field, please skip to step 9.
Run a CAT Summary Report | 4 | Click the Drill Down radio button for Funding Division.
Run a CAT Summary Report | 5 | Note the Roll Up box for Funding Division stays checked.
Run a CAT Summary Report | 6 | Click the Run button. |  | Displays totals for each Funding Division in the tester's specific Business Funding Unit
Run a CAT Summary Report | 7 | Uncheck the Roll Up box for Funding Division. |  | Displays search tool for Funding Division under Selection Type
Run a CAT Summary Report | 8 | Use the search tool to enter desired Funding Division. | Tester's Funding Division (larger division recommended)
Run a CAT Summary Report | 9 | Click the Drill Down radio button for Funding Department.
Run a CAT Summary Report | 10 | Note the Roll Up box for Funding Department stays checked.
Run a CAT Summary Report | 11 | Click the Run button. |  | Displays totals for each Funding Department in the tester's specific Business Funding Unit and Funding Division
Run a CAT Summary Report | 12 | Uncheck the Roll Up box for Funding Department. |  | Displays search tool for Funding Department under Selection Type
Run a CAT Summary Report | 13 | Use the search tool to enter desired Funding Department. | Tester's Funding Department - five characters in X##### format (larger department recommended)
Run a CAT Summary Report | 14 | Keep the Drill Down radio button clicked for Fund.
Run a CAT Summary Report | 15 | Click the Run button. |  | Displays totals for each Funding Department in the tester's specific Business Funding Unit and Funding Division
Run a CAT Summary Report | 16 | Note that some departments may display multiple Funding Departments strings.
Run a CAT Summary Report | 17 | If applicable, click the Drill Down button at the far right of the Results section for a given string. |  | Autopopulates the search criteria for that specifc subdepartment and deselects the corresponding Drill Down button
Run a CAT Summary Report | 18 | Note that one must specify a Funding Business Unit to select a Funding Division, and both a Funding Business Unit and Funding Division to select a Funding Department. |  | Failure to specify necessary fields will result in a error message when the Run button is clicked.
Run a CAT Summary Report | 19 | Click the Clear Drill Down button in the Search Criteria Box. | Funding Business Unit OR Funding Business Unit and Funding Division OR Funding Business Unit and Funding Division and Funding Department
Run a CAT Summary Report | 20 | Click the Run button. |  | Displays totals for all unspecified, rolled up parameters for the specified parameters, not drilled down to any particular parameter
Run a CAT Summary Report | 21 | Click the Reset All button. |  | Clears all parameters except for the default Fiscal Year and Business Unit.
Run a CAT Summary Report | 22 | Click the Drill Down radio button for Empl Class.
Run a CAT Summary Report | 23 | Click the Run button. |  | Displays totals for all unspecified, rolled up parameters for each individual Empl Class string.
Run a CAT Summary Report | 24 | Click the Reset All button. |  | Clears all parameters except for the default Fiscal Year and Business Unit.
Run a CAT Summary Report | 25 | Uncheck the Roll Up box for Funding Business Unit. |  | Displays search tool for Funding Business Unit under Selection Type
Run a CAT Summary Report | 26 | Use the search tool to select desired Funding Business Unit. | Tester's Funding Business Unit
Run a CAT Summary Report | 27 | Press the Drill Down radio button for Fund, Program, Project Id, Staff Type, Empl Class, or Action Reason.
Run a CAT Summary Report | 28 | Click the Run button. |  | Displays totals for all unspecified, rolled up parameters within the specified Funding Business Unit drilled down to the chosen parameter.

## UAT-ADM-17
Test Script ID: | UAT-ADM-17 |  | Overall Pass/Fail:
Test Script Description: | Budget Summary (BSUM) |  | KB#: | N/A
Tested By: |  |  | Tested Date:
Environment Link: | N/A
Page Navigation: | N/A
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Review Budget Summary Data | 1 | Navigate to 3270 Budget System test environment.
Review Budget Summary Data | 2 | Login to 3270. |  | Successfully login to 3270 test system.
Review Budget Summary Data | 3 | Press F3.
Review Budget Summary Data | 4 | Type ZBSUM and click enter. |  | Directed to the Project Summary page.
Review Budget Summary Data | 5 | Enter 2 into the Page field.
Review Budget Summary Data | 6 | Type desired UDDS value and click enter. | Tester's UDDS (division letter only) | Page 2 showing total budget and FTE totals.
Review Budget Summary Data | 7 | Compare Budget Totals to the values on the CAT Summary Report Page. (Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Reports > Summary Reporting Page) |  | Budget Totals should nearly match CAT Summary Report page.
Review Budget Summary Data | 8 | Compare FTE Totals to values on the CAT Summary Report Page. (Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Reports > Summary Reporting Page) |  | FTE Totals should nearly match CAT Summary Report page.
Review Budget Summary Data | 9 | Type 27 into the Page field and click enter
Review Budget Summary Data | 10 | Compare Program Totals to values on the CAT Summary Report Page. (Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Reports > Summary Reporting Page) |  | Program Totals should nearly match CAT Summary Report page.

## UAT-ADM-18
Test Script ID: | UAT-ADM-18 |  | Overall Pass/Fail:
Test Script Description: | Query a CAT EPM View |  | KB#:
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/epqas-bd/signon.html
Page Navigation: | Main Menu > Reporting Tools > Query > Query Manager
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Query a CAT EPM View - CAT Current Funding View | 1 | Log in to the EPM Test Environment.
Query a CAT EPM View - CAT Current Funding View | 2 | Navigate to Main Menu > Reporting Tools > Query > Query Manager.
Query a CAT EPM View - CAT Current Funding View | 3 | Click the Create New Query link.
Query a CAT EPM View - CAT Current Funding View | 4 | Select the Description option to Search By and search for the CAT views. | CAT
Query a CAT EPM View - CAT Current Funding View | 5 | Click the Search button.
Query a CAT EPM View - CAT Current Funding View | 6 | Click the Add Record link next to the CAT Current Funding View. |  | Receive pop-up message regarding application of effect dating.
Query a CAT EPM View - CAT Current Funding View | 7 | Click the OK button. |  | Taken to the Query tab.
Query a CAT EPM View - CAT Current Funding View | 8 | Select the desired information to be returned with the Fields checkboxes.
Query a CAT EPM View - CAT Current Funding View | 9 | Click the Criteria tab and delete the prepopulated effective date criteria, and add any other desired criteria.
Query a CAT EPM View - CAT Current Funding View | 10 | Click the Run tab. |  | Results and desired fields are populated on page.
Query a CAT EPM View - CAT Current Funding View | 11 | Click the Download to Excel link at the top of the results table.
Query a CAT EPM View - CAT Current Funding View | 12 | Click the file named “download(#).xls”. The “#” will be the number of downloads processed during the current browser session. |  | This file contains all records in the selected view and all fields selected for the query.
Query a CAT EPM View - CAT Current Funding View | 13 | If the file does not automatically open, you may need to bring up Excel.
Query a CAT EPM View - CAT Current Funding View | 14 | Save the downloaded EPM output.
Query a CAT EPM View - CAT Current Funding View | 15 | Verify the field headers match what was selected for the query.
Query a CAT EPM View - CAT Current Funding View | 16 | Verify funding information is correct based on CAT page data for five employees (Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Page) | Record validated Employee IDs here: 1) 2) 3) 4) 5) | Column values should match the CAT Page.
Query a CAT EPM View - CAT Current Rate and Funding View | 17 | Navigate back to the Query Manager page.
Query a CAT EPM View - CAT Current Rate and Funding View | 18 | Click the Create New Query link.
Query a CAT EPM View - CAT Current Rate and Funding View | 19 | Select the Description option to Search By and search for the CAT views. | CAT
Query a CAT EPM View - CAT Current Rate and Funding View | 20 | Click the Search button.
Query a CAT EPM View - CAT Current Rate and Funding View | 21 | Click the Add Record link next to the CAT Current Rate and Funding View. |  | Receive pop-up message regarding application of effect dating.
Query a CAT EPM View - CAT Current Rate and Funding View | 22 | Click the OK button. |  | Taken to the Query tab.
Query a CAT EPM View - CAT Current Rate and Funding View | 23 | Select the desired information to be returned with the Fields checkboxes.
Query a CAT EPM View - CAT Current Rate and Funding View | 24 | Click the Criteria tab and delete the prepopulated effective date criteria, and add any other desired criteria.
Query a CAT EPM View - CAT Current Rate and Funding View | 25 | Click the Run tab. |  | Results and desired fields are populated on page.
Query a CAT EPM View - CAT Current Rate and Funding View | 26 | Click the Download to Excel link at the top of the results table.
Query a CAT EPM View - CAT Current Rate and Funding View | 27 | Click the file named “download(#).xls”. The “#” will be the number of downloads processed during the current browser session. |  | This file contains all records in the selected view and all fields selected for the query.
Query a CAT EPM View - CAT Current Rate and Funding View | 28 | If the file does not automatically open, you may need to bring up Excel.
Query a CAT EPM View - CAT Current Rate and Funding View | 29 | Save the downloaded EPM output.
Query a CAT EPM View - CAT Current Rate and Funding View | 30 | Verify the field headers match what was selected for the query.
Query a CAT EPM View - CAT Current Rate and Funding View | 31 | Verify rate and funding information is correct based on CAT page data for five employees (Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Page) | Record validated Employee IDs here: 1) 2) 3) 4) 5) | Column values should match the CAT Page.

## UAT-ADM-18B (hidden)
Test Script ID: | UAT-ADM-18B |  | Overall Pass/Fail:
Test Script Description: | EPM and Interactive Reporting - Interactive Reporting Views |  | KB#:
Tested By: |  |  | Tested Date:
Environment Link: | https://bi2.fastar.wisconsin.edu/workspace/index.jsp
Page Navigation: | N/A
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?

## UAT-ADM-19
Test Script ID: | UAT-ADM-19 |  | Overall Pass/Fail:
Test Script Description: | IPS Load Edit/Overwrite |  | KB#: | 54557
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Processes > IPS Edit/Replace CAT
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
IPS Load Edit/Overwrite | 1 | Navigate to Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Processes > IPS Edit/Replace CAT.
IPS Load Edit/Overwrite | 2 | Locate the previous version of the IPS saved in UAT-ADM-04, which contains the employees that require a compensation and/or funding change.
IPS Load Edit/Overwrite | 3 | “Save As” the current version of the IPS as a new version, and make changes in the new version.
IPS Load Edit/Overwrite | 4 | Edit the compensation and funding data in the IPS (Comp Admin Planning Tool Tab) that is incorrect, incomplete, or new to upload into the CAT. Refer to script UAT-ADM-05 for instruction on how to update the IPS, and note that only compensation adjustment and funding related fields may be edited by this process.
Update Compensation Rate and Funding Changes | 5 | Verify all the employee updates are included in IPS.
Prepare IPS File to Upload | 6 | Click the “IPS --> CAT” tab.
Prepare IPS File to Upload | 7 | Scroll to the bottom of this tab and delete any rows that appear as so: ;;;;;;;;;;----;; ;;;;;;;;;;----;; ;;;;;;;;;;----;; ;;;;;;;;;;----;;
IPS Load Edit/Overwrite | 8 | Press the “Click Here to Export File for CAT Page Upload” button.
IPS Load Edit/Overwrite | 9 | Save the output file “Name.CSV” under the file menu. | Any name for the IPS edit/overwrite file (ex. IPS-CAT Entry Output File_YY_MM_DD.CSV)
IPS Load Edit/Overwrite | 10 | Select Okay to the message: "Make sure the file looks correct."
IPS Load Edit/Overwrite | 11 | Close the file once the “Name.CSV” file will appears on the screen.
IPS Load Edit/Overwrite | 12 | Log in to HRS.
Run IPS Load Edit/Overwrite process in Report Mode | 13 | Navigate to IPS Edit/Replace process (Workforce Administration > UW External HR Systems > Compensation Admin Tool > IPS Edit/Replce)
Run IPS Load Edit/Overwrite process in Report Mode | 14 | Click the Add a New Value tab.
Run IPS Load Edit/Overwrite process in Report Mode | 15 | Enter a Run Control ID. | Any unique identifier (ex. your initials and the date)
Run IPS Load Edit/Overwrite process in Report Mode | 16 | Click the Add button. |  | Taken to the IPS Edit/Replace run control page.
Run IPS Load Edit/Overwrite process in Report Mode | 17 | Select the Report Only radio button. |  | Processes data without committing data to the CAT. It generates an output .xls file that allows the data and any possible errors to be reviewed
Run IPS Load Edit/Overwrite process in Report Mode | 18 | Confirm Fiscal Year should be automatically populated with the current budget planning year. | 2017
Run IPS Load Edit/Overwrite process in Report Mode | 19 | Select the appropriate “Data to Be Loaded" run control option. | •Select “Compensation” if only the compensation rate increase data is being changed (comprate increase $ amount). •Select “Funding” if only the funding distribution percentage data is being changed. •Select “Both” if both the compensation and funding data are being changed.
Run IPS Load Edit/Overwrite process in Report Mode | 20 | Select the appropriate “Data Load Option" run control option. | •Select “Edit” if the update method is being used. •Select “Replace All” if overwrite method is being used.
Run IPS Load Edit/Overwrite process in Report Mode | 21 | Confirm “Compensation Adjustment” automatically populates under Inbound File Upload Criteria
Run IPS Load Edit/Overwrite process in Report Mode | 22 | Select the desired information for the Business Unit field. | Tester's Business Unit
Run IPS Load Edit/Overwrite process in Report Mode | 23 | Enter the File Description, which will be used to name the output file after the process runs. | Any identifier for the output report (ex.CAT IPS Edit_YY_MM_DD)
Run IPS Load Edit/Overwrite process in Report Mode | 24 | Click the “UPLOAD FILE” link next to Attached File to browse for, select, and upload the CSV file from Step 1.
Run IPS Load Edit/Overwrite process in Report Mode | 25 | Click the “Save” button. |  | Process parameters save.
Run IPS Load Edit/Overwrite process in Report Mode | 26 | Click “Run” at the top right of the window.
Run IPS Load Edit/Overwrite process in Report Mode | 27 | Click “OK” at the bottom of the Process Scheduler Request page.
Run IPS Load Edit/Overwrite process in Report Mode | 28 | Note the process instance number under the Process Monitor link.
Run IPS Load Edit/Overwrite process in Report Mode | 29 | Click “Process Monitor” link.
Run IPS Load Edit/Overwrite process in Report Mode | 30 | Click the Refresh button intermittently until the Run Status is Success, and the Distribution Status is Posted.
Review the IPS Edit/Overwrite Output | 31 | Click the Details link next to the UW_CAT_LOAD process just run. |  | The Process Detail page appears.
Review the IPS Edit/Overwrite Output | 32 | Click the View Log/Trace. |  | The View Log/Trace page appears.
Review the IPS Edit/Overwrite Output | 33 | Click the UW_IPS_Upload_XX.xls link |  | The IPS to CAT Upload Process excel report appears.
Review the IPS Edit/Overwrite Output | 34 | Click “Yes" if an error message appears indicating that “The file you are trying to open…is in a different format than specified by the file extension.”
Review the IPS Edit/Overwrite Output | 35 | Review the output report. |  | Review the report to review Error, Warning, and Successful sections.
Run IPS Load Edit/Overwrite process in Process Mode | 36 | Return to IPS Edit/Replace process (Workforce Administration > UW External HR Systems > Compensation Admin Tool > IPS Edit/Replce)
Run IPS Load Edit/Overwrite process in Process Mode | 37 | Click the Search button on the Find an Existing Value tab.
Run IPS Load Edit/Overwrite process in Process Mode | 38 | Select a Run Control ID. | Use a previous run control
Run IPS Load Edit/Overwrite process in Process Mode | 39 | Select the Process and Report radio button. |  | Commits data to the CAT and generates an output .xls file.
Run IPS Load Edit/Overwrite process in Process Mode | 40 | Confirm Fiscal Year should be automatically populated with the current budget planning year. | 2017
Run IPS Load Edit/Overwrite process in Process Mode | 41 | Select the appropriate “Data to Be Loaded" run control option. | •Select “Compensation” if only the compensation rate increase data is being changed (comprate increase $ amount). •Select “Funding” if only the funding distribution percentage data is being changed. •Select “Both” if both the compensation and funding data are being changed.
Run IPS Load Edit/Overwrite process in Process Mode | 42 | Select the appropriate “Data Load Option" run control option. | •Select “Edit” if the update method is being used. •Select “Replace All” if overwrite method is being used.
Run IPS Load Edit/Overwrite process in Process Mode | 43 | Confirm “Compensation Adjustment” automatically populates under Inbound File Upload Criteria
Run IPS Load Edit/Overwrite process in Process Mode | 44 | Select the desired information for the Business Unit field. | Tester's Business Unit
Run IPS Load Edit/Overwrite process in Process Mode | 45 | Enter the File Description, which will be used to name the output file after the process runs. | Any identifier for the output report (ex.CAT IPS Edit_YY_MM_DD)
Run IPS Load Edit/Overwrite process in Process Mode | 46 | Click the “UPLOAD FILE” link next to Attached File to browse for, select, and upload the CSV file from Step 1.
Run IPS Load Edit/Overwrite process in Process Mode | 47 | Click the “Save” button. |  | Process parameters save.
Run IPS Load Edit/Overwrite process in Process Mode | 48 | Click “Run” at the top right of the window.
Run IPS Load Edit/Overwrite process in Process Mode | 49 | Click “OK” at the bottom of the Process Scheduler Request page.
Run IPS Load Edit/Overwrite process in Process Mode | 50 | Note the process instance number under the Process Monitor link.
Run IPS Load Edit/Overwrite process in Process Mode | 51 | Click “Process Monitor” link.
Run IPS Load Edit/Overwrite process in Process Mode | 52 | Click the Refresh button intermittently until the Run Status is Success, and the Distribution Status is Posted.
Review the IPS Edit/Overwrite Output | 53 | Click the Details link next to the UW_CAT_LOAD process just run. |  | The Process Detail page appears.
Review the IPS Edit/Overwrite Output | 54 | Click the View Log/Trace. |  | The View Log/Trace page appears.
Review the IPS Edit/Overwrite Output | 55 | Click the UW_IPS_Upload_XX.xls link |  | The IPS to CAT Upload Process excel report appears.
Review the IPS Edit/Overwrite Output | 56 | Click “Yes" if an error message appears indicating that “The file you are trying to open…is in a different format than specified by the file extension.”
Review the IPS Edit/Overwrite Output | 57 | Review the output report. |  | Review the report to review Error, Warning, and Successful sections.

## UAT-ADM-20
Test Script ID: | UAT-ADM-20 |  | Overall Pass/Fail:
Test Script Description: | Turn off Job Data Feed |  | KB#: | N/A
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Setup > Annual Setup
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Turn off Job Data Feed | 1 | Navigate to Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Setup > Annual Setup.
Turn off Job Data Feed | 2 | Click magnifying glass to select the Fiscal Year under the Find Existing Value tab. | 2017
Turn off Job Data Feed | 3 | Select the desired information for the Business Unit field. | Tester's Business Unit
Turn off Job Data Feed | 4 | Click Search.
Turn off Job Data Feed | 5 | Select the Data Freeze tab. |  | Returns the division list for selected business unit.
Turn off Job Data Feed | 6 | Click the Lock All button to stop the HRS data feed. |  | Data Feed Stopped? checkboxes are all checked.
Turn off Job Data Feed | 7 | Click Save. |  | Changes to the Data Freeze tab are saved.

## UAT-ADM-21A
Test Script ID: | UAT-ADM-21A |  | Overall Pass/Fail:
Test Script Description: | Lock out Users in a Unit |  | KB#: | N/A
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Setup > Lock Users
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Lock out Users in a Unit | 1 | Navigate to Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Setup > Lock Users.
Lock out Users in a Unit | 2 | Click magnifying glass to select or enter a Business Unit on the *HR Deptid field. | Tester's Business Unit. | Selected Business Unit value populates in the HR Deptid field.
Lock out Users in a Unit | 3 | Select the Security Role to lock, if desired. |  | Selected security role populates in the Security Role field.
Lock out Users in a Unit | 4 | Click magnifying glass to select or enter a HR Division or HR Department ID on the *HR Deptid field.
Lock out Users in a Unit | 5 | Click Search.
Lock out Users in a Unit | 6 | Scroll to right and click the Lock All button. |  | Lock users checkboxes are all checked.
Lock out Users in a Unit | 7 | Click Save. |  | Changes to the Lock Users page are saved.

## UAT-ADM-21B
Test Script ID: | UAT-ADM-21B |  | Overall Pass/Fail:
Test Script Description: | Lock out Users in an Institution |  | KB#: | N/A
Tested By: |  |  | Tested Date:
Environment Link: | https://test.ps.wisconsin.edu/psp/hrqa-bd/?cmd=login
Page Navigation: | Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Setup > Lock Users
Test Script Objective | Step Number | Action | Input Data Value | Expected Result | Pass or Fail?
Lock out Users in an Institution | 1 | Navigate to Main Menu > Workforce Administration > UW External HR Systems > Compensation Admin Tool > CAT Setup > Lock Users.
Lock out Users in an Institution | 2 | Click magnifying glass to select or enter a Business Unit on the *HR Deptid field. | Tester's Business Unit. | Selected Business Unit value populates in the HR Deptid field.
Lock out Users in an Institution | 3 | Select the Security Role to lock, if desired. |  | Selected security role populates in the Security Role field.
Lock out Users in an Institution | 4 | Confirm the Row Level Security field is populated to ALL. |  | Row Level Security defaults to ALL.
Lock out Users in an Institution | 5 | Click Search.
Lock out Users in an Institution | 6 | Scroll to right and click the Lock All button. |  | Lock users checkboxes are all checked.
Lock out Users in an Institution | 7 | Click Save. |  | Changes to the Lock Users page are saved.

## PassFail (hidden)
Pass
Fail