## 2019 Close Timeline (hidden)
University of Wisconsin System SFS Accounting Manual
Category: General Ledger |  |  | Effective Date: Updated Annually
Task or Process: FY2019 Year-End Closing Timeline Grid |  |  | Revision Date: Apr 24, 2019
Contact Information: Name - Ginger Hintz |  | Email - ghintz@uwsa.edu | Phone - 608-262-6010
The schedule below provides information about dates, processes, etc. that will occur during the close of fiscal year 2019.
Date | Event | Fiscal Impact | Issues | Person/Area Responsible
SFS performance may be slower than usual over FYE, due to month-end and year-end processing on top of normal daily processing.
Feb 1 | Nightly ETL of SFS data to WISDM begins for FY2020 | Set up FY20 in WISDM |  | SFS Staff
April 1 or before | Open FY20 edits for UWMSN | Add and check the edits in other environments, including SFTRAIN. |  | SFS Staff
Before April 29 | Load SFS tables w/FY rows | Add FY rows found under maintain EXTN tables |  | SFS Staff / Jacque Milski
May 1 | The Standard Budget Ledger for period 1 of FY20 is opened to allow BUs to begin posting budget journals. | UWSA opens Ledger for all BUs |  | Donna Fosshage
May 1 | BU's should begin closely monitoring encumbrance balances for all funds in SFS. You need to insure that the SFS balances are accurate by the time we get to the mid-July cutoff. | The SFS balances at end of FY19 will be reported to DOA by UWSA staff. Those balances also dictate the carryover encumbrance balances that may be established in SFS for FY20. Limitations: Any PO that has a balance less than $50 cannot be carried over. All FY2019 blanket orders must be cancelled before the mid-July closing. | Due to how DOA Star handles Allotments for Prior Year encumbrances, all purchase orders will be reviewed at the account level.
May 1 | UWSA, DoIT and HRS staff will ensure that all SFS fiscal year based control tables and calendars have been established for FY20 by this date. |  |  | Jacque Milski/Nou Vang
May 1 | The PO module for FY2020 is opened in SFS to allow BU's to begin creating new year POs. NOTE: This does not mean that Period 1 of the new fiscal year is open for GL processing. | New year POs can be created in the PO module |  | Denise McDonald - communicate to campus SFS Staff - open period
May 16 | Need to identify all projects that will expire at the end of June 30. Also, need list of all internal projects. | ·This will aid the process of POs for year end | Note: this item only applies to business units using the Grants modules (MSN, MIL, EXT) | need 7-1 end date Kirk Anderson
May 16 | May A Biweekly is processed | Salary and all fringe expense is charged to FY19 |  | HRS
May 23 | May Unclassified payroll is processed | Salary and all fringe expense is charged to FY19 |  | HRS
May 30 | May B Biweekly payroll is processed | Salary and all fringe expense is charged to FY19 |  | HRS
May 31 | Final day for processing FY19 purchase orders in SFS | Purchases made after May 31 (for goods and services related to the normal operations of the institution) that will be received and consumed by June 30 can be direct charged as FY19 expenses in SFS. |  | Denise McDonald
June 7 | Cutoff date for FY19 budget transfers that need UWSA approval | To guarantee the processing of any remaining FY19 budget transfers before the end of June, please submit your budget transfer requests by this date. Transfers received after this date will be processed as time allows. |  | Donna Fosshage
June 10 | The May accounting period is closed in SFS first thing in the morning | SFS business units (BU's) need to have all May journals posted |  | Julia Lengyel
June 13 | The June A Biweekly payroll is processed. | Health and Life fringe cost must be charged to FY20 Salary and all other fringe expense is charged to FY19 |  | HRS
June 14 | TER Deadline for TERs Audited Centrally | Allow adequate time for the TER audit process which may require resubmission and reapproval.
June 20 | The June regular Unclassified payroll is processed | Health and Life fringe cost must be charged to FY20 Salary and all other fringe expense is charged to FY19 except summer session salary and fringe expense will be charged to FY20 |  | HRS
June 21 | Update new AP, CR, GL table for the new fiscal year under Navigation - SFS Extensions >DOA STAR Interface > Use > DOA Period 13 Definitions |  |  | Julia Lengyel
June 22 | All FY19 salary encumbrance balances will be cancelled by this time by HRS staff. |  | Salary encumbrances will not be posted for the remainder of FY19. | Nou Vang and HRS
June 24-30 | BU's must not process any check cancels, voids, or stop payments during this period unless there is certainty that there are sufficient payment dollars to cover the negative dollar effect of those transactions. | These type of check related adjustment should be done in the new fiscal year (July 2 or later) if there is not assurance that a negative PY journal will not be created in the old year. | Failure to comply with this rule may result in PY journals that have a negative balance. We cannot interface negative balance data to DOA. | Laura Parman/Beth Vereb - communicate to Controllers and Bursars
June 27 | The June B Biweekly payroll is processed. | Health and Life fringe cost must be charged to FY20 Salary and all other fringe expense is charged to FY19 | Will be posted with 6-27 date to Period 12 | HRS
June 28 | Entry of June deposits against A/R is complete |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, EXT) | Kirk Anderson
June 28 | Pre-Close reconciliation of all balance sheets Accounts is completed. | GM - A/R and UAR | Note: this item only applies to business units using the Grants modules (MSN, MIL, EXT) | Kirk Anderson
June 28 | UWSA staff will open period 13 for all BU's except Madison. Madison staff will do the same for their BU. |  |  | Julia Lengyel, Susie Maloney
June 28 | The Pro-Card billing period that ends today will be the last one charged to FY2019 | Payment can be processed on July 2nd - 5th (FY20). Expense distribution journal will be posted in period 13 (FY19) | On July 1st, you will get the statement indicating the total amount due. Note: The only time the upload process will change the date to July 1 is when the cycle end dates are 6-28, 29 or 30. | Andy Struebel/Ginger
June 28 | JET Accounting dates change to July 1 at 4pm. For UWMSN it will remain the 13th period until 4pm on July 5. All other institutions the date will remain July 1 until the night of the 15th. |  |  | Susie Maloney
June 28 | Business Units run final Pay Cycle Manager process that will create FY19 'PY' journals. Pay Cycles (as many as desired) can be run up until 3:30 p.m. PY journal posting is performed after 4:00 p.m. |  | BUs must reconcile their Accounts Payable balance to unpaid AP vouchers. BUs that have Accounts Payable balances at end of the fiscal year must be able to track and verify that offsetting Accounts Payable transactions charged to the new fiscal year (in PY journals) do accurately bring the old fiscal year balances to zero. | Laura Parman/Beth Vereb
July 1 | This is the SFS accounting period calendar date that represents the 13th month. | All BU's must make certain that journals for the 13th period are assigned a journal date of July 1.
July 1 | No pay cycle or expense processing for either fiscal year may be performed on this date. |  |  | Laura Parman/Beth Vereb
July 1 | You must not cancel, void, or put a stop on any payments on this day!!! |  |  | Laura Parman/Beth Vereb
July 1 to 8 | UW Service Center (HRS) must not process payrolls in both fiscal years on the same night during the period of July 1 through July 8. |  |  | HRS
July 1 to 15 | BUs work on year end check list. Check list should be completed by July 15 (Period 13 close) | Check list certification due to UW System Controller by July 17 (see July 17)
July 1 | PO Rollover from FY2019 to 2020 is started for all business units. |  |  | Denise McDonald
July 2 | The SFS ledgers are opened for posting of FY20 journals and all other normal daily operations. |  |  | Julia Lengyel
July 3 | Final reconciliation of Accounts Payable to Project Costing is completed. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, EXT) | Kirk Anderson
July 3 | FY20 salary encumbrance initialization process will be started on this date by HRS staff. |  |  | Nou Vang and HRS
July 4 | H O L I D A Y
July 5 | BI Complete processing all invoices in PeopleSoft. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, EXT) | Kirk Anderson
July 5 | F&A and Fringe Allocations must be current. | All Errors Resolved | Note: this item only applies to business units using the Grants modules (MSN, MIL, EXT) | Kirk Anderson
July 5 | Complete Cash Application of FY19 payments | Determine cash application process after 7/16 (entered into the GL via manual journal entry for the A/R, Cash and Unapplied Cash accounts?) | Note: this item only applies to business units using the Grants modules (MSN, MIL, EXT) | Kirk Anderson
July 5 per HRS | This is the last day that FY19 Direct Retros can be processed through HRS (period 13). |  |  | HRS
July 5 to 15 | UWMSN Restricts use of JET tool by campus users |  |  | Susie Maloney
July 5 | All prior year purchase order encumbrance balances must be cleaned up by this date |  |  | Denise McDonald
July 5 | All PO Rollover "problem clean-up" is completed for all units |  |  | Denise McDonald
July 8 | The June accounting period in SFS is closed (early am) | BU's must have all final journals for June posted before this date |  | Julia Lengyel
July 11 | The July A Biweekly payroll is processed. | First full payroll to be entirely in FY20
July 12 - 15 | UWSA staff release FY20 pre-paid fringe data to be sent to DOA | UWSA staff will initiate this release by checking the appropriate boxes in the Summer Session and Prepaid Fringe Release Control panel of SFS Salary Maintenance. |  | Nou Vang
July 12 - 15 | UWSA staff release FY20 Summer Session salary and fringe data to be sent to DOA. | UWSA staff will initiate this release by checking the appropriate boxes in one of the Salary Maintenance panels of SFS. |  | Nou Vang
July 15 | All Institutions except Madison - Last day to process IUJ journals in JET. The fiscal year will change at 4 pm.
July 15 | UWMSN – First Day for FY 2020 for JET and Cost Transfer Tool |  |  | Susie Maloney
July 15 | All direct retros must be posted to SFS by this date. |  |  | HRS
July 15 | Final day for SFS BU's to post FY19 data in SFS (period 13). Journals entered in prior days must be posted. Any journals entered today must be posted during the day. All journals must be posted by 3:30 pm. Period 13 is closed in SFS at 4:00 pm. UWSA staff will verify that all FY19 journals are posted before closing the period. | All FY19 Fund 990 revenue distributions should be complete by this date. Fund 990 Cash Balance (account 6100) must net to zero. All Fund 998, Department PAYCLR balances must be at zero. All Fund 128 PRDFLT and PRSUSP must be zero. All Fund account 1000 must be zero. All Payroll Interface "default coding" balances must be at zero. Please see Fiscal Year Closing Process Checklist at: https://www.wisconsin.edu/financial-administration/download/fiscal_year_end/fiscal-year-end-closing-process-checklistFY16.pdf Checklist should be complete by today and must be submitted to the UW System Controller by July 17.
July 16 | BU's begin working on identifying any period 998 adjustments they will need to post to SFS. BU's should verify that end of year cash balances are properly accounted for in SFS. | Dollar amounts can be shifted between Program, DeptID, and Project codes within the same fund and major line. Transfers that cross state appropriations (Block grants) and/or account are not allowed. | Period 998 adjustments can be loaded to SFS by the BU, but must get UW System Controller approval before the journals can be posted. Period 998 adjustments must be completed by Aug. 15
July 17 through July 31 | UWSA staff begins final reconciliation with DOA. Final adjustments that affect BU's are identified and processed. | Final adjustment journals will be posted directly in SFS to period 13.
July 17 | Certified Year End Checklist is due to UW System Controller
July 17 | GL Run final fiscal year journal generation for all modules |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, EXT) | Kirk Anderson
July 17 | GL Enter manual post-close journal entries to update balance of Balance Sheet Accounts. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, EXT) | Kirk Anderson
July 18 | The July Reg Unclassified payroll is processed | All salary and fringe expense is charged to FY20.
July 19 | Final FY19 Fund 104 Budgets due |  |  | Donna Fosshage Carol Edquist
July 19 | MSN, MIL and EXT BU's must notify UWSA of their end of June fringe "pool" balances for Funds 133, 144, 233 and 161 by this date. | UWSA staff will use that data to make the transfer of fringe balances to the Systemwide fringe pool accounts | Balances for the comprehensive institutions remain at the institution | Connie Christianson
July 22 | UWSA staff begin preparations for moving the gift/grant/trust fringe "pool" DeptID balances out of the BU accounts and into the UWSYS accounts. Amounts shifted are based on end of June balances. | UWSA staff will make all of the needed journal entries in SFS to transfer the balances. |  | Connie Christianson
July 23 | Year End Checklist Checkout Completed By UWSA Staff | Institutions will be contacted for coding corrections as needed. |  | Lisa Fransee
July 30 | Second Check of Year End Checklist checkout |  |  | Lisa Fransee
August 2 | Last day UW can post FY2019 data in STAR
August 6 | UW's Form 78s Final Forms Available
August 1 through August 15 | UWSA staff clear 131 cash balances from BU accounts via period 998 adjustments
| Cash account balances in all GPR funds and SEG annual funds are zeroed via an SQR program run at UWSA | All GPR and SEG Annual fund/org balances for Cash (account 6100) should be at zero at the start of the new year. Verify by looking at data in period zero of the new year. | Funds involved are: 100, 101, 102, 103, 104, 106, 109, 110, 112, 116, 117, 118, 119, 126, 139, 163, 169, 171, 172, 174, 180, 188, 191, 301, 402, 403, 406, and 601
UWSA staff create period 998 journals to move 997 and 980 fringe clearing balances to their proper carryover DeptID
Staff at BU's work on getting carryover encumbrance budgets from FY19 loaded to FY20 in SFS
| Staff at BU's work on getting gift/grant/trust budgets loaded to FY20 in SFS | There should be no budget data loaded for accounts that are totally closed out.
| All "first pass" period 998 journals for FY19 are posted for all BU's. The BU's perform journal uploads to get the period 998 adjustments into SFS. UWSA staff review/approve the data and post the journals. | Account balances get moved to the funding that is appropriate/desired for carryover to the new fiscal year.
The fiscal year "close" process is run for all BU's (done by UWSA staff) so that the effect of the period 998 adjustments can be reviewed in period zero of FY20 and in WISDM.
Additional period 998 adjustments are created and posted as needed
The fiscal year close process is re-run for BU's as needed
All FY19 closing activity is expected to be completed by August 15
August 30 or earlier if possible | Transfer Cash From UWSYS 131, 132, 189 to AJE_LEDGER to cover GPO Shifts.
October 31 | Close WISDM - FY19 | WISDM team to confirm with UWSA staff before closing. |  | Scott Larson
VERY IMPORTANT
VERY IMPORTANT
First payroll Health/Life to New FY
VERY IMPORTANT
IMPORTANT
When processing IUJs in the 13th period remember to work with the other institutions involved
Option 1 (Preferred)
1) Process the payment on July 2nd - 5th through a regular pay cycle with a cash payment made in FY2020. Use account 7105; Vouchers Payable Between Years for the payment.
2) Process an Internal Transfer Journal (INT) in FY19 to clear the amount paid on 7105 and establish the expense on 3100. Account 3100 will be cleared when the reallocation/distribution journal is processed.
3) Institutions with a seven day reallocation period will receive the SBF file on July 8th. The file must be uploaded by July 12th and posted with a date of 7/1 to Period 13. Note: The only time the upload process will change the date to July 1 is when the cycle end dates are 6-28, 29 or 30.
Option 2
1) Process the payment on July 2nd - 5th through a regular pay cycle with a cash payment made in FY2020. Use account 3100 (or your default account code) as usual.
2) Process an Internal Transfer Journal (INT) in FY19 to clear account 3100 to account 7105. This will establish the balance sheet account that will carry over between years.
3) Process an Internal Transfer Journal (INT) in FY19 reversing the entry made in FY20. This will clear the 7105 and re-establish the expenditure on account 3100.
4) ) Institutions with a seven day reallocation period will receive the SBF file on July 8th. The file must be uploaded by July 12th and posted with a date of 7/1 to Period 13.
VERY IMPORTANT
VERY IMPORTANT

## 2020 Close Timeline (hidden)
University of Wisconsin System SFS Accounting Manual
Category: General Ledger |  |  | Effective Date: Updated Annually
Task or Process: FY2020 Year-End Closing Timeline |  |  | Revision Date: March XX, 2020
Contact Information: Name - Ginger Hintz |  | Email - ghintz@uwsa.edu | Phone - 608-262-6010
The schedule below provides information about dates, processes, etc. that will occur during the close of fiscal year 2020.
Date | Event | Fiscal Impact | Issues | Person/Area Responsible
SFS performance may be slower than usual over FYE, due to month-end and year-end processing on top of normal daily processing.
Feb 3 | Nightly ETL of SFS data to WISDM/WISER begins for FY2021 | Set up FY21 in WISDM/WISER |  | SFS Staff
Feb 17 | Open FY21 edits for all BUs | Add and check the edits in other environments, including SFTRAIN. |  | SFS Staff
Before April 29 | Load SFS tables w/FY rows | Add FY rows found under maintain EXTN tables |  | SFS Staff / Jacque Milski
May 1 | The Standard Budget Ledger for period 1 of FY21 is opened to allow BUs to begin posting budget journals. | UWSA opens Ledger for all BUs |  | Jessica Laeseke
May 1 | BUs should begin closely monitoring encumbrance balances for all funds in SFS. You need to ensure that the SFS balances are accurate by the time we get to the mid-July cutoff. | The SFS balances at end of FY20 will be reported to DOA by UWSA staff. Those balances also dictate the carryover encumbrance balances that may be established in SFS for FY21. Limitations: Any PO that has a balance less than $50 cannot be carried over. All FY2020 blanket orders must be cancelled before the mid-July closing. | Due to how DOA STAR handles Allotments for Prior Year encumbrances, all purchase orders will be reviewed at the account level.
May 1 | UWSA, DoIT and HRS staff will ensure that all SFS fiscal year based control tables and calendars have been established for FY21 by this date. |  |  | Jacque Milski/Nou Vang
May 1 | The PO module for FY2021 is opened in SFS to allow BUs to begin creating new year POs. NOTE: This does not mean that Period 1 of the new fiscal year is open for GL processing. | New year POs can be created in the PO module |  | Denise McDonald - communicate to campus SFS Staff - open period
May 16 | Need to identify all projects that will expire at the end of June 30. Also, need list of all internal projects. | This will aid the process of POs for year end | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | need 7-1 end date Kirk Anderson
May 14 | May A Biweekly is processed | Salary and all fringe expense is charged to FY20 |  | HRS
May 21 | May Unclassified payroll is processed | Salary and all fringe expense is charged to FY20 |  | HRS
May 28 | May B Biweekly payroll is processed | Salary and all fringe expense is charged to FY20 |  | HRS
May 29 | Final day for processing FY20 purchase orders in SFS | Purchases made after May 29 (for goods and services related to the normal operations of the institution) that will be received and consumed by June 30 can be direct charged as FY20 expenses in SFS. |  | Denise McDonald
June 4 | The May accounting period is closed in SFS first thing in the morning | SFS BUs need to have all May journals posted |  | Julia Lengyel
June 11 | The June A Biweekly payroll is processed. | Health and Life fringe cost must be charged to FY21 Salary and all other fringe expense is charged to FY20 |  | HRS
June 12 | Cutoff date for FY20 budget transfers that need UWSA approval | To guarantee the processing of any remaining FY20 budget transfers before the end of June, please submit your budget transfer requests by this date. Transfers received after this date will be processed as time allows. |  | Jessica Laeseke
June 15 | TER Deadline for TERs Audited Centrally | Allow adequate time for the TER audit process which may require resubmission and reapproval.
June 18 | The June regular Unclassified payroll is processed | Health and Life fringe cost must be charged to FY21 Salary and all other fringe expense is charged to FY20 except summer session salary and fringe expense will be charged to FY21 |  | HRS
June 19 | Update UW_DOA Period 13 table for AP, CR and GL transactions | Navigation - SFS Extensions >DOA STAR Interface > Use > DOA Period 13 Definitions |  | Julia Lengyel
June 19 | All FY20 salary encumbrance balances will be cancelled by this time by HRS staff. |  | Salary encumbrances will not be posted for the remainder of FY20. | Nou Vang and HRS
June 23-30 | BUs must not process any check cancels, voids, or stop payments during this period unless there is certainty that there are sufficient payment dollars to cover the negative dollar effect of those transactions. | These type of check related adjustments should be done in the new fiscal year (July 2 or later) if there is not assurance that a negative PY journal will not be created in the old year. | Failure to comply with this rule may result in PY journals that have a negative balance. We cannot interface negative balance data to DOA. | Laura Parman/Beth Vereb - communicate to Controllers and Bursars
June 25 | The June B Biweekly payroll is processed. | Health and Life fringe cost must be charged to FY21 Salary and all other fringe expense is charged to FY20 | Will be posted with 6-25 date to Period 12 | HRS
June 26 | The Pro-Card billing period that ends today will be the last one charged to FY2020 | Payment can be processed on June 29-30th (FY20). Expense distribution journal will be posted in period 13 (FY20) | On June 29th, you will get the statement indicating the total amount due. Note: The only time the upload process will change the date to July 1 is when the cycle end dates are 6-26, 27, 28, 29 or 30. | Andy Struebel/Ginger
June 30 | JET Accounting dates change to July 1 at 4pm. For UWMSN it will remain the 13th period until 4pm on July 8. All other institutions the date will remain July 1 until the night of the 15th. |  |  | Lea Erickson
June 30 | Business Units run final Pay Cycle Manager process that will create FY20 'PY' journals. Pay Cycles (as many as desired) can be run up until 3:30 p.m. PY journal posting is performed after 4:00 p.m. |  | BUs must reconcile their Accounts Payable balance to unpaid AP vouchers. BUs that have Accounts Payable balances at end of the fiscal year must be able to track and verify that offsetting Accounts Payable transactions charged to the new fiscal year (in PY journals) do accurately bring the old fiscal year balances to zero. | Laura Parman/Beth Vereb
June 30 | Entry of June deposits against A/R is complete |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
June 30 | Pre-Close reconciliation of all balance sheets Accounts is completed. | GM - A/R and UAR | Note: this item only applies to business units using the Grants modules (MSN, MIL,SYS) | Kirk Anderson
June 30 | UWSA staff will open period 13 for all BU's except Madison. Madison staff will do the same for their BU. |  |  | Julia Lengyel, Lea Erickson
July 1 | This is the SFS accounting period calendar date that represents the 13th month. | All BUs must make certain that journals for the 13th period are assigned a journal date of July 1.
July 1 | No pay cycle or expense processing for either fiscal year may be performed on this date. |  |  | Laura Parman/Beth Vereb
July 1 | You must not cancel, void, or put a stop on any payments on this day!!! |  |  | Laura Parman/Beth Vereb
July 1 to 13 | BUs work on year-end checklist. Checklist should be certified by July 13
July 1 | PO Rollover from FY2020 to 2021 is started for all business units. |  |  | Denise McDonald
July 2 | The SFS ledgers are opened for posting of FY21 journals and all other normal daily operations. |  |  | Julia Lengyel
July 3 | Final reconciliation of Accounts Payable to Project Costing is completed. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
July 4 | Floating Holiday
July 5 | FY21 salary encumbrance initialization process will be started on this date by HRS staff. |  |  | Nou Vang and HRS
July 6 | BI Complete processing all invoices in PeopleSoft. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
July 6 | F&A and Fringe Allocations must be current. | All Errors Resolved | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
July 6 | Complete Cash Application of FY20 payments | Determine cash application process after 7/16 (entered into the GL via manual journal entry for the A/R, Cash and Unapplied Cash accounts?) | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
July 6 | All prior year purchase order encumbrance balances must be cleaned up by this date |  |  | Denise McDonald
July 6 | All PO Rollover "problem clean-up" is completed for all units |  |  | Denise McDonald
July 6 | The June accounting period in SFS is closed (early am) | BUs must have all final journals for June posted before this date |  | Julia Lengyel
July 8 to 14 | UWMSN Restricts use of JET tool by campus users |  |  | Lea Erickson
July 9 per HRS | This is the last day that FY20 Direct Retros can be processed through HRS (period 13). |  |  | HRS
July 9 | The July A Biweekly payroll is processed. | First full payroll to be entirely in FY21
July 13 | Year-End Checklist is due for UWSA review
July 13 - 14 | UWSA review BUs' checklists | Institutions will be contacted for coding corrections as needed. |  | Connie Christianson
July 13 - 15 | UWSA staff release FY21 pre-paid fringe data to be sent to DOA | UWSA staff will initiate this release by checking the appropriate boxes in the Summer Session and Prepaid Fringe Release Control panel of SFS Salary Maintenance. |  | Nou Vang
July 13 - 15 | UWSA staff release FY21 Summer Session salary and fringe data to be sent to DOA. | UWSA staff will initiate this release by checking the appropriate boxes in one of the Salary Maintenance panels of SFS. |  | Nou Vang
July 15 | Review of Year-End Checklist is completed |  |  | Connie Christianson
July 15 | All Institutions except Madison - Last day to process IUJ journals in JET. The fiscal year will change at 4 pm.
July 15 | UWMSN – First Day for FY 2021 for JET and Cost Transfer Tool |  |  | Lea Erickson
July 15 | All direct retros must be posted to SFS by this date. |  |  | HRS
July 15 | Final day for SFS BUs to post FY20 data in SFS (period 13). Journals entered in prior days must be posted. Any journals entered today must be posted during the day. All journals must be posted by 3:30 pm. Period 13 is closed in SFS at 4:00 pm. UWSA staff will verify that all FY20 journals are posted before closing the period. | All FY20 Fund 990 revenue distributions should be complete by this date. Fund 990 Cash Balance (account 6100) must net to zero. All Fund 998, Department PAYCLR balances must be at zero. All Fund 128 PRDFLT and PRSUSP must be zero. All Fund account 1000 must be zero. All Payroll Interface "default coding" balances must be at zero. Please see Fiscal Year Closing Process Checklist at: https://www.wisconsin.edu/financial-administration/download/fiscal_year_end/Year-End-Checklist-2019-20.pdf Checklist must be submitted to the UW System Controller by July 13 and reviewed by July 15.
July 16 | BUs begin working on identifying any period 998 adjustments they will need to post to SFS. BUs should verify that end of year cash balances are properly accounted for in SFS. | Dollar amounts can be shifted between Program, DeptID, and Project codes within the same fund and major line. Transfers that cross state appropriations (Block grants) and/or account are not allowed. | Period 998 adjustments can be loaded to SFS by the BU, but must get UW System Controller approval before the journals can be posted. Period 998 adjustments must be completed by Aug. 14
July 16 through July 31 | UWSA staff begins final reconciliation with DOA. Final adjustments that affect BU's are identified and processed. | Final adjustment journals will be posted directly in SFS to period 13.
July 16 | The July Reg Unclassified payroll is processed | All salary and fringe expense is charged to FY21.
July 17 | GL Run final fiscal year journal generation for all modules |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
July 17 | GL Enter manual post-close journal entries to update balance of Balance Sheet Accounts. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL,SYS) | Kirk Anderson
July 20 | MSN and MIL BU's must notify UWSA of their end of June fringe "pool" balances for Funds 133, 144, 233 and 161 by this date. | UWSA staff will use that data to make the transfer of fringe balances to the Systemwide fringe pool accounts | Balances for the comprehensive institutions remain at the institution | Connie Christianson
July 22 | UWSA staff begin preparations for moving the gift/grant/trust fringe "pool" DeptID balances out of the BU accounts and into the UWSYS accounts. Amounts shifted are based on end of June balances. | UWSA staff will make all of the needed journal entries in SFS to transfer the balances. |  | Connie Christianson
August 1 through August 15 | UWSA staff clear 131 cash balances from BU accounts via period 998 adjustments
| Cash account balances in all GPR funds and SEG annual funds are zeroed via an SQR program run at UWSA with the exception of cash balance to cover any accruals. | All GPR and SEG Annual fund/org balances for Cash (account 6100) should be at zero at the start of the new year. Verify by looking at data in period zero of the new year. | Funds involved are: 100, 101, 102, 103, 104, 106, 109, 110, 112, 116, 117, 118, 119, 126, 139, 163, 164, 167, 168, 169, 171, 172, 174, 180, 188, 190, 191, 301, 402, 403, 406, and 601
UWSA staff create period 998 journals to move 997 and 980 fringe clearing balances to their proper carryover DeptID
Staff at BUs work on getting carryover encumbrance budgets from FY20 loaded to FY21 in SFS
| Staff at BUs work on getting gift/grant/trust budgets loaded to FY21 in SFS | There should be no budget data loaded for accounts that are totally closed out.
| All "first pass" period 998 journals for FY20 are posted for all BU's. The BUs perform journal uploads to get the period 998 adjustments into SFS. UWSA staff review/approve the data and post the journals. | Account balances get moved to the funding that is appropriate/desired for carryover to the new fiscal year.
The fiscal year "close" process is run for all BUs (done by UWSA staff) so that the effect of the period 998 adjustments can be reviewed in period zero of FY21 and in WISDM/WISER.
Additional period 998 adjustments are created and posted as needed
The fiscal year close process is re-run for BU's as needed
All FY20 closing activity is expected to be completed by August 15
August 3 | Run Year-End Close process for ADB calculation for DOA | Must be done first thing in the morning the first business day of August. The close must be reversed the same day. |  | Julia Lengyel
August 7 | Last day UW can post FY 2020 data in STAR |  |  | Julia Lengyel
August 11 | UW's Forms 78 Certified |  |  | Ginger Hintz
August 30 or earlier if possible | Transfer Cash From UWSYS 131 to AJE_LEDGER to cover GPO Shifts.
October 31 | Close WISDM/WISER - FY20 | WISDM/WISER team to confirm with UWSA staff before closing. |  | Renee Copes Scott Larson
Note on A19: Julia Lengyel: Set the date to Jan 1st in future years
Note on A76: Julia Lengyel: Billing period end date - 26th Statement received next business day - 29th Payment can be processed next two bsuiness days - 29-30 SBF file is received a week from the day the statement is received - July 6th
VERY IMPORTANT
VERY IMPORTANT
First payroll Health/Life to New FY
VERY IMPORTANT
IMPORTANT
When processing IUJs in the 13th period remember to work with the other institutions involved
Option 1 (Preferred)
1) Process the payment on June 29-30th through a regular pay cycle with a cash payment made in FY2020. If unable to process the payment by June 30th - See Option 2.
2) Institutions with a seven day reallocation period will receive the SBF file on July 6th. The file must be uploaded by July 10th and posted with a date of 7/1 to Period 13. Note: The only time the upload process will change the date to July 1 is when the cycle end dates are 6-26, 27, 28, 29 or 30.
Option 2
1) If unable to process the payment by June 30th - use account 3100 (or your default account code) as usual in FY2021.
2) Process an Internal Transfer Journal (INT) in FY21 to clear account 3100 to account 7105. This will establish the balance sheet account that will carry over between years.
3) Process an Internal Transfer Journal (INT) in FY20 reversing the entry made in FY21. This will clear the 7105 and re-establish the expenditure on account 3100.
4) ) Institutions with a seven day reallocation period will receive the SBF file on July 6th. The file must be uploaded by July 10th and posted with a date of 7/1 to Period 13.
VERY IMPORTANT
VERY IMPORTANT

## 2021 Close Timeline (hidden)
University of Wisconsin System SFS Accounting Manual
Category: General Ledger |  |  | Effective Date: Updated Annually
Task or Process: FY2021 Year-End Closing Timeline |  |  | Revision Date: April 2021
Contact Information: Name - Ginger Hintz |  | Email - ghintz@uwsa.edu | Phone - 608-262-6010
The schedule below provides information about dates, processes, etc. that will occur during the close of fiscal year 2021.
Date | Event | Fiscal Impact | Issues | Person/Area Responsible
SFS performance may be slower than usual over FYE, due to month-end and year-end processing on top of normal daily processing.
Jan 4 | Open FY22 edits for UWMSN | Add and check the edits in other environments, including SFTRAIN. |  | MSN in Production; SFS staff in other environments
January 31 | Send a reminder to BUs regarding dual-year edits in the STD_BUDGET ledger | BUs copy current year ORG_EDIT tree and name it ORG_EDFY with a 7/2/2021 effective date in order for dual edits in the STD_BUDGET ledger to work and for their budget office to load budgets for FY22. Both trees need to be maintained for the remainder of the fiscal year. |  | Jessica Laeseke
Feb 1 | Nightly ETL of SFS data to WISER begins for FY2022 | Set up FY22 in WISER |  | SFS Staff
April 1 | The PO module for FY22 is opened in SFS. Only Grant/Awards NEW YEAR Purchase Orders can be created in SFS; all other orders created in ShopUW+. CREATED RECORDS WILL NOT INTERFACE INTO SFS UNTIL 7-2-2021 |  |  | Denise McDonald - communicate to campus SFS Staff - open period
Before April 29 | Load SFS tables w/FY rows | Add FY rows found under maintain EXTN tables |  | SFS Staff / Jacque Milski
May 3 | The Standard Budget Ledger for period 1 of FY22 is opened to allow BUs to begin posting budget journals. | UWSA opens Ledger for all BUs |  | Jessica Laeseke
May 3 | BUs should begin closely monitoring encumbrance balances for all funds in SFS. You need to ensure that the SFS balances are accurate by the time we get to the mid-July cutoff. | The SFS balances at end of FY21 will be reported to DOA by UWSA staff. Those balances also dictate the carryover encumbrance balances that may be established in SFS for FY22. Limitations: Any PO that has a balance less than $50 cannot be carried over. All FY21 blanket orders must be cancelled before the mid-July closing. | Due to how DOA STAR handles Allotments for Prior Year encumbrances, all purchase orders will be reviewed at the account level.
May 3 | UWSA, DoIT and HRS staff will ensure that all SFS fiscal year based control tables and calendars have been established for FY22 by this date. |  |  | Jacque Milski/Nou Vang
May 13 | Need to identify all projects that will expire at the end of June 30. Also, need list of all internal projects. | This will aid the process of POs for year end | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | need 7-1 end date Kirk Anderson
May 13 | May A Biweekly is processed | Salary and all fringe expense is charged to FY21 |  | HRS
May 20 | May Unclassified payroll is processed | Salary and all fringe expense is charged to FY21 |  | HRS
May 26 | May B Biweekly payroll is processed | Salary and all fringe expense is charged to FY21 |  | HRS
May 31 | Final day for processing FY21 orders | FINAL DAY FOR PROCESSING CURRENT YEAR PURCHASE ORDERS If you have an invoice, create a Cash with Order PO or complete a Direct Payment |  | Denise McDonald
June 4 | The May accounting period is closed in SFS first thing in the morning | SFS BUs need to have all May journals posted |  | Julia Lengyel
June 10 | The June A Biweekly payroll is processed. | Health and Life fringe cost must be charged to FY22 Salary and all other fringe expense is charged to FY21 |  | HRS
June 10 | Cutoff date for FY21 budget transfers that need UWSA approval | To guarantee the processing of any remaining FY21 budget transfers before the end of June, please submit your budget transfer requests by this date. Transfers received after this date will be processed as time allows. |  | Jessica Laeseke
June 15 | TER Deadline for TERs Audited Centrally | Allow adequate time for the TER audit process which may require resubmission and reapproval.
June 17 | The June regular Unclassified payroll is processed | Health and Life fringe cost must be charged to FY22 Salary and all other fringe expense is charged to FY21 except summer session salary and fringe expense will be charged to FY22 |  | HRS
June 18 | Update UW_DOA Period 13 table for AP, CR and GL transactions | Navigation - SFS Extensions >DOA STAR Interface > Use > DOA Period 13 Definitions |  | Julia Lengyel
June 21 | All FY21 salary encumbrance balances will be cancelled by this time by HRS staff. | HRS will run the process to close out the encumbrance balances on June 19th. Journals will not be created and subsequently interfaced for these transactions until Monday, June 21st. This is due to the 6M payroll journals not being interfaced until Friday evening June 18th. Encumbrance calculations will run the final time on Thursday, June 17th, prior to the 6M Post confirm processing. | Salary encumbrances will not be posted for the remainder of FY21. | Nou Vang and HRS
June 23-30 | BUs must not process any check cancels, voids, or stop payments during this period unless there is certainty that there are sufficient payment dollars to cover the negative dollar effect of those transactions. | Encumbrance calculations will run the final time on Thursday June 17th prior to the 6M Post confirm processing. | Failure to comply with this rule may result in PY journals that have a negative balance. We cannot interface negative balance data to DOA. | Beth Vereb/Denise McDonald - communicate to Controllers and Bursars
June 24 | The June B Biweekly payroll is processed. | Health and Life fringe cost must be charged to FY22 Salary and all other fringe expense is charged to FY21 | Will be posted with 6-24 date to Period 12 | HRS
June 25 | The Pro-Card billing period that ends today will be the last one charged to FY2021 | Payment can be processed on June 28-29th (FY21). Expense distribution journal will be posted in period 12 (FY21) | On June 28th, you will get the statement indicating the total amount due. Note: The only time the upload process will change the date to July 1 is when the cycle end dates are 6-26, 27, 28, 29 or 30. | Andy Struebel/Ginger
June 30 | JET Accounting dates change to July 1 at 4pm. For UWMSN it will remain the 13th period until 4pm on July 8. All other institutions the date will remain July 1 until the night of the 15th. |  |  | Lea Erickson
June 30 | Business Units run final Pay Cycle Manager process that will create FY21 'PY' journals. Pay Cycles (as many as desired) can be run up until 3:30 p.m. PY journal posting is performed after 4:00 p.m. |  | BUs must reconcile their Accounts Payable balance to unpaid AP vouchers. BUs that have Accounts Payable balances at end of the fiscal year must be able to track and verify that offsetting Accounts Payable transactions charged to the new fiscal year (in PY journals) do accurately bring the old fiscal year balances to zero. | Beth Vereb/Denise McDonald
June 30 | Entry of June deposits against A/R is complete |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
June 30 | Pre-Close reconciliation of all balance sheets Accounts is completed. | GM - A/R and UAR | Note: this item only applies to business units using the Grants modules (MSN, MIL,SYS) | Kirk Anderson
June 30 | UWSA staff will open period 13 for all BU's except Madison. Madison staff will do the same for their BU. |  |  | Julia Lengyel, Lea Erickson
June 30 | All prior year purchase order encumbrance balances must be cleaned up by this date |  |  | Denise McDonald
July 1 | This is the SFS accounting period calendar date that represents the 13th month. | All BUs must make certain that journals for the 13th period are assigned a journal date of July 1.
July 1 | No pay cycle or expense processing for either fiscal year may be performed on this date. |  |  | Beth Vereb/Denise McDonald
July 1 | You must not cancel, void, or put a stop on any payments on this day!!! |  |  | Beth Vereb/Denise McDonald
July 1 | Update AP open periods for the next fiscal year |  |  | Beth Vereb/Denise McDonald
July 1 or prior to | Query the COMBO_RULE_TBL record and identify any combo edit rules that ended, or will end, PRIOR to or on 07/01 current FY and adjust end date if necessary. |  |  | Jacque Milski/SFS Staff
July 1 to 13 | BUs work on year-end checklist. Checklist should be certified by July 13
July 1 | PO Rollover from FY21 to FY22 is started for all business units. |  |  | Denise McDonald
July 2 | The SFS ledgers are opened for posting of FY22 journals and all other normal daily operations. |  |  | Julia Lengyel
July 2 | Deadline to complete PO rollover and for Controllers to sign off on certification totals |  |  | Denise McDonald
July 2 | Final reconciliation of Accounts Payable to Project Costing is completed. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
July 2 | FY22 salary encumbrance initialization process will be started on this date by HRS staff. |  |  | Nou Vang and HRS
July 5 | Holiday Observed
July 6 | BI Complete processing all invoices in PeopleSoft. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
July 6 | F&A and Fringe Allocations must be current. | All Errors Resolved | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
July 6 | Complete Cash Application of FY21 payments | Determine cash application process after 7/16 (entered into the GL via manual journal entry for the A/R, Cash and Unapplied Cash accounts?) | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
July 7 | The June accounting period in SFS is closed (early am) | BUs must have all final journals for June posted before this date |  | Julia Lengyel
July 8 | This is the last day that FY21 Direct Retros can be processed through HRS (period 13). |  |  | HRS
July 9 to 14 | UWMSN Restricts use of JET tool by campus users |  |  | Lea Erickson
July 8 | The July A Biweekly payroll is processed. | First full payroll to be entirely in FY22
July 13 | Year-End Checklist is due for UWSA review
July 13 - 14 | UWSA review BUs' checklists | Institutions will be contacted for coding corrections as needed. |  | Cora Beach
July 13 - 15 | UWSA staff release FY22 pre-paid fringe data to be sent to DOA | UWSA staff will initiate this release by checking the appropriate boxes in the Summer Session and Prepaid Fringe Release Control panel of SFS Salary Maintenance. |  | Nou Vang
July 13 - 15 | UWSA staff release FY21 Summer Session salary and fringe data to be sent to DOA. | UWSA staff will initiate this release by checking the appropriate boxes in one of the Salary Maintenance panels of SFS. |  | Nou Vang
July 15 | Review of Year-End Checklist is completed |  |  | Cora Beach
July 15 | All Institutions except Madison - Last day to process IUJ journals in JET. Last day to process journals using Cost Transfer Tool. The fiscal year will change at 4 pm.
July 15 | UWMSN – First Day for FY22 for JET and Cost Transfer Tool |  |  | Lea Erickson
July 15 | All direct retros must be posted to SFS by this date. |  |  | HRS
July 15 | Final day for SFS BUs to post FY21 data in SFS (period 13). Journals entered in prior days must be posted. Any journals entered today must be posted during the day. All journals must be posted by 3:30 pm. Period 13 is closed in SFS at 4:00 pm. UWSA staff will verify that all FY21 journals are posted before closing the period. | All FY21 Fund 990 revenue distributions should be complete by this date. Fund 990 Cash Balance (account 6100) must net to zero. All Fund 998, Department PAYCLR balances must be at zero. All Fund 128 PRDFLT and PRSUSP must be zero. All Fund account 1000 must be zero. All Payroll Interface "default coding" balances must be at zero. Please see Fiscal Year Closing Process Checklist at: https://www.wisconsin.edu/financial-administration/download/fiscal_year_end/Year-End-Checklist-2020-21.pdf Checklist must be submitted to the UW System Controller by July 13 and reviewed by July 15.
July 15 | The July Reg Unclassified payroll is processed | All salary and fringe expense is charged to FY22.
July 16 | BUs begin working on identifying any period 998 adjustments they will need to post to SFS. BUs should verify that end of year cash balances are properly accounted for in SFS. | Dollar amounts can be shifted between Program, DeptID, and Project codes within the same fund and major line. Transfers that cross state appropriations (Block grants) and/or account are not allowed. | Period 998 adjustments can be loaded to SFS by the BU, but must get UW System Controller approval before the journals can be posted. Period 998 adjustments must be completed by Aug. 15
July 16 through July 31 | UWSA staff begins final reconciliation with DOA. Final adjustments that affect BUs are identified and processed. | Final adjustment journals will be posted directly in SFS to period 13.
July 19 | GL Run final fiscal year journal generation for all modules |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS) | Kirk Anderson
July 19 | GL Enter manual post-close journal entries to update balance of Balance Sheet Accounts. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL,SYS) | Kirk Anderson
July 20 | MSN and MIL BU's must notify UWSA of their end of June fringe "pool" balances for Funds 133, 144, 233 and 161 by this date. | UWSA staff will use that data to make the transfer of fringe balances to the Systemwide fringe pool accounts | Balances for the comprehensive institutions remain at the institution | Connie Christianson
July 22 | UWSA staff begin preparations for moving the gift/grant/trust fringe "pool" DeptID balances out of the BU accounts and into the UWSYS accounts. Amounts shifted are based on end of June balances. | UWSA staff will make all of the needed journal entries in SFS to transfer the balances. |  | Connie Christianson
August 1 through August 15 | UWSA staff clear 131 cash balances from BU accounts via period 998 adjustments
| Cash account balances in all GPR funds and SEG annual funds are zeroed via an SQR program run at UWSA with the exception of cash balance to cover any accruals. | All GPR and SEG Annual fund/org balances for Cash (account 6100) should be at zero at the start of the new year. Verify by looking at data in period zero of the new year. | Funds involved are: 100, 101, 102, 103, 104, 106, 109, 110, 112, 116, 117, 118, 119, 126, 163, 169, 171, 172, 174, 188, 191, 402, 403, 406, and 601
UWSA staff create period 998 journals to move 997 and 980 fringe clearing balances to their proper carryover DeptID
Staff at BUs work on getting carryover encumbrance budgets from FY21 loaded to FY22 in SFS
| Staff at BUs work on getting gift/grant/trust budgets loaded to FY22 in SFS | There should be no budget data loaded for accounts that are totally closed out.
| All "first pass" period 998 journals for FY21 are posted for all BU's. The BUs perform journal uploads to get the period 998 adjustments into SFS. UWSA staff review/approve the data and post the journals. | Account balances get moved to the funding that is appropriate/desired for carryover to the new fiscal year.
The fiscal year "close" process is run for all BUs (done by UWSA staff) so that the effect of the period 998 adjustments can be reviewed in period zero of FY22 and in WISER.
Additional period 998 adjustments are created and posted as needed
The fiscal year close process is re-run for BU's as needed
All FY21 closing activity is expected to be completed by August 15
August 2 | Run Year-End Close process for ADB calculation for DOA | Must be done first thing in the morning the first business day of August. The close must be reversed the same day. |  | Cora Beach
August 6 | Last day UW can post FY21 data in STAR |  |  | Julia Lengyel
August 10 | UW's Forms 78 Certified |  |  | Ginger Hintz
August 30 or earlier if possible | Transfer Cash From UWSYS 131 to AJE_LEDGER to cover GPO Shifts.
October 31 | Close WISER - FY21 | WISER team to confirm with UWSA staff before closing. |  | Renee Copes Scott Larson
Note on A75: Julia Lengyel: Billing period end date - 25th Statement received next business day - 28th Payment can be processed next two bsuiness days - 28-29 SBF file is received a week from the day the statement is received - July 6th
Note on E65: Julia Lengyel: Update when DOA posts closing schedule for FY21
VERY IMPORTANT
VERY IMPORTANT
First payroll Health/Life to New FY
VERY IMPORTANT
IMPORTANT
When processing IUJs in the 13th period remember to work with the other institutions involved
Option 1 (Preferred)
1) Process the payment on June 28-29th through a regular pay cycle with a cash payment made in FY2021. If unable to process the payment by June 30th - See Option 2.
2) Institutions with a seven day reallocation period will receive the SBF file on July 6th. The file must be uploaded on July 6th and posted with a date of 6/25 to Period 12. Note: The only time the upload process will change the date to July 1 is when the cycle end dates are 6-26, 27, 28, 29 or 30.
Option 2
1) If unable to process the payment by June 30th - use account 3100 (or your default account code) as usual in FY2022.
2) Process an Internal Transfer Journal (INT) in FY22 to clear account 3100 to account 7105. This will establish the balance sheet account that will carry over between years.
3) Process an Internal Transfer Journal (INT) in FY21 reversing the entry made in FY22. This will clear the 7105 and re-establish the expenditure on account 3100.
4) ) Institutions with a seven day reallocation period will receive the SBF file on July 6th. The file must be uploaded on July 6th and posted with a date of 6/25 to Period 12.
VERY IMPORTANT
VERY IMPORTANT

## 2022 Close Timeline
University of Wisconsin System SFS Accounting Manual
Category: General Ledger |  |  | Effective Date: Updated Annually
Task or Process: FY2022 Year-End Closing Timeline |  |  | Revision Date: April 2022
Contact Information: Name - Ginger Hintz |  | Email - ghintz@uwsa.edu | Phone - 608-262-6010
The schedule below provides information about dates, processes, etc. that will occur during the close of fiscal year 2022.
Date | Event | Fiscal Impact | Issues | Person/Area Responsible
SFS performance may be slower than usual over FYE, due to month-end and year-end processing on top of normal daily processing.
Jan 4 | Open FY23 edits for all units | Add and check the edits in other environments, including SFTRAIN. |  | MSN in Production; SFS staff in other environments
January 31 | Send a reminder to BUs regarding dual-year edits in the STD_BUDGET ledger | BUs copy current year ORG_EDIT tree and name it ORG_EDFY with a 7/2/2023 effective date in order for dual edits in the STD_BUDGET ledger to work and for their budget office to load budgets for FY23. Both trees need to be maintained for the remainder of the fiscal year. |  | Jessica Laeseke
Feb 1 | Nightly ETL of SFS data to WISER begins for FY2023 | Set up FY23 in WISER |  | SFS Staff
April 1 | The PO module for FY23 is opened in SFS. Only Grant/Awards NEW YEAR Purchase Orders can be created in SFS; all other orders created in ShopUW+. CREATED RECORDS WILL NOT INTERFACE INTO SFS UNTIL 7-2-2022 |  |  | Lisa Eyers - communicate to campus SFS Staff - open period
May 2 | The Standard Budget Ledger for period 1 of FY23 is opened to allow BUs to begin posting budget journals. | UWSA opens Ledger for all BUs |  | Jessica Laeseke
May 3 | BUs should begin closely monitoring encumbrance balances for all funds in SFS. You need to ensure that the SFS balances are accurate by the time we get to the mid-July cutoff. | The SFS balances at end of FY22 will be reported to DOA by UWSA staff. Those balances also dictate the carryover encumbrance balances that may be established in SFS for FY23. Limitations: Any PO that has a balance less than $50 cannot be carried over. All FY22 blanket orders must be cancelled before the mid-July closing. | Due to how DOA STAR handles Allotments for Prior Year encumbrances, all purchase orders will be reviewed at the account level.
May 3 | UWSA, DoIT and HRS staff will ensure that all SFS fiscal year based control tables and calendars have been established for FY23 by this date. |  |  | Jacque Milski/Nou Vang
May 12 | May A Biweekly is processed (post confirm on 5/13/22) | Salary and all fringe expense is charged to FY22 |  | HRS
May 13 | Need to identify all projects that will expire at the end of June 30. Also, need list of all internal projects. | This will aid the process of POs for year end | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | need 7-1 end date Kirk Anderson
May 26 | May B Biweekly payroll is processed (post confirm on 5/27/22) | Salary and all fringe expense is charged to FY22 |  | HRS
May 31 | Final day for processing FY22 orders | FINAL DAY FOR PROCESSING CURRENT YEAR PURCHASE ORDERS If you have an invoice, create a Cash with Order PO or complete a Direct Payment |  | Lisa Eyers
June 6 | The May accounting period is closed in SFS first thing in the morning | SFS BUs need to have all May journals posted |  | Julia Lengyel
June 9 | The June A Biweekly payroll is processed (post confirm on 6/10/22) | Health and Life fringe cost must be charged to FY23 Salary and all other fringe expense is charged to FY22 |  | HRS
June 15 | TER Deadline for TERs Audited Centrally | Allow adequate time for the TER audit process which may require resubmission and reapproval.
June 17 | Cutoff date for FY22 budget transfers that need UWSA approval | To guarantee the processing of any remaining FY22 budget transfers before the end of June, please submit your budget transfer requests by this date. Transfers received after this date will be processed as time allows. |  | Jessica Laeseke
June 18 | Update UW_DOA Period 13 table for AP, CR and GL transactions | Navigation - SFS Extensions >DOA STAR Interface > Use > DOA Period 13 Definitions |  | Julia Lengyel
June 23 | The June B Biweekly payroll is processed (post confirm on 6/24/22) | Health and Life fringe cost must be charged to FY23 Salary and all other fringe expense is charged to FY22 | Will be posted with 6-23 date to Period 12 | HRS
June 23-30 | BUs must not process any check cancels, voids, or stop payments during this period unless there is certainty that there are sufficient payment dollars to cover the negative dollar effect of those transactions. | Encumbrance calculations will run the final time on Thursday June 17th prior to the 6M Post confirm processing. | Failure to comply with this rule may result in PY journals that have a negative balance. We cannot interface negative balance data to DOA. | Beth Vereb/Lisa Eyers - communicate to Controllers and Bursars
June 24 | The Pro-Card billing period that ends today will be the last one charged to FY2022 | Payment can be processed on June 27-29th (FY22). Expense distribution journal will be posted in period 12 (FY22) | On June 27th, you will get the statement indicating the total amount due. Note: The only time the upload process will change the date to July 1 is when the cycle end dates are 6-26, 27, 28, 29 or 30. | Andy Struebel/Ginger
June 28 | All FY22 salary encumbrance balances will be cancelled by this time by HRS staff. | HRS will run the process to close out the encumbrance balances on June 20th. Journals will not be created and subsequently interfaced for these transactions until June 28th. This is due to the 6B payroll journals not being interfaced until 6/27/2022. Encumbrance calculations will run the final time on the 23rd, prior to the 6B Post confirm processing. | Salary encumbrances will not be posted for the remainder of FY22. | Nou Vang and HRS
June 30 | JET Accounting dates change to July 1 at 4pm. For UWMSN it will remain the 13th period until 4pm on July 8. All other institutions the date will remain July 1 until the night of the 15th. |  |  | Lea Erickson
June 30 | Business Units run final Pay Cycle Manager process that will create FY22 'PY' journals. Pay Cycles (as many as desired) can be run up until 3:30 p.m. PY journal posting is performed after 4:00 p.m. |  | BUs must reconcile their Accounts Payable balance to unpaid AP vouchers. BUs that have Accounts Payable balances at end of the fiscal year must be able to track and verify that offsetting Accounts Payable transactions charged to the new fiscal year (in PY journals) do accurately bring the old fiscal year balances to zero. | Beth Vereb/Lisa Eyers
June 30 | Entry of June deposits against A/R is complete |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Kirk Anderson
June 30 | Pre-Close reconciliation of all balance sheets Accounts is completed. | GM - A/R and UAR | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Kirk Anderson
June 30 | UWSA staff will open period 13 for all BU's except Madison. Madison staff will do the same for their BU. |  |  | Julia Lengyel, Lea Erickson
June 30 | All prior year purchase order encumbrance balances must be cleaned up by this date |  |  | Lisa Eyers
July 1 or prior to | Query the COMBO_RULE_TBL record and identify any combo edit rules that ended, or will end, PRIOR to or on 07/01 current FY and adjust end date if necessary. |  |  | Jacque Milski/SFS Staff
July 1 | This is the SFS accounting period calendar date that represents the 13th month. | All BUs must make certain that journals for the 13th period are assigned a journal date of July 1.
July 1 | No pay cycle or expense processing for either fiscal year may be performed on this date. |  |  | Beth Vereb/Lisa Eyers
July 1 | You must not cancel, void, or put a stop on any payments on this day!!! |  |  | Beth Vereb/Lisa Eyers
July 1 | Update AP open periods for the next fiscal year |  |  | Beth Vereb/Lisa Eyers
July 1 | PO Rollover from FY22 to FY23 is started for all business units. |  |  | Lisa Eyers
July 1 | FY23 salary encumbrance initialization process will be started on this date by HRS staff. |  |  | Nou Vang and HRS
July 1 to 13 | BUs work on year-end checklist. Checklist should be certified by July 13
July 2 | The SFS ledgers are opened for posting of FY23 journals and all other normal daily operations. |  |  | Julia Lengyel
July 4 | Holiday Observed
July 5 | Deadline to complete PO rollover and for Controllers to sign off on certification totals |  |  | Lisa Eyers
July 5 | Final reconciliation of Accounts Payable to Project Costing is completed. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Kirk Anderson
July 6 | BI Complete processing all invoices in PeopleSoft. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Kirk Anderson
July 6 | F&A and Fringe Allocations must be current. | All Errors Resolved | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Kirk Anderson
July 6 | Complete Cash Application of FY22 payments | Determine cash application process after 7/16 (entered into the GL via manual journal entry for the A/R, Cash and Unapplied Cash accounts?) | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Kirk Anderson
July 7 | The June accounting period in SFS is closed (early am) | BUs must have all final journals for June posted before this date |  | Julia Lengyel
July 7 | The July A Biweekly payroll is processed. | First full payroll to be entirely in FY23
July 8 to 14 | UWMSN Restricts use of JET tool by campus users |  |  | Lea Erickson
July 11 | This is the last day that FY22 Direct Retros can be processed through HRS (period 13). | This is the last date HRS has the page unlocked for campus users to enter direct retros. |  | HRS
July 11 - 15 | UWSA staff release FY23 pre-paid fringe data to be sent to DOA | UWSA staff will initiate this release by checking the appropriate boxes in the Summer Session and Prepaid Fringe Release Control panel of SFS Salary Maintenance. |  | Nou Vang
July 11 - 15 | UWSA staff release FY22 Summer Session salary and fringe data to be sent to DOA. | UWSA staff will initiate this release by checking the appropriate boxes in one of the Salary Maintenance panels of SFS. |  | Nou Vang
July 13 | Year-End Checklist is due for UWSA review
July 13 - 14 | UWSA review BUs' checklists | Institutions will be contacted for coding corrections as needed. |  | Cora Beach
July 14 | All direct retros must be posted to SFS by this date. | This deadline applies to HRS, not campuses, to clean up any issues with processing and to post all journals by period 13 close. |  | HRS
July 15 | Review of Year-End Checklist is completed |  |  | Cora Beach
July 15 | All Institutions except Madison - Last day to process IUJ journals in JET. Last day to process journals using Cost Transfer Tool. The fiscal year will change at 4 pm.
July 15 | UWMSN – First Day for FY23 for JET and Cost Transfer Tool |  |  | Lea Erickson
July 15 | Final day for SFS BUs to post FY22 data in SFS (period 13). Journals entered in prior days must be posted. Any journals entered today must be posted during the day. All journals must be posted by 3:30 pm. Period 13 is closed in SFS at 4:00 pm. UWSA staff will verify that all FY22 journals are posted before closing the period. | All FY22 Fund 990 revenue distributions should be complete by this date. Fund 990 Cash Balance (account 6100) must net to zero. All Fund 998, Department PAYCLR balances must be at zero. All Fund 128 PRDFLT and PRSUSP must be zero. All Fund account 1000 must be zero. All Payroll Interface "default coding" balances must be at zero. Please see Fiscal Year Closing Process Checklist at: https://www.wisconsin.edu/financial-administration/accounting-and-budget-control/ Checklist must be submitted to the UW System Controller by July 13 and reviewed by July 15.
July 18 | BUs begin working on identifying any period 998 adjustments they will need to post to SFS. BUs should verify that end of year cash balances are properly accounted for in SFS. | Dollar amounts can be shifted between Program, DeptID, and Project codes within the same fund and major line. Transfers that cross state appropriations (Block grants) and/or account are not allowed. | Period 998 adjustments can be loaded to SFS by the BU, but must get UW System Controller approval before the journals can be posted. Period 998 adjustments must be completed by Aug. 15
July 18 through July 29 | UWSA staff begins final reconciliation with DOA. Final adjustments that affect BUs are identified and processed. | Final adjustment journals will be posted directly in SFS to period 13. |  | Julia Lengyel
July 18 | GL Run final fiscal year journal generation for all modules |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Kirk Anderson
July 18 | GL Enter manual post-close journal entries to update balance of Balance Sheet Accounts. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL,SYS and STP) | Kirk Anderson
July 18 | MSN and MIL BU's must notify UWSA of their end of June fringe "pool" balances for Funds 133, 144, 233 and 161 by this date. | UWSA staff will use that data to make the transfer of fringe balances to the Systemwide fringe pool accounts | Balances for the comprehensive institutions remain at the institution | Connie Christianson
July 20 | UWSA staff begin preparations for moving the gift/grant/trust fringe "pool" DeptID balances out of the BU accounts and into the UWSYS accounts. Amounts shifted are based on end of June balances. | UWSA staff will make all of the needed journal entries in SFS to transfer the balances. |  | Connie Christianson
August 1 through August 15 | UWSA staff clear 131 cash balances from BU accounts via period 998 adjustments
| Cash account balances in all GPR funds and SEG annual funds are zeroed via an SQR program run at UWSA with the exception of cash balance to cover any accruals. | All GPR and SEG Annual fund/org balances for Cash (account 6100) should be at zero at the start of the new year. Verify by looking at data in period zero of the new year. | Funds involved are: 100, 101, 102, 103, 104, 106, 109, 110, 112, 113, 116, 117, 118, 119, 126, 163, 169, 171, 172, 174, 188, 191, 402, 403, 406, and 601
UWSA staff create period 998 journals to move 997 and 980 fringe clearing balances to their proper carryover DeptID
Staff at BUs work on getting carryover encumbrance budgets from FY22 loaded to FY23 in SFS
| Staff at BUs work on getting Fund 113 carryover budgets from FY22 loaded to FY23 in SFS | Use ADJUSTED scenario code
| Staff at BUs work on getting gift/grant/trust budgets loaded to FY23 in SFS | There should be no budget data loaded for accounts that are totally closed out.
| All "first pass" period 998 journals for FY22 are posted for all BU's. The BUs perform journal uploads to get the period 998 adjustments into SFS. UWSA staff review/approve the data and post the journals. | Account balances get moved to the funding that is appropriate/desired for carryover to the new fiscal year.
The fiscal year "close" process is run for all BUs (done by UWSA staff) so that the effect of the period 998 adjustments can be reviewed in period zero of FY23 and in WISER.
Additional period 998 adjustments are created and posted as needed
The fiscal year close process is re-run for BU's as needed
All FY22 closing activity is expected to be completed by August 15
August 1 | Run Year-End Close process for ADB calculation for DOA | Must be done first thing in the morning the first business day of August. The close must be reversed the same day. |  | Cora Beach
August 5 | Last day UW can post FY22 data in STAR |  |  | Julia Lengyel
August 9 | UW's Forms 78 Certified |  |  | Ginger Hintz
August 30 or earlier if possible | Transfer Cash From UWSYS 131 to AJE_LEDGER to cover GPO Shifts.
October 31 | Close WISER - FY22 | WISER team to confirm with UWSA staff before closing. |  | Renee Copes Scott Larson
Note on A58: Julia Lengyel: Billing period end date - 24th Statement received next business day - 27th Payment can be processed next two bsuiness days - 27-28 SBF file is received a week from the day the statement is received - July 5th
Note on E51: Julia Lengyel: Update when DOA posts closing schedule for FY22
VERY IMPORTANT
VERY IMPORTANT
First payroll Health/Life to New FY
VERY IMPORTANT
IMPORTANT
When processing IUJs in the 13th period remember to work with the other institutions involved
ProCard Interface Load: Option 1 (Preferred)
1) Process the payment on June 27-29th through a regular pay cycle with a cash payment made in FY2022. If unable to process the payment by June 30th - See Option 2.
2) Institutions with a seven-day reallocation period will receive the SBF file on July 2nd. The file must be uploaded by July 6th and posted with a date of 6/24 to Period 12. Note: The only time the upload process will change the date to July 1 is when the cycle end dates are 6-26, 27, 28, 29 or 30.
Option 2
1) If unable to process the payment by June 30th - use account 3100 (or your default account code) as usual in FY2023.
2) Process an Internal Transfer Journal (INT) in FY23 to clear account 3100 to account 7105. This will establish the balance sheet account that will carry over between years.
3) Process an Internal Transfer Journal (INT) in FY22 reversing the entry made in FY23. This will clear the 7105 and re-establish the expenditure on account 3100.
4) ) Institutions with a seven-day reallocation period will receive the SBF file on July 2nd. The file must be uploaded by July 6th and posted with a date of 6/24 to Period 12.
VERY IMPORTANT
VERY IMPORTANT
SFS P-Card Module:
Friday, June 24th - The final daily file load of transactions posted on June 24th will deliver on Saturday June 25th. The SFS team will upload the June 24th daily file on Saturday June 25th. Transactions posted to credit cards through June 24 will be paid in FY22; All p-card transactions must be reconciled and approved in SFS by June 29th. Any transactions not reconciled by June 29th will be manually forced to system close. It is highly recommended that reconciling be completed by the June 29th due date since funding cannot be changed once close. Cost transfers would then have to be done to move the funding. Caution should be given to the timing of purchases during this timeframe because purchases posted to accounts on June 25th or after will be posted to FY23. If in doubt, please ask the vendor when the charge will be posted to purchasing card

## 2023 Close Timeline
University of Wisconsin System SFS Accounting Manual
Category: General Ledger |  |  | Effective Date: Updated Annually
Task or Process: FY2023 Year-End Closing Timeline |  |  | Revision Date: June 29 2023
Contact Information: Name - Julia Lengyel |  | Email - jlengyel@uwsa.edu | Phone - 608-262-5850
The schedule below provides information about dates, processes, etc. that will occur during the close of fiscal year 2023.
Date | Event | Fiscal Impact | Issues | Person/Area Responsible
SFS performance may be slower than usual over FYE due to month-end and year-end processing on top of normal daily processing.
Jan 3 | Open FY24 edits for all units | Add and check the edits in other environments, including SFTRAIN. |  | MSN in Production; SFS staff in other environments
January 31 | Send a reminder to BUs regarding dual-year edits in the STD_BUDGET ledger | BUs copy current year ORG_EDIT tree and name it ORG_EDFY with a 7/2/2024 effective date in order for dual edits in the STD_BUDGET ledger to work and for their budget office to load budgets for FY24. Both trees need to be maintained for the remainder of the fiscal year. |  | Jessica Laeseke
Feb 1 | Nightly ETL of SFS data to WISER begins for FY2024 | Set up FY24 in WISER |  | Renee Copes
April 3 | The PO module for FY24 is opened in SFS. Only Grant/Awards NEW YEAR Purchase Orders can be created in SFS; all other orders created in ShopUW+. CREATED RECORDS WILL NOT INTERFACE INTO SFS UNTIL 7-2-2023 |  |  | Sarah Peck - communicate to campus SFS Staff - open period
May 1 | The Standard Budget Ledger for period 1 of FY24 is opened to allow BUs to begin posting budget journals. | UWSA opens Ledger for all BUs |  | New Budget Accountant
May 1 | BUs should begin closely monitoring encumbrance balances for all funds in SFS. You need to ensure that the SFS balances are accurate by the time we get to the mid-July cutoff. | The SFS balances at end of FY23 will be reported to DOA by UWSA staff. Those balances also dictate the carryover encumbrance balances that may be established in SFS for FY24. Limitations: Any PO that has a balance less than $50 cannot be carried over. All FY23 blanket orders must be cancelled before the mid-July closing. | Due to how DOA STAR handles Allotments for Prior Year encumbrances, all purchase orders will be reviewed at the account level.
May 1 | UWSA, DoIT and HRS staff will ensure that all SFS fiscal year based control tables and calendars have been established for FY24 by this date. |  |  | Linda Diring
May 11 | May A Biweekly is processed (post confirm on 5/12/23) | Salary and all fringe expense is charged to FY23 |  | HRS
May 15 | Need to identify all projects that will expire at the end of June 30. Also, need list of all internal projects. | This will aid the process of POs for year end. Need 7-1 end date. | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Grants Campus
May 25 | May B Biweekly payroll is processed (post confirm on 5/26/23) | Salary and all fringe expense is charged to FY23 |  | HRS
May 26 | TER Deadline for TERs Audited Centrally | Allow adequate time for the TER audit process which may require resubmission and reapproval.
May 31 | Final day for processing FY23 orders | FINAL DAY FOR PROCESSING CURRENT YEAR PURCHASE ORDERS If you have an invoice, create a Cash with Order PO or complete a Direct Payment |  | Sarah Peck
June 6 | The May accounting period is closed in SFS first thing in the morning | SFS BUs need to have all May journals posted |  | Julia Lengyel
June 8 | The June A Biweekly payroll is processed (post confirm on 6/09/23) | Health and Life fringe cost must be charged to FY24 Summer session Salary and allowable Fringes are charged to FY24 Salary and all other fringe expense is charged to FY23 |  | HRS
June 16 | Cutoff date for FY23 budget transfers that need UWSA approval | To guarantee the processing of any remaining FY23 budget transfers before the end of June, please submit your budget transfer requests by this date. Transfers received after this date will be processed as time allows. |  | New Budget Accountant
June 19 | Update UW_DOA Period 13 table for AP, CR and GL transactions | Navigation - SFS Extensions >DOA STAR Interface > Use > DOA Period 13 Definitions |  | Julia Lengyel
June 22 | The June B Biweekly payroll is processed (post confirm on 6/23/23) | Health and Life fringe cost must be charged to FY24 Summer session Salary and allowable Fringes are charged to FY24 Salary and all other fringe expense is charged to FY23 | Will be posted with 6-23 date to Period 12 | HRS
June 23-30 | BUs must not process any check cancels, voids, or stop payments during this period unless there is certainty that there are sufficient payment dollars to cover the negative dollar effect of those transactions. | Encumbrance calculations will run the final time on Friday June 16th prior to the 6M Post confirm processing. | Failure to comply with this rule may result in PY journals that have a negative balance. We cannot interface negative balance data to DOA. | Vicki Kissack - communicate to Controllers and Bursars
June 23 | The Pro-Card billing period that ends today will be the last one charged to FY2023 | Payment can be processed on June 26-29th (FY23). Expense distribution journal will be posted in period 12 (FY23) | On June 26th, you will get the statement indicating the total amount due. Note: The only time the upload process will change the date to July 1 is when the cycle end dates are 6-26, 27, 28, 29 or 30. | Jessica Laeseke/Ginger
June 27 | All FY23 salary encumbrance balances will be cancelled by this time by HRS staff. | HRS will run the process to close out the encumbrance balances on June 24th. Journals will not be created and subsequently interfaced for these transactions until June 27th. Encumbrance calculations will run the final time on the 23rd, same day as the 6B final calc and confirm. | Salary encumbrances will not be posted for the remainder of FY23. | Renee Copes and HRS
June 30 | Business Units run final Pay Cycle Manager process that will create FY23 'PY' journals. Pay Cycles (as many as desired) can be run up until 3:30 p.m. PY journal posting is performed after 4:00 p.m. |  | BUs must reconcile their Accounts Payable balance to unpaid AP vouchers. BUs that have Accounts Payable balances at end of the fiscal year must be able to track and verify that offsetting Accounts Payable transactions charged to the new fiscal year (in PY journals) do accurately bring the old fiscal year balances to zero. | Vicki Kissack
June 30 | JET Accounting dates change to July 1 at 4pm. For UWMSN it will remain the 13th period until 4pm on July 7. All other institutions the date will remain July 1 until the night of the 14th. |  |  | Lea Erickson
June 30 | Entry of June deposits against A/R is complete |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Grants Campus
June 30 | Pre-Close reconciliation of all balance sheets Accounts is completed. | GM - A/R and UAR | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Grants Campus
June 30 | UWSA staff will open period 13 for all BU's except Madison. Madison staff will do the same for their BU. |  |  | Julia Lengyel, Lea Erickson
June 30 | All prior year purchase order encumbrance balances must be cleaned up by this date |  |  | Sarah Peck
June 30 or prior to | Update AP open periods for the next fiscal year |  |  | Vicki Kissack
July 1 | No pay cycle or expense processing for either fiscal year may be performed on this date. |  |  | Vicki Kissack
July 1 | You must not cancel, void, or put a stop on any payments on this day!!! |  |  | Vicki Kissack
July 1 or prior to | Query the COMBO_RULE_TBL record and identify any combo edit rules that ended, or will end, PRIOR to or on 07/01 current FY and adjust end date if necessary. |  |  | Linda Diring
July 1 | This is the SFS accounting period calendar date that represents the 13th month. | All BUs must make certain that journals for the 13th period are assigned a journal date of July 1.
July 2 | The SFS ledgers are opened for posting of FY24 journals and all other normal daily operations. |  |  | Julia Lengyel
July 3 | PO Rollover from FY23 to FY24 is started for all business units. |  |  | Sarah Peck
July 3 | FY24 salary encumbrance initialization process will be started on this date by HRS staff. |  |  | Renee Copes and HRS
July 3 to 13 | BUs work on year-end checklist. Checklist should be certified by July 13
July 4 | Holiday Observed
July 6 | Deadline to complete PO rollover and for Controllers to sign off on certification totals |  |  | Sarah Peck
July 5 | Final reconciliation of Accounts Payable to Project Costing is completed. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Grants Campus
July 6 | BI Complete processing all invoices in PeopleSoft. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Grants Campus
July 6 | F&A and Fringe Allocations must be current. | All Errors Resolved | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Grants Campus
July 6 | Complete Cash Application of FY23 payments | Determine cash application process after 7/17 (entered into the GL via manual journal entry for the A/R, Cash and Unapplied Cash accounts?) | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Grants Campus
July 6 | The July A Biweekly payroll is processed. | First full payroll to be entirely in FY24
July 7 | The June accounting period in SFS is closed (early am) | BUs must have all final journals for June posted before this date |  | Julia Lengyel
July 7 to 13 | UWMSN Restricts use of JET tool by campus users |  |  | Lea Erickson
July 11 | This is the last day that FY23 Direct Retros can be processed through HRS (period 13). | This is the last date HRS has the page unlocked for campus users to enter direct retros. |  | HRS
July 11 - 14 | UWSA staff release FY24 pre-paid fringe data to be sent to DOA | UWSA staff will initiate this release by checking the appropriate boxes in the Summer Session and Prepaid Fringe Release Control panel of SFS Salary Maintenance. |  | Renee Copes
July 11 - 14 | UWSA staff release FY23 Summer Session salary and fringe data to be sent to DOA. | UWSA staff will initiate this release by checking the appropriate boxes in one of the Salary Maintenance panels of SFS. |  | Renee Copes
July 14 | UWMSN – First Day for FY24 for JET and Cost Transfer Tool |  |  | Lea Erickson
July 17 | Year-End Checklist is due for UWSA review
July 17-18 | UWSA review BUs' checklists | Institutions will be contacted for coding corrections as needed. |  | Cora Beach
July 17 | All direct retros must be posted to SFS by this date. | This deadline applies to HRS, not campuses, to clean up any issues with processing and to post all journals by period 13 close. |  | HRS
July 17-18 | Review of Year-End Checklist is completed |  |  | Cora Beach
July 17 | All Institutions except Madison - Last day to process IUJ journals in JET. Last day to process journals using Cost Transfer Tool. The fiscal year will change at 4 pm.
July 17 | Final day for SFS BUs to post FY23 data in SFS (period 13). Journals entered in prior days must be posted. Any journals entered today must be posted during the day. All journals must be posted by 3:30 pm. Period 13 is closed in SFS at 4:00 pm. UWSA staff will verify that all FY23 journals are posted before closing the period. | All FY23 Fund 990 revenue distributions should be complete by this date. Fund 990 Cash Balance (account 6100) must net to zero. All Fund 998, Department PAYCLR balances must be at zero. All Fund 128 PRDFLT and PRSUSP must be zero. All Fund account 1000 must be zero. All Payroll Interface "default coding" balances must be at zero. | See Fiscal Year Closing Process Checklist at: https://www.wisconsin.edu/financial-administration/accounting-and-budget-control/
July 18 | BUs begin working on identifying any period 998 adjustments they will need to post to SFS. BUs should verify that end of year cash balances are properly accounted for in SFS. | Dollar amounts can be shifted between Program, DeptID, and Project codes within the same fund and major line. Transfers that cross state appropriations (Block grants) and/or account are not allowed. | Period 998 adjustments can be loaded to SFS by the BU, but must get UW System Assistant Controller review and approval before the journals can be posted. Period 998 adjustments must be completed by Aug. 15
July 18 through July 28 | UWSA staff begins final reconciliation with DOA. Final adjustments that affect BUs are identified and processed. | Final adjustment journals will be posted directly in SFS to period 13. |  | Julia Lengyel
July 18 | GL - Run final fiscal year journal generation for all modules |  | Note: this item only applies to business units using the Grants modules (MSN, MIL, SYS and STP) | Grants Campus
July 18 | GL - Enter manual post-close journal entries to update balance of Balance Sheet Accounts. |  | Note: this item only applies to business units using the Grants modules (MSN, MIL,SYS and STP) | Grants Campus
August 1 through August 15 | UWSA staff clear 131 cash balances from BU accounts via period 998 adjustments
| Cash account balances in all GPR funds and SEG annual funds are zeroed via an SQR program run at UWSA with the exception of cash balance to cover any accruals. | All GPR and SEG Annual fund/org balances for Cash (account 6100) should be at zero at the start of the new year. Verify by looking at data in period zero of the new year. | Funds involved are: 100, 101, 102, 103, 104, 106, 109, 110, 112, 113, 116, 117, 118, 119, 126, 163, 169, 171, 172, 174, 188, 191, 402, 403, 406, and 601
UWSA staff create period 998 journals to move 997 and 980 fringe clearing balances to their proper carryover DeptID
Staff at BUs work on getting carryover encumbrance budgets from FY23 loaded to FY24 in SFS
| Staff at BUs work on getting Fund 113 carryover budgets from FY23 loaded to FY24 in SFS | Use CARRYOVER scenario code
| Staff at BUs work on getting gift/grant/trust budgets loaded to FY24 in SFS | There should be no budget data loaded for accounts that are totally closed out.
Staff at BUs review to ensure there are no balances in inactive depts/projects and that cash is in the appropriate program codes
| All "first pass" period 998 journals for FY23 are posted for all BU's. The BUs perform journal uploads to get the period 998 adjustments into SFS. UWSA staff review/approve the data and post the journals. | Account balances get moved to the funding that is appropriate/desired for carryover to the new fiscal year.
The fiscal year "close" process is run for all BUs (done by UWSA staff) so that the effect of the period 998 adjustments can be reviewed in period zero of FY24 and in WISER.
Additional period 998 adjustments are created and posted as needed
The fiscal year close process is re-run for BU's as needed
All FY23 closing activity is expected to be completed by August 15
August 1 | Run Year-End Close process for ADB calculation for DOA | Must be done first thing in the morning the first business day of August. The close must be reversed the same day. |  | Cora Beach
August 3 | Last day UW can post FY23 data in STAR |  |  | Julia Lengyel
August 8 | UW's Forms 78 Certified |  |  | Ginger Hintz
August 30 or earlier if possible | Transfer Cash From UWSYS 131 to AJE_LEDGER to cover GPO Shifts.
October 31 | Close WISER - FY23 | WISER team to confirm with UWSA staff before closing. |  | Renee Copes
Note on A52: Julia Lengyel: Billing period end date - 23rd Statement received next business day - 26th Payment can be processed next two bsuiness days - 26-27 SBF file is received a week from the day the statement is received - July 3rd
Note on E45: Julia Lengyel: Update when DOA posts closing schedule for FY23
VERY IMPORTANT
VERY IMPORTANT
First payroll Health/Life to New FY
VERY IMPORTANT
IMPORTANT
When processing IUJs in the 13th period remember to work with the other institutions involved
ProCard Interface Load: Option 1 (Preferred)
1) Process the payment on June 26-29th through a regular pay cycle with a cash payment made in FY2023. If unable to process the payment by June 30th - See Option 2.
2) Institutions with a seven-day reallocation period will receive the SBF file on July 3rd. The file must be uploaded by July 6th and posted with a date of 6/23 to Period 12. Note: The only time the upload process will change the date to July 1 is when the cycle end dates are 6-26, 27, 28, 29 or 30.
Option 2
1) If unable to process the payment by June 30th - use account 3100 (or your default account code) as usual in FY2024.
2) Process an Internal Transfer Journal (INT) in FY24 to clear account 3100 to account 7105. This will establish the balance sheet account that will carry over between years.
3) Process an Internal Transfer Journal (INT) in FY23 reversing the entry made in FY24. This will clear the 7105 and re-establish the expenditure on account 3100.
4) ) Institutions with a seven-day reallocation period will receive the SBF file on July 3rd. The file must be uploaded by July 6th and posted with a date of 6/23 to Period 12.
VERY IMPORTANT
VERY IMPORTANT
SFS P-Card Module:
Friday, June 23rd - The final daily file load of transactions posted on June 23rd will deliver on Sunday June 25th. The SFS team will upload the June 23rd daily file on Monday June 26th. Transactions posted to credit cards through June 23rd will be paid in FY23; All p-card transactions must be reconciled and approved in SFS by June 29th. Any transactions not reconciled by June 29th will be manually forced to system close. It is highly recommended that reconciling be completed by the June 29th due date since funding cannot be changed once close. Cost transfers would then have to be done to move the funding. Caution should be given to the timing of purchases during this timeframe because purchases posted to accounts on June 24th or after will be posted to FY24. If in doubt, please ask the vendor when the charge will be posted to purchasing card
VERY IMPORTANT
VERY IMPORTANT
VERY IMPORTANT
VERY IMPORTANT