## Full List
Line ID | Check | Deliverable | Responsible | Notes | Stage
1 | 0 | Business Case | Anyone | Includes ROM Variance of -50% to +50% | Conceptualizing
2 | 0 | Limited Stakeholder List | Portfolio Manager | A list of stakeholder groups and high-level needs of each. Will feed into the Communication Framework during Discovery. | Conceptualizing
3 | 0 | Role Definitions (Standard) | PMO | A pre-defined list of roles and responsibilities needed for every project with the people assigned to them. (E.g. Sponsor, PM, Techincal Lead, Executive Sponsor, Steering Committee) | Conceptualizing
4 | 0 | Project Prioritization | PMO | An official acknowledgement of the priority of a project in relation to others in the portfolio. | Conceptualizing
5 | 0 | Project Pressure | PM | Identify an initial pressure profile and include in PM's portfolio documentation. Based on the timeline for project implementation and perceived importance of the project. | Conceptualizing
6 | 0 | Task Tracker Setup | PMO Manager | Create Task Tracker for entire Project (Not based on different phases). | Initiating
7 | 0 | Security Analysis | PM | Review by Security personnel of process approach regarding physical and technological security. | Initiating
8 | 0 | Project Charter | PM | A statement of the scope, objectives, participants, timeline, etc. in a project. | Initiating
9 | 0 | Project Approach | PM | A high-level outline of current thinking on how the project will function. With the Task List, will help determine the project plan. | Initiating
10 | 0 | Budget Estimate ROM | PMO | Variance of -10% to +25% | Initiating
11 | 0 | Project Control Plan | PMO | Plan for approving changes to the project during its develompent and execution. | Initiating
12 | 0 | Historial Lessons Learned Review | PM | Review of last year's LL, if cyclical project. | Initiating
13 | 0 | Core Team List | PM, Project Team | Self explanatory. Feeds into Role Definitions. Add team to Task Tracker. | Initiating
14 | 0 | Role Definitions (Project-specific) | PM | Self explanatory. Uses Core Team List. Role definitions should be templated, for easy fill-in. | Initiating
15 | 0 | Business Requirements | PM | The business requirements for a functioning system/process at the end of completion. Uses objectives and scope of the Short-Form Charter. Items numbered and used in the Functional Requirements. | Initiating
16 | 0 | Task List | PM | List of tasks to be performed for the purposes of executing the project. These tasks do not need to have dependencies or duration estimates, which will be investigated in the Project Plan's detailed WBS. | Initiating
17 | 0 | People/Process Impact | PM | A list of people, process, or technology that will be impacted. This should be both within the service center and without. This should be expanded upon from information in the original business case and charter. It should be included as part of the project plan, when that is written. | Initiating
18 | 0 | Resource Allocation ROM | PM | ROM includes # of resources from functional groups. Detailed resource needs will emerge as part of writing the Project Plan. | Initiating
19 | 0 | Risk Log | PM | A list of risks. Includes estimates on severity and likelihood. Used in the Risk Management Plan, in the Project Plan, when developing risk mitigation strategies. | Initiating
20 | 0 | Full Stakeholder List | PM | Expanded list of stakeholders, building off the Stakeholder List from Identify stage. | Initiating
21 | 0 | Communication Framework | PM | Lay out how the project will communicate to stakeholders, including the project team, sponsor, and customers. Uses the Full Stakeholder List. | Initiating
22 | 0 | Testing Framework | PM | A description of the approach for testing, and a list of the business requirements to be met during testing. To be used in creating the Testing Plan. | Initiating
23 | 0 | Training Framework | PM | A desription of the approach needed for training based on the business requirements. To be used in creating the Training Plan. | Initiating
24 | 0 | Roll-out Framework | PM | A desription of the approach needed for rollout, referencing the training framework. To be used in creating the Roll-out Plan. | Initiating
25 | 0 | Exit/Success Criteria | PM | List of critera to be used to determine success/failure of the project. Use the Charter's Scope to help determine. | Initiating
26 | 0 | Electronic Storage Location Created | PM | MWS, SharePoint, S: Drive, etc. | Initiating
27 | 0 | Continuation Approvals | PMO | Use the Full Stakeholder List & Communication Framework. | Initiating
28 | 0 | Project Plan - Scope | PM | Revised from Charter. (Presentation, Approvals) | Planning
29 | 0 | Project Plan - Detailed WBS | PM | Full WBS with estimated duration, estimated work, dependencies, etc. Use Task List and Resource Allocation ROM. | Planning
30 | 0 | Project Plan - Schedule | PM | Separate document to show schedule. (Presentation, Approvals) | Planning
31 | 0 | Project Plan - Project Team | PM | Specific project team members wider than core team. Includes developers and outside folks besides core team. Use Task List and Detailed WBS. | Planning
32 | 0 | Project Plan - Definitive Estimate | PM | Variance of -5% to +10%. Based on Detailed WBS. | Planning
33 | 0 | Project Plan - Programming Work List | PM | Based on Detailed WBS and Functional Requirements | Planning
34 | 0 | Project Plan - Resource Needs | PM | Based on the detailed WBS and Project Team. Includes putting the Resource uses into the RAT. Use the Detailed WBS. | Planning
35 | 0 | Project Plan - Testing Plan | PM | Describes the approach to all development, unit, integration, system, qualification and acceptance testing needed to complete the project properly. Uses the Testing Framework. | Planning
36 | 0 | Project Plan - Roll-out Plan | Prof Dev | A detailed outline of the technical roll-out for the project, including technological readiness checklists. To be implemented during the Deployment phase. Based on the Roll-out Framework. | Planning
37 | 0 | Project Plan - Communication Plan | PM | A delivery method to a determined audience outlining what information needs to be communicated, how and how often the information will be disseminated. Uses the Communication Framework and Full Stakeholder List. | Planning
38 | 0 | Project Plan - Change Management Plan | PM | Outline of steps to take to improve acceptance of new process, technology, and policies. Includes readiness checklist. Uses the Roll-out Plan. | Planning
39 | 0 | Project Plan - Risk Management Plan | PM | The mitigations plans for all risks. To be regularly reviewed to address known unknowns. Uses the Risk Log. | Planning
40 | 0 | Project Plan - Final Document | PM | For Leadership Approval | Planning
41 | 0 | Functional Requirements | PM | The collection of a set of statements which define what needs to be provided by a solution to meet expectations. Uses the Business Requirements. | Execution and Control
42 | 0 | Requirements Traceability Matrix | PM | Link the Business requirements to the Functional requirements to ensure all BR are addressed by FR. | Execution and Control
43 | 0 | Functional/Technical Design | PM | A complex and creative process encompassing a wide range of activities, elements and attributes to develop the end product for the customer. Include Business Process Review, to determine impacted systems. | Execution and Control
44 |  | Development |  | Action. Development taking FTD and building the requested functionality. Can be iterative with testing.
45 | 0 | System Change Document | Technical Lead | Documentation of any system changes for future use during upgrades, other projects, or project work. Reference FD and Programming Work List. | Execution and Control
46 | 0 | Configuration Change Document | Technical Lead | Documentation of any configuration changes for future use during upgrades, other projects, or project work. Reference FD and Programming Work List. | Execution and Control
47 | 0 | Test Plan |  | Minimum includes Conditions, Test Script Integration pages of template. Stored in appropriate JIRA.
48 | 0 | Test Results (Preliminary |  | Stored in appropriate JIRA.
49 | 0 | Test Plan (Final) |  | Stored in appropriate JIRA. | Execution and Control
50 | 0 | Project JIRAs | PM, Project Team | A list of all associated project JIRAs. Best practice is to create a master JIRA for projects, then associate project JIRAs to be closed during the course of the project. | Execution and Control
52 | 0 | Deployment Plan - Communication Plan Review |  |  | Deployment
54 | 0 | Deployment Plan - Training Plan Review |  |  | Deployment
55 | 0 | Deployment Plan - Checklist |  |  | Deployment
56 | 0 | Overall Deployment Plan |  |  | Deployment
57 |  | Roll-out | PM |  | Deployment
58 | 0 | Post-Roll-Out Support | PM |  | Deployment
59 | 0 | Customer Satisfaction Survey | PM |  | Closeout
60 | 0 | Checklist/Next year's plan | PM |  | Closeout
61 | 0 | Exit Criteria Evaluation | PM |  | Closeout
62 | 0 | Success Measurement Document | PM | Evaluation of the project based on the Success Criteria. | Closeout
63 | 0 | Lessons Learned Document | PM | The learning gained from the process of performing the project. | Closeout
64 | 0 | Closeout Approval | PM | The final communication announcing the end of the project, and start of next phase of lifecycle (close, maintainence/operations, etc.) | Closeout